## Tasks
Mobio production backlog |  |  |  | 95 tasks ¦ Edit amber owner/status cells ¦ Filter by priority, scope or owner role
Audit: 27 September 2026 |  |  |  | P0: immediate security/integrity risk ¦ P1: affected-launch gate |  |  | P2: hardening ¦ P3: measured optimization |  |  | Status tracks recommended work, including verification of existing controls.
|  |  |  | Effort S / M / L: narrow / coordinated / cross-system work |  |  | Planning bands, not delivery estimates |  |  | Gate scope follows enabled features; disabled Face does not block core launch.
Tasks | 95 | P0 open | 5 | P1 open | 76 | Complete | 0
ID | Priority | Release scope | Area | Task | Status | Assigned owner | Owner role | Effort | Dependencies | Acceptance criteria | Why this matters | Source evidence
M001 | P0 | Core | Source access | Restrict the public Drive working-copy folder and preserve an access-review record | Not started |  | Security lead + folder owner | S | None | Named access replaces anyone-writer; inherited/child permissions and link access are verified; preserve activity evidence and an incident decision without asserting outsider use. | Root permission metadata confirms anyone-with-link writer access; source and signing material share that folder. | Drive root metadata reviewed 2026-09-27; https://drive.google.com/drive/folders/120JIOTyeNX6nHaHPDqS3UgbaTWyJAE57; audit/platform_review.md PL-01
M002 | P0 | Core | Signing and secrets | Inventory exposed credentials and replace or revoke affected secrets using their actual provenance | Not started |  | Security + Android release owner | M | M001 | Identify owner, purpose, exposure window and actual upload/app-signing role; reset upload keys or revoke credentials as warranted; prove a trusted signed update path and remove exposed copies under retention policy. | Signing configuration and two keystores exist in the publicly editable working-copy upload; current Git index does not track them. | android/key.properties; android/mobi-upload.jks; android/app/upload-keystore.jks; audit/git_index_inventory.json; https://support.google.com/googleplay/android-developer/answer/9842756?hl=en Original source: https://drive.google.com/file/d/1eV0tMds3GICIBCp0yGnF-GDre8fAckk2/view?usp=drivesdk https://drive.google.com/file/d/1Hc8W34L5NqaydBHLhTJN9MXwuk4dwEtJ/view?usp=drivesdk
M003 | P0 | Core | Identity authority | Bind verified WhatsApp/phone identity to an immutable, unique Auth identity | Not started |  | Backend + security | L | M001 | Separate editable contact data from verified login authority; migrate duplicate aliases; verification cannot select or reassign another account; negative fixtures plus real Auth collision behavior pass. Phone-based BioPay discovery also resolves only the canonical verified recipient authority, never an editable contact alias. | Editable profile aliases and newest-created selection can misdirect OTP resolution; mocked helper reproduced wrong selection and a reassignment attempt. | supabase/functions/verify-login-otp/index.ts:80-229; supabase/migrations/20260614153000_rentals_vehicle_type_onboarding.sql:193-243; audit/validation_review.md IV-01; supabase/migrations/20260908090000_biopay_payment_discovery.sql:239-245 Original source: https://drive.google.com/file/d/1rLnSrgP58oGUWfhbZqV18wBkV-xUvuGO/view?usp=drivesdk https://drive.google.com/file/d/1rgP7K6iACtSIV9YJI6_7tmzawe63L1r6/view?usp=drivesdk https://drive.google.com/file/d/1VzfemejMhTryu0KVQFVpt8lxcSH57O4N/view?usp=drivesdk
M004 | P1 | Core | Authorization | Protect identity and privilege columns and audit effective table/RPC grants | Not started |  | Backend + security | M | M003 | Publish effective role/table/column/function matrix; default-deny sensitive updates and security-definer execution; ordinary sessions cannot mutate verified aliases, creation order, member ID or admin authority. Test fn_biopay_discover against attempted editable-phone impersonation. | Own-row policies do not by themselves protect sensitive column authority; accumulated migrations can preserve broad grants. | supabase/migrations/20260501080000_backend_security_payment_rls_hardening.sql; supabase/migrations/20260501110000_security_profile_chat_dashboard_hardening.sql; audit/backend_review.md B-02; supabase/migrations/20260908090000_biopay_payment_discovery.sql:239-245 Original source: https://drive.google.com/file/d/1iPUAzOiUANdBMpfbyHZgffrhTR3njUz1/view?usp=drivesdk https://drive.google.com/file/d/1h4svjoUNZVOu5_kZOWH3XMtGKfnOqP2l/view?usp=drivesdk https://drive.google.com/file/d/1rgP7K6iACtSIV9YJI6_7tmzawe63L1r6/view?usp=drivesdk
M005 | P1 | Core | Member identity | Reconcile duplicate member IDs and enforce atomic unique six-digit allocation | Not started |  | Backend + data migration owner | M | M003; M004 | Duplicate inventory reviewed; controlled remediation preserves account UUIDs and references; unique constraint plus concurrent allocation tests pass; ambiguous recipient lookup fails safely. | Server allocation lacks a uniqueness constraint and existing lookups can choose one ambiguous match. | supabase/migrations/20260324175000_comprehensive_rpcs.sql:40-72; audit/flutter_review.md FL-01; audit/backend_review.md Original source: https://drive.google.com/file/d/13yI6aGP0ZoPmYKSFL-PiftK-FD0VkBO-/view?usp=drivesdk
M006 | P1 | Core | Member identity | Display the authoritative member ID consistently across all client surfaces | Not started |  | Flutter + QA | M | M005 | One fixture displays one server-issued six-digit ID in profile, nearby, trip, chat and wallet; no fabricated fallback; wrong/missing/ambiguous recipient regression cases pass. | Driver cards hash UUIDs, Trips truncates them, and Profile uses different or fixed fallbacks. | lib/shared/widgets/driver_card.dart; lib/features/profile/presentation/profile_screen.dart; lib/features/bookings/presentation/bookings_screen.dart; audit/flutter_review.md FL-01, FL-08 Original source: https://drive.google.com/file/d/133jijD3OWgkiq8kvYppJsiGdn427lgiK/view?usp=drivesdk https://drive.google.com/file/d/18urTvEQkxOoO54RdPEqF3hG6P_FLgWYX/view?usp=drivesdk
M007 | P1 | Core | Account lifecycle | Implement ordinary sign-out with finally-safe local and native cleanup | Not started |  | Flutter + native platform owners | M | M003 | Offline exit clears local credentials, account state, drafts/listeners and camera/NFC/location activity; cleanup failures cannot restore access; account A data never appears after B signs in. | Only Exit Admin invokes account exit; failed cleanup can prevent sign-out and current helper can retain the prior authenticated session. | lib/app/router/screen_wrappers.dart:120-130; lib/core/auth/supabase_session_service.dart:61-81; audit/flutter_review.md FL-02 Original source: https://drive.google.com/file/d/1q4klsIHCcBSAx3BdaRdwzqNC3X2zD7jq/view?usp=drivesdk https://drive.google.com/file/d/1yXHyXe8vVhu5ITKzP5IYgndcRKLU0V5O/view?usp=drivesdk
M008 | P1 | Core | Push identity | Revoke FCM association before losing its owning session and atomically bind device ownership | Not started |  | Flutter + backend | M | M007 | Two-account device test receives only current-owner messages; captured identity is rechecked around token retrieval/upsert; anonymous registration rejected; stale-token expiry and revocation verified. | Current signed-out cleanup runs under an identity that cannot delete the prior own-row token; anonymous refresh also needs rejection. | lib/app/shell.dart; lib/features/notifications/data/push_notification_service.dart:343-418; audit/flutter_review.md FL-03 Original source: https://drive.google.com/file/d/1g_9q58Z-2302LqjJteF3pqrzqIRnUCUA/view?usp=drivesdk https://drive.google.com/file/d/1pMxjMX11Yc0j6Gmpp5TvuMC7eVce0itE/view?usp=drivesdk
M009 | P1 | Core | Admin security | Define and enforce admin idle, absolute lifetime and sensitive-action authentication | Not started |  | Security + backend + Flutter | M | M003; M007 | Retained timeout requirements are enforced server-side and reflected in UI; idle/background/resume/refresh/role-revocation tests pass; high-impact operations require the agreed admin purpose. | Advertised 15-minute timeout affects a fallback flag while an admin role can remain authoritative indefinitely in the client guard. | lib/core/auth/admin_session_guard.dart; lib/app/router/app_router.dart; audit/flutter_review.md FL-04; audit/backend_review.md Original source: https://drive.google.com/file/d/1X7sWfPgFxAKSm-EZLwKq7SmuvRQHnOlH/view?usp=drivesdk https://drive.google.com/file/d/10iUOdZWSzYH51vT01fjN0BBQsTULtV9D/view?usp=drivesdk
M010 | P1 | Core | Credential storage | Migrate native refresh-session persistence to supported OS-protected storage | Not started |  | Flutter + security | M | M007 | At-rest/backup inspection and migration, restart, sign-out, reinstall and revocation tests pass on Android/iOS; recovery behavior is documented; browser storage is addressed separately. | Supabase initialization uses default local storage; no custom protected native adapter is configured. | lib/app/bootstrap.dart:79-82; audit/flutter_review.md FL-10; https://pub.dev/packages/supabase_flutter Original source: https://drive.google.com/file/d/16rAbretfd1HwG3q_qLdo6WHrvbIB061u/view?usp=drivesdk https://drive.google.com/drive/folders/1VeEGNOl32YcDgwjU7FZhqwcj_7Vyqy6c
M011 | P1 | Core | Review access | Constrain the store-review identity to monitored synthetic data and rotate its access | Not started |  | Security + release + backend | M | M003; M009 | Review account has approved minimal access and no real-user financial/biometric records; rate cap, audit monitoring and rotation procedure work; live OTP-claim semantics remain enforced. | Fixed review OTP flow still creates an ordinary consumer identity and bypasses some send throttling/Integrity checks; no admin bypass was demonstrated. | supabase/functions/_shared/play-review-login.ts; supabase/functions/send-login-otp/index.ts; audit/backend_review.md B-11 Original source: https://drive.google.com/file/d/1GNs7SS0ZnkVMp96ZipCG6lOqW77dNTcK/view?usp=drivesdk https://drive.google.com/file/d/14OGjfqPCwD8YXGL1_8RJVacWZZLazQZ1/view?usp=drivesdk
M012 | P1 | Core | OTP production config | Reject OTP dry-run in production and redact all authentication secrets | Not started |  | Backend + DevOps | S | M002 | Deployment gate rejects WHATSAPP_CLOUD_DRY_RUN in production; sanitized config readback and log fixtures show no OTP/full phone; testing still uses explicitly isolated fixtures. | Dry-run logs complete phone/code and reports send success, creating an unsafe production configuration. | supabase/functions/_shared/whatsapp-cloud.ts:218-220; audit/privacy_review.md PRIV-09 Original source: https://drive.google.com/file/d/12qJwdf1UXnXqeY3d1I9ttnFYZhMZ77pT/view?usp=drivesdk
M013 | P2 | Core | Abuse prevention | Choose an explicit Play Integrity policy and bind/consume protected requests | Not started |  | Android + backend + security | M | M003; M091 | Document acceptable device/app verdicts and exceptions; replay/content-substitution fixtures fail where required; monitor-to-enforce decision uses measured false rejects and does not indiscriminately block users. | Classic token validation logs device verdicts without policy checks; nonce is not bound to request content or consumed once. | supabase/functions/_shared/play-integrity.ts:66-72,118-298; audit/backend_review.md B-10; https://developer.android.com/google/play/integrity/classic Original source: https://drive.google.com/file/d/1D17M-jpEvOSKaBtoBJFHNSl_V1u-p1zf/view?usp=drivesdk
M014 | P2 | Core | Web session security | Verify admin browser persistence, CSP and session revocation against an explicit threat model | Not started |  | Web + security | M | M009 | Approved persistence policy, effective headers and browser expiry/revoke/role-change tests recorded; cached pages and service workers expose no prior-account sensitive data. | Native secure storage does not address web token exposure, cached admin content or long-lived browser sessions. | audit/flutter_review.md FL-10; scripts/web/admin_service_worker.js; scripts/tests/admin_service_worker.test.mjs; audit/validation_review.md Node Pages/Admin scope Original source: https://drive.google.com/file/d/1AclcH-_QKjPYyyPzDbMD-36G3H2OV87A/view?usp=drivesdk https://drive.google.com/file/d/16ZESpb117vIxtZrIiAGQhMaJiPaz_oh3/view?usp=drivesdk
M015 | P0 | Paid transport | Booking authorization | Remove passenger authority to self-confirm or mark a booking paid | Not started |  | Backend + security | M | M004 | Direct PostgREST attempts to set confirmed/paid, paid_at, receipt, price, route or seat authority fail for passengers; only trusted transactional RPCs can make valid transitions. | Owner UPDATE grant and row policy permit mutation beyond legitimate held-booking fields. | supabase/migrations/20260608093000_public_transport_booking_foundation.sql:253,401-413; audit/backend_review.md B-01; audit/validation_review.md IV-03 Original source: https://drive.google.com/file/d/1PcLY4jkG2pCwPilr22NSbzjK9LsjgnEV/view?usp=drivesdk
M016 | P0 | SMS | Receipt integrity | Require strong payment evidence before automatic subscription activation | Not started |  | Backend + payments owner | L | M020; M026 | Non-payment, uncertain, missing-reference, wrong merchant/currency and ambiguous fixtures cannot credit; require classified payment plus stable provider reference and intended payer/invoice binding; quarantine for reviewed resolution. | Parser forwards negative/low-confidence messages; allocator can match only amount/time without payer/member/reference. | supabase/functions/_shared/momo-sms.ts:155-200; supabase/functions/momobio-sms-ingest/index.ts:52-73; supabase/migrations/20260906145000_subscription_receipt_integrity.sql:156-219; audit/validation_review.md IV-02 Original source: https://drive.google.com/file/d/1VLrjCisiaiRqSAoExNMKwOtQXGdWo2TW/view?usp=drivesdk https://drive.google.com/file/d/1ABtcrIk1N1ve9MSKEpHlyDgu4FLI8yKi/view?usp=drivesdk
M017 | P1 | Paid transport | Seat inventory | Make booking holds idempotent and durably expire/release seats | Not started |  | Backend + database QA | M | M015 | Bounded expiry job, cancellation and hold idempotency work; concurrent last-seat/expiry/confirmation tests conserve inventory and never produce negative or stranded seats. | Repeated holds decrement inventory; an expired status update is rolled back by a raised exception; no durable sweeper was found. | supabase/migrations/20260611170000_public_transport_rpc_column_qualification.sql:7-160; audit/backend_review.md B-04; audit/validation_review.md IV-05 Original source: https://drive.google.com/file/d/1FyZe9Prez95TVZQwyrYGKgBf7Fw0XAm3/view?usp=drivesdk
M018 | P1 | Paid transport | Payment receipts | Bind one provider receipt atomically to one intended booking and exact amount/currency | Not started |  | Backend + payments owner | M | M015; M020 | Duplicate reference on same booking is idempotent; reference reuse on another booking is rejected; amount/currency and issuer authority are checked under concurrent confirmation. | Receipt upsert conflict handling does not prevent a reused reference from confirming another booking. | supabase/migrations/20260611170000_public_transport_rpc_column_qualification.sql:163-204; audit/backend_review.md B-05 Original source: https://drive.google.com/file/d/1FyZe9Prez95TVZQwyrYGKgBf7Fw0XAm3/view?usp=drivesdk
M019 | P1 | SMS | Subscription periods | Serialize paid subscription renewals by profile and vehicle type | Not started |  | Backend + database QA | M | M016 | Deterministic two-session test with distinct receipts preserves both paid durations without overlap; duplicate invoice retry creates exactly one activation; expiry boundaries are explicit. | Distinct invoices lock distinct requests and can read the same maximum period end before insertion. | supabase/migrations/20260906145000_subscription_receipt_integrity.sql:298-390; audit/backend_review.md B-06; audit/validation_review.md IV-04 Original source: https://drive.google.com/file/d/1VLrjCisiaiRqSAoExNMKwOtQXGdWo2TW/view?usp=drivesdk
M020 | P1 | SMS | Merchant configuration | Make merchant identity, currency and receipt formats explicit validated configuration | Not started |  | Payments operations + backend | M | Approved merchant/operator inventory | Each enabled collector maps to approved merchant/account/operator/currency and parser fixtures; missing or wrong configuration blocks auto-credit with visible reason; no guessed merchant identifier. | A missing merchant code can become a fabricated default, weakening invoice matching and auditability. | supabase/migrations/20260906145000_subscription_receipt_integrity.sql; supabase/functions/_shared/momo-sms.ts; audit/backend_review.md B-03 Original source: https://drive.google.com/file/d/1VLrjCisiaiRqSAoExNMKwOtQXGdWo2TW/view?usp=drivesdk https://drive.google.com/file/d/1jy2qeudD4ypMt6bl6SltIQwb3KGpece7/view?usp=drivesdk
M021 | P1 | Core | Financial retries | Use durable account-scoped wallet operation IDs and reconcile uncertain outcomes | Not started |  | Flutter + backend | M | M003; M006; M054 | Response loss, process restart, account switch and failed storage retain correct operation identity or block unsafe retry; committed operation is discoverable; duplicate retry cannot charge twice. | Existing keys omit owner identity, expose raw note in preference keys and ignore persistence failure; UI promises stronger retry safety. | lib/features/profile/presentation/wallet_screen.dart:782-828; audit/flutter_review.md FL-13 Original source: https://drive.google.com/file/d/1LlppucPRV_7Kpp3kh07UDhWL39XAPyVI/view?usp=drivesdk
M022 | P1 | Paid transport | Financial boundaries | Specify and test refunds, cancellation, monetary precision and time boundaries | Not started |  | Product + payments + backend | M | M017; M018; M019; M024 | Approved rules and tests cover invalid/zero/negative/large amounts, currency, timezone/day rollover, duplicate refund, cancellation after payment and reconciliation; no new settlement engine is introduced. | Release needs a complete operating contract for already implemented paid booking/subscription/reward paths. | audit/backend_review.md recommended tasks; docs/product/public_transport_tracking_booking_scope_2026-06-08.md; audit/privacy_review.md section 5 Original source: https://drive.google.com/file/d/11YYuUj98ZIEPP48aikNWMtWIGKOcwybM/view?usp=drivesdk
M023 | P1 | SMS | Financial reconciliation | Reconcile collector receipts, ingestion outcomes and activated invoices with operator records | Not started |  | Payments operations + backend | M | M016; M028; M034 | Daily exception report reconciles eligible receipts, duplicate/rejected/quarantined cases and credits to trusted operator evidence; lost receipt/manual resolution is audited without permissive auto-match. | A missed SMS broadcast, device failure or ambiguous match can otherwise silently deny or misapply a paid entitlement. | apps/momobio_sms_bridge/app/src/main/java/com/momobio/app/SmsReceiver.kt; audit/platform_review.md PL-06; audit/backend_review.md B-03 Original source: https://drive.google.com/file/d/14Xk8YpNg33EJncxUz4ZFh08gXr_v_0gT/view?usp=drivesdk
M024 | P1 | Paid transport | Operating authority | Obtain a feature-specific payments/transport classification and responsibility decision | Not started |  | Product lead + qualified Rwanda counsel | M | Feature and funds-flow draft; coordinate with refund design | Current primary rules and actual funds flow support a written decision for each enabled paid feature; provider/agency contracts, responsible entity and customer promises are recorded; unresolved features stay disabled. | Actual funds flow, merchant ownership, agency agreements, refunds and reward terms were not supplied; no licence conclusion was possible. | audit/privacy_review.md section 5; docs/product/public_transport_tracking_booking_scope_2026-06-08.md Original source: https://drive.google.com/file/d/11YYuUj98ZIEPP48aikNWMtWIGKOcwybM/view?usp=drivesdk
M025 | P1 | SMS | Collector signing | Replace debug-keystore operational packaging with a managed production signing/update path | Not started |  | Android release + fleet operations | M | M002 | Distribution artifact uses approved managed signing; signature/version verified; enrolled request-signing identity and pending receipts survive supported updates or a documented controlled migration. | device_uat.sh signs release output with the standard debug keystore; enrolled keys and queued receipts need a safe upgrade. | apps/momobio_sms_bridge/scripts/device_uat.sh:69-76; apps/momobio_sms_bridge/app/build.gradle.kts; audit/platform_review.md PL-04 Original source: https://drive.google.com/file/d/1MLWnXsRSeoudgNb9hkGCqMeXVXFZumKJ/view?usp=drivesdk https://drive.google.com/file/d/13unWV3K7o-vQdJnFfdpVzk5xZckDNc47/view?usp=drivesdk
M026 | P1 | SMS | Collection minimization | Filter eligible receipt data on-device and present a clear upload/AI-processing notice | Not started |  | Android + privacy + payments | M | M020 | Unrelated sender/content fixtures never enter queue or network; notice explains purpose, recipients, retention and support before access; changed formats route to minimal controlled review without auto-credit. | Receiver currently queues and uploads all new SMS before server filtering; dedicated private distribution does not justify unrelated collection. | apps/momobio_sms_bridge/app/src/main/java/com/momobio/app/SmsReceiver.kt; SmsReceiptDecoder.kt; UploadClient.kt; audit/platform_review.md PL-05; audit/privacy_review.md PRIV-03 Original source: https://drive.google.com/file/d/14Xk8YpNg33EJncxUz4ZFh08gXr_v_0gT/view?usp=drivesdk
M027 | P1 | SMS | Distribution policy | Document private fleet distribution and obtain SMS/FGS approval if using public Play | Not started |  | Android release + compliance | S | M025; M026 | Actual channel and authorized device population recorded; applicable Play exception/permission and foreground-service review evidence supplied before public distribution; private-policy claims match access controls. | Bridge is documented in-house; public Play distribution would introduce restricted SMS permissions and declaration requirements. | apps/momobio_sms_bridge/README.md; app/src/main/AndroidManifest.xml; https://support.google.com/googleplay/android-developer/answer/10208820; audit/platform_review.md PL-05 Original source: https://drive.google.com/file/d/1THqrvAz2dVb6sLK6RTD8BeIcaQEcY1pG/view?usp=drivesdk https://drive.google.com/file/d/1qFn0W9M6GEXpT3ZhuSm-AyB38Qxnkqah/view?usp=drivesdk
M028 | P1 | SMS | Durable queue | Use a transactional bounded receipt queue with corruption quarantine and retained acknowledgement state | Not started |  | Android + backend | M | M026 | Crash/restart/disk-full/corrupt-row and partial-ack tests preserve eligible records; bounded batches/age/bytes and dedupe retention verified; capacity alerts precede exhaustion; migration is lossless. | Whole-queue preference JSON and unbounded hash history are fragile; malformed rows can disappear during a later save. | apps/momobio_sms_bridge/app/src/main/java/com/momobio/app/SmsQueue.kt; audit/platform_review.md PL-06; audit/privacy_review.md PRIV-08 Original source: https://drive.google.com/file/d/1-yEWiItXERM_jmBtgePmT13WZUNUb0g-/view?usp=drivesdk
M029 | P1 | SMS | Retry coordination | Centralize collector work leasing, backoff and response handling | Not started |  | Android + backend | M | M028 | One shared batch lease prevents concurrent uploads; bounded jitter/backoff handles 429/503/network loss; each attempt retains fresh nonce/signature; partial-success retries cannot duplicate credits. | UI, service and WorkManager retries can compete; per-instance flags do not coordinate work or honor Retry-After. | apps/momobio_sms_bridge/app/src/main/java/com/momobio/app/BridgeSupervisor.kt; BridgeForegroundService.kt; BridgeSyncWorker.kt; UploadClient.kt; audit/platform_review.md PL-07 Original source: https://drive.google.com/file/d/1TCLP0gLC0lyCHAF9vvir7CxcwCzRi3Ob/view?usp=drivesdk
M030 | P1 | SMS | Collector lifecycle | Verify boot, force-stop, OEM battery and Android job-quota behavior on managed devices | Not started |  | Android QA + fleet operations | M | M025; M028; M029 | Real fleet models pass reboot/update/offline/process-death/Doze/restricted-permission cases; force-stop and OEM limitations are visible with reconciliation instructions; no fictitious always-on guarantee. | WorkManager and foreground services do not guarantee timely capture under every device state; receipt history is not reread. | apps/momobio_sms_bridge/app/src/main/java/com/momobio/app/BridgeBootReceiver.kt; audit/platform_review.md device matrix; https://developer.android.com/about/versions/16/behavior-changes-all Original source: https://drive.google.com/file/d/1SOpL0EkATxERvbJo2lw_eXGk2mIefSgp/view?usp=drivesdk
M031 | P1 | SMS | Legacy ingest authority | Inventory deployed legacy SMS callers and retire or harden shared-secret ingest aliases | Not started |  | Backend + security + operations | M | M016; M029 | Deployed endpoint/caller inventory complete; unused routes return a controlled retirement response; retained routes use registered collector authority, replay/body/rate bounds and monitored migration. | parse-sms and reconcile-momo-sms preserve older global-secret paths without per-collector replay/revocation controls. | supabase/functions/parse-sms/index.ts:22-42; supabase/functions/reconcile-momo-sms/index.ts:22-42; audit/backend_review.md B-08 Original source: https://drive.google.com/file/d/1snmFTu4PpKv7cY09FBswSVfAuSWoy_-f/view?usp=drivesdk https://drive.google.com/file/d/1Q_gKdjfTVAO5JjxLkfYPMHPt1hfo1vtr/view?usp=drivesdk
M032 | P1 | SMS | Backend intake | Persist authenticated receipt admission before asynchronous parsing and allocation | Not started |  | Backend + SRE | M | M016; M028; M029 | Durable per-message intake/outcome identity; bounded worker with leases/retry/dead-letter handling; crash after first item or lost final acknowledgement yields one financial effect and reproducible status. | Sequential AI/SQL processing can partially commit a batch then return a transient failure; repeat parsing increases cost and uncertainty. | supabase/functions/momobio-sms-ingest/index.ts; audit/backend_review.md collector strengths and partial-batch risk Original source: https://drive.google.com/file/d/1ABtcrIk1N1ve9MSKEpHlyDgu4FLI8yKi/view?usp=drivesdk
M033 | P1 | SMS | Fleet security | Establish dedicated institutional devices/SIMs, enrollment, revocation and replacement procedures | Not started |  | Fleet operations + security | M | M025; M026; M027 | Named custodians and inventory; dedicated SIM restriction, screen/device protection, enrollment approval, lost-device revocation, replacement/export policy and staff training rehearsed with no personal-SMS collection. | Financial SMS and enrolled collector authority need controlled hardware ownership and incident handling. | apps/momobio_sms_bridge/README.md; audit/privacy_review.md PR-T06; audit/platform_review.md PL-04 to PL-07 Original source: https://drive.google.com/file/d/1THqrvAz2dVb6sLK6RTD8BeIcaQEcY1pG/view?usp=drivesdk https://drive.google.com/file/d/1qFn0W9M6GEXpT3ZhuSm-AyB38Qxnkqah/view?usp=drivesdk
M034 | P1 | SMS | Collector health | Expose truthful enrolled/configured/connected/acknowledged state and backlog age | Not started |  | Android + operations | M | M028; M029; M032 | Missing config, expired/revoked key, denied permission and server outage have distinct states; last successful server acknowledgement and oldest eligible receipt are visible and alertable. | Empty queues can report success before configuration is checked and UI may show Running without a usable enrolled backend. | apps/momobio_sms_bridge/app/src/main/java/com/momobio/app/MainActivity.kt; UploadClient.kt; audit/platform_review.md PL-07 Original source: https://drive.google.com/file/d/1VaIxl4s-bYjAbwW0zj8QP29_x09Ag4sb/view?usp=drivesdk
M035 | P1 | Face | Face release policy | Keep Face-USSD disabled until exact current scope is accepted and health surfaces agree | Not started |  | Product + backend + release | M | M036; M037; M038; M039; M040; M067; M068 | One versioned decision binds approved no-liveness recipient lookup, model/policy/index and health semantics; enablement requires acceptance; manual/QR alternatives remain usable; dialer launch never means settlement. | September policy is intentionally disabled/unthresholded; older admin status still hardcodes not-ready and historical AWS requirements are superseded. | docs/product/face-ussd-20260920/APPROVAL.md; supabase/migrations/20260920150000_biopay_face_shortcut.sql; audit/validation_review.md section 2 Original source: https://drive.google.com/file/d/1xop9aCYCPDg70qLFnM9fyHhWzGvx-Vc1/view?usp=drivesdk https://drive.google.com/file/d/1Ql7MVmCXqbgiB8DwU11kDXAjNmRtYF-k/view?usp=drivesdk
M036 | P1 | Face | Inference artifact | Build and verify the exact Linux inference image, models and private service bindings | Not started |  | Platform + ML engineer | M | M077; M082 | Immutable image/model digests and licences recorded; real health/embed tests pass in Linux container; Worker authentication, private binding, index dimension/version and environment isolation verified. | Historical implementation report did not complete the Docker image or production model deployment. | services/face-inference/Dockerfile; cloudflare/face-service/wrangler.jsonc; docs/product/face-ussd-20260920/IMPLEMENTATION_REPORT.md; audit/operations_review.md OPS-04 Original source: https://drive.google.com/file/d/13toaULZ0qSRF3mcOySrbey9WeHRMSidj/view?usp=drivesdk https://drive.google.com/file/d/10XfUXtvPdRtBHiWA9yhRro_v6glk8XvJ/view?usp=drivesdk
M037 | P1 | Face | Deployment contracts | Rehearse latest face migrations, PostgREST/Edge, Vault and scheduled maintenance together | Not started |  | Backend + platform + database QA | M | M036; M078 | Full-schema rehearsal verifies exact RPC argument/privilege/session contract; deployment history, secrets presence and scheduled execution read back; activation and deletion converge after provider interruption. | Source health checks and cleanup implementations do not establish target schema parity or an executing maintenance schedule. | supabase/migrations/20260920150000_biopay_face_shortcut.sql; supabase/functions/biopay-face-provider/index.ts; docs/operations/face-ussd-runbook.md; audit/operations_review.md O05,O08 Original source: https://drive.google.com/file/d/1xop9aCYCPDg70qLFnM9fyHhWzGvx-Vc1/view?usp=drivesdk https://drive.google.com/file/d/1rDo-iJSUPd_QhiakftQOghMtlmsk2P6S/view?usp=drivesdk
M038 | P1 | Face | Matching acceptance | Calibrate and independently accept matching thresholds and cross-owner margins | Not started |  | ML QA + product + privacy | L | M036; M067; M068 | Pre-agreed error/latency criteria; held-out consented cohort covering lighting, skin tones, age and devices; report denominators, gallery size, uncertainty and thresholds/model hash; ambiguous matches fail safely. | No consented held-out cohort or gallery-scale false-match/false-nonmatch evidence was established for the active SFace path. | services/face-inference/inference.py; cloudflare/face-service/src/handler.ts; docs/product/face-ussd-20260920/IMPLEMENTATION_REPORT.md; audit/operations_review.md OPS-04 Original source: https://drive.google.com/file/d/13toaULZ0qSRF3mcOySrbey9WeHRMSidj/view?usp=drivesdk https://drive.google.com/file/d/1ZMe2Z6-28lqVhf4GD24uS02hOaPsgsYZ/view?usp=drivesdk
M039 | P1 | Face | Biometric deletion | Exercise pause/remove/replacement and delayed-upsert cleanup end to end | Not started |  | Backend QA + privacy + operations | M | M036; M037 | Immediate discovery exclusion plus eventual verified vector absence; cancellation, replacement, delayed insert, provider outage and restored-backup cases pass; cleanup owner/SLA and tombstone retention approved. | SQL exclusion and retryable vector cleanup exist but observed external absence and production cleanup SLA are not proven. | docs/operations/face-ussd-runbook.md; supabase/functions/biopay-face-maintenance; audit/privacy_review.md PR-T10; audit/validation_review.md section 2 Original source: https://drive.google.com/drive/folders/1Yd3ushY1JBVNcm_zloDSgVpLwQt-k867 https://drive.google.com/file/d/1vZVjzSVzBGDPvEDyH5wTO996VJbSCDGt/view?usp=drivesdk
M040 | P1 | Face | Camera-to-USSD acceptance | Run physical-device face capture through one correct operator dialer handoff | Not started |  | Mobile QA + operator liaison | M | M036; M037; M038; M046; M051 | Selected receiving method/number resolves correctly; changed/paused payee, timeout, interruption, cancellation, restart, dual-SIM and denial cases pass; one amount-free Android handoff; iOS fallback is clear. | Lifecycle and at-most-once safeguards are strong in source, but current build/operator/dual-SIM evidence was not executed. | lib/features/biopay/presentation/biopay_face_scan_screen.dart; lib/features/biopay/domain/face_shortcut.dart; android/app/src/main/kotlin; audit/flutter_review.md strengths; audit/platform_review.md Original source: https://drive.google.com/file/d/1VQx1_L_ad_B0ir4GoXgkwo9Em7fVeaMh/view?usp=drivesdk https://drive.google.com/file/d/1FpuSdHRpxtU6abvwywD3Q0WKOZWat9ma/view?usp=drivesdk
M041 | P1 | Face | Launch capacity | Measure cold/warm latency, burst admission and regional network performance at the launch workload | Not started |  | Performance + platform + ML | M | M036; M038 | Approved workload and p95/error budget met from target Rwandan networks; report busy/cold-start/index latency/memory/CPU; bounded capacity and safe retry decisions use results rather than autoscaling assumptions. | Single serialized container and repeated index compatibility calls impose an unmeasured capacity limit. | cloudflare/face-service/wrangler.jsonc:9; src/handler.ts:90-165; services/face-inference/inference.py:32-88; audit/operations_review.md OPS-05 Original source: https://drive.google.com/file/d/10XfUXtvPdRtBHiWA9yhRro_v6glk8XvJ/view?usp=drivesdk https://drive.google.com/file/d/140d2FVWo8zH96uUG9K55Svsd5twTSLzR/view?usp=drivesdk
M042 | P2 | Face | Inference serving | Use bounded production HTTP serving with graceful drain and failure limits | Not started |  | Backend + platform | M | M036; M041 | Saturation, slow/truncated/oversized body, concurrent request, termination during inference and restart tests pass; no raw payload logs or arbitrary URL fetch; concurrency and deadlines remain bounded. | ThreadingHTTPServer lacks a bounded serving pool and graceful process drain; private binding reduces exposure but does not prove robust serving. | services/face-inference/server.py:1,35; audit/operations_review.md OPS-09; https://docs.python.org/3.12/library/http.server.html Original source: https://drive.google.com/file/d/1UjDIz7n8Uk4OhFXYNLmB3vShd_P1ziTY/view?usp=drivesdk
M043 | P1 | Face | Face state consistency | Test cross-system enrollment/lookup races and fail-closed identity transitions | Not started |  | Backend + Flutter QA | M | M037; M039; M055 | Concurrent enrollment/replacement, account switch, consent withdrawal, route change, expired ticket, model mismatch and ambiguous result cannot produce a stale payee handoff; retries preserve at-most-once semantics. | Vector availability, SQL consent/owner/method state and client ticket state must agree despite asynchronous work. | lib/features/biopay/domain/face_shortcut.dart; supabase/migrations/20260920150000_biopay_face_shortcut.sql; cloudflare/face-service/src/handler.ts; audit/flutter_review.md Original source: https://drive.google.com/file/d/1xop9aCYCPDg70qLFnM9fyHhWzGvx-Vc1/view?usp=drivesdk https://drive.google.com/file/d/1FpuSdHRpxtU6abvwywD3Q0WKOZWat9ma/view?usp=drivesdk
M044 | P1 | Core | Android release | Target API 36 and verify Android 16 behavior for the consumer release | Not started |  | Android + Flutter + QA | M | M074; M077 | Release manifest confirms target36; edge-to-edge, predictive back, large-screen layouts, foreground services and permissions pass; actual Play preflight/extension status recorded separately from existing-app availability. | Main app compiles with 36 but targets 35; current Play new/update submission requirement is 36 from 2026-08-31, absent a verified extension. | android/app/build.gradle.kts; https://support.google.com/googleplay/android-developer/answer/11926878?hl=en; https://developer.android.com/about/versions/16/behavior-changes-16; audit/platform_review.md PL-02 Original source: https://drive.google.com/file/d/1v5ftCzLKueY28L_0UpgcByPB0Hc4qHF5/view?usp=drivesdk
M045 | P1 | Core | Android native libraries | Verify every shipped native library and release package on 16 KB pages | Not started |  | Android release + QA | M | M044; M081 | Inspect exact AAB/APKs and ELF/RELRO alignment, run zip alignment checks, install and exercise native/camera paths on 16 KB device/emulator; retain artifact evidence before 2027-02-01 update enforcement. | Modern AGP supports packaging but does not prove all Flutter/plugin prebuilts and ELF segments comply. The current Play requirement concerns API35+ apps on 64-bit devices. | android/settings.gradle.kts; android/app/build.gradle.kts; https://developer.android.com/guide/practices/page-sizes; audit/platform_review.md PL-09 Original source: https://drive.google.com/file/d/1v5ftCzLKueY28L_0UpgcByPB0Hc4qHF5/view?usp=drivesdk https://drive.google.com/file/d/1Cr3nlB2FWbztO4CXBBZMibfRduyk2Rfa/view?usp=drivesdk
M046 | P1 | Core | iOS release | Produce a signed Xcode 26+ archive and verify production entitlements/device behavior | Not started |  | iOS release + QA | M | M002; M077; M081 | Xcode/iOS SDK versions asserted; signed archive entitlements/provisioning verified; TestFlight install, APNs, camera/location/NFC and recovery pass on supported iPhones; no native macOS product is implied. | Current iOS check is --no-codesign; a build on a macOS host is not proof of signing, APNs, NFC or TestFlight operation. | scripts/ci/verify_ios_release.sh:51; ios/Runner/Info.plist; ios/Runner/Runner.entitlements; https://developer.apple.com/news/upcoming-requirements/; audit/platform_review.md PL-03 Original source: https://drive.google.com/file/d/1A2RP5xT5ZyUTrF_MafKUGssYZ_4pWp8k/view?usp=drivesdk https://drive.google.com/file/d/1BVpHj8Sp2PkZtlB_oR1YIVBzyihEFZRJ/view?usp=drivesdk
M047 | P1 | Core | NFC lifecycle | Enforce NFC advertisement expiry and owner lifecycle in the native APDU service | Not started |  | Android + Flutter | M | M007; M055 | Expired, signed-out, reset, changed-owner and restarted states cannot serve stale payload; exact APDU validation tested; explicit stop clears persistent material and UI reflects current state. | Persistent enabled/raw USSD payload can survive navigation or process restart; native read does not enforce expiry. | android/app/src/main/kotlin/rw/mobi/app/BioPayHostApduService.kt; MainActivity.kt; lib/features/biopay/presentation/biopay_nfc_screen.dart:51-62; audit/platform_review.md PL-08 Original source: https://drive.google.com/file/d/1E9pNYeMyNT7Wn5T7DP805IDmicfiFVEc/view?usp=drivesdk https://drive.google.com/file/d/13xDP1FXYO1bq-kP2l81oWO6ytezyfSTZ/view?usp=drivesdk
M048 | P1 | Core | Verified links | Verify Android App Links and iOS Universal Links against actual signed application identities | Not started |  | Mobile + web release QA | S | M002; M044; M046 | Production association files match package/bundle and current signing identities; payment/auth/admin link open, malformed link, browser fallback and reinstall cases pass without open redirects or account confusion. | Source associations and deep-link routes do not establish deployed domain verification or safe behavior in every installation state. | android/app/src/main/AndroidManifest.xml; ios/Runner/Runner.entitlements; landing/.well-known; https://developer.android.com/training/app-links/verify-applinks; audit/platform_review.md Original source: https://drive.google.com/file/d/1CshVCQSVniVLcrD_P0He9olWV0jRsK5f/view?usp=drivesdk https://drive.google.com/file/d/1BVpHj8Sp2PkZtlB_oR1YIVBzyihEFZRJ/view?usp=drivesdk
M049 | P1 | Core | Permissions and FGS | Align minimum permissions, background location and foreground-service declarations with visible product use | Not started |  | Android/iOS + privacy + release | M | M056; M065 | Permission-denied/revoked/background states behave safely; background location disclosure/video and applicable FGS purpose declarations accepted for actual release; no unused permissions or misleading always-on promise. | Main app requests background location and native features that require accurate disclosures and real device/state acceptance. | android/app/src/main/AndroidManifest.xml; ios/Runner/Info.plist; https://support.google.com/googleplay/android-developer/answer/9799150?hl=en; https://developer.android.com/develop/background-work/services/fgs/service-types; audit/platform_review.md PL-10 Original source: https://drive.google.com/file/d/1CshVCQSVniVLcrD_P0He9olWV0jRsK5f/view?usp=drivesdk https://drive.google.com/file/d/171_14QerVA_QQJxoY7pX9do6v_YMrT5c/view?usp=drivesdk
M050 | P1 | Core | SDK privacy | Audit bundled SDK data collection, required-reason APIs and archive privacy manifests | Not started |  | iOS/Android + privacy | M | M046; M065; M068 | Final archive privacy report and Android SDK inventory map actual collection to notices/store answers; necessary manifests/reasons present; analytics/ads dependencies and consent choices are justified by measured configuration. | No first-party manifest was found; Firebase/analytics/conversion SDK footprint requires actual archive and behavior review, not an assumption of tracking. | ios/Podfile.lock; ios/Runner; pubspec.lock; audit/platform_review.md PL-10; https://developer.apple.com/documentation/bundleresources/privacy-manifest-files Original source: https://drive.google.com/file/d/1Zkr32UrCgElDUhIuBrQVciYfKFsxCaZp/view?usp=drivesdk https://drive.google.com/file/d/11FVzDpJjUtz-PxJtvaPmIsqcYDCZq3WC/view?usp=drivesdk
M051 | P1 | Core | Operator continuity | Validate USSD/SMS on current Rwanda operators, SIM options and 4G/VoLTE devices | Not started |  | Operator liaison + mobile QA | M | M044; M046 | Approved handset/SIM/operator matrix covers dual-SIM, permission defaults, low coverage and 4G/VoLTE; track 2027-06-30 3G transition guidance without claiming USSD disappears; collector hardware choice is evidence-based. | Dialer and collector behavior is operator/device dependent; announced 3G sunset changes procurement and regression needs. | audit/platform_review.md device matrix; audit/privacy_review.md section 6; https://www.minict.gov.rw/news-detail/rwanda-to-switch-off-3g-networks-on-30-june-2027
M052 | P1 | Core | Store readiness | Reconcile store content, version identity, age-rating questions and reviewer instructions | Not started |  | Release + product + privacy | M | M011; M044; M046; M050; M065 | Current feature scope, screenshots, support/privacy/deletion URLs, permissions and age-rating answers agree with signed artifact; exact version/build and review access verified; draft/internal submission reviewed before publication. | Store text omits current features and iOS camera copy still names retired AWS; exact submitted artifact/version evidence is required. | ios/Runner/Info.plist; android/fastlane/metadata; docs/release; audit/platform_review.md PL-10; https://developer.apple.com/news/upcoming-requirements/ Original source: https://drive.google.com/drive/folders/1zahDeIbIAOW55lWawkAqajb_BhrPLZsg https://drive.google.com/file/d/171_14QerVA_QQJxoY7pX9do6v_YMrT5c/view?usp=drivesdk
M053 | P1 | Core | Startup resilience | Bound minimum bootstrap and defer optional Firebase/config/push work | Not started |  | Flutter | M | M012 | Airplane mode, slow DNS, captive portal and Firebase outage produce usable cached/retry states; mandatory configuration still fails closed; cold/warm release launch measurements meet agreed budget. | Optional initialization precedes mounting the app and some awaits have no deadline; failure can strand the launch screen. | lib/app/bootstrap.dart:39-160; lib/core/firebase/firebase_bootstrap_service.dart; firebase_remote_config_service.dart; audit/flutter_review.md FL-05 Original source: https://drive.google.com/file/d/1cmH3dI_QSwTvgj-22nU3q1Nb26915hjh/view?usp=drivesdk https://drive.google.com/file/d/16rAbretfd1HwG3q_qLdo6WHrvbIB061u/view?usp=drivesdk
M054 | P1 | Core | Request outcomes | Standardize request deadlines and distinguish unknown mutation outcomes from failure | Not started |  | Flutter + backend | M | M091; shared operation-outcome contract | Read timeouts show recoverable unavailable states; writes retain operation identity and query status after response loss; no false payment-success label or blind duplicated mutation. | Payment-discovery/admin calls lack explicit bounded UI recovery; timing out a future does not cancel a committed write. | lib/features/biopay/data/payment_discovery_service.dart:41-107; lib/features/bookings/data/trip_service.dart:138-145; audit/flutter_review.md FL-06 Original source: https://drive.google.com/file/d/1VUan_d6DaBvOdyaJaPwIUhYmYIVpNgfH/view?usp=drivesdk https://drive.google.com/file/d/18TwBSLp6s-TqZ8Ny_zPOREtE7Ql13kn-/view?usp=drivesdk
M055 | P1 | Core | Account-bound async work | Apply account and generation checks across Profile, shell, bookings and pending operations | Not started |  | Flutter | M | M007 | Delay A responses until after B signs in; no A profile/role/data changes B UI; rapid mode/search changes discard stale results and disposed work cannot restore listeners. | Older responses can overwrite current user/mode state after asynchronous work; stronger notification/face patterns already exist. | lib/features/bookings/presentation/bookings_screen.dart:67-132; lib/features/profile/presentation/profile_screen.dart:77-114; lib/app/shell.dart:68-96; audit/flutter_review.md FL-07 Original source: https://drive.google.com/file/d/133jijD3OWgkiq8kvYppJsiGdn427lgiK/view?usp=drivesdk https://drive.google.com/file/d/18urTvEQkxOoO54RdPEqF3hG6P_FLgWYX/view?usp=drivesdk
M056 | P1 | Core | Location authority | Bind driver sharing to its account and enforce server freshness, radius and result caps | Not started |  | Flutter + backend + privacy | M | M007; M055 | Concurrent start/stop/account changes cannot resurrect sharing; stale presence excluded on all surfaces; bounded radius/limit and coordinate precision follow purpose; denied/revoked permission marks unavailable/offline. | Client start/stop races can install obsolete subscriptions; discovery trusts online flags without a server TTL and exposes broad precise-location results. | lib/features/nearby/data/driver_location_sharing_service.dart; supabase/migrations/20260915003031_harden_driver_discovery_identity.sql:5-102; audit/flutter_review.md FL-07; audit/backend_review.md B-07 Original source: https://drive.google.com/file/d/13WznvHZhWTofuAfvMnxlKTPdDtwfs6AX/view?usp=drivesdk https://drive.google.com/file/d/1YxrFAODfP5TOTqAo9h72e7UZh8p2uEt5/view?usp=drivesdk
M057 | P1 | Face | Truthful status | Represent unknown/unavailable face state distinctly from not enrolled | Not started |  | Flutter | S | M055 | Existing enrollment is never displayed as absent solely from service failure; loading, unavailable and approved cached state are distinct; retry and pause/remove recovery remain usable. | Profile replaces a failed face-status request with not_started, misleading enrolled users during outages. | lib/features/profile/presentation/profile_screen.dart:89-108,371-374,547-557; audit/flutter_review.md FL-08 Original source: https://drive.google.com/file/d/18urTvEQkxOoO54RdPEqF3hG6P_FLgWYX/view?usp=drivesdk
M058 | P1 | Core | Launch localization | Complete and review critical journeys in each promised launch language | Not started |  | Flutter + localization + product | M | M065 | Supported language promise documented; login, money, consent, permission, deletion, moderation, support and error journeys translated and fluent-reviewed; Kinyarwanda/French formatting and text expansion accepted where promised. | Three translation catalogs exist but authentication, chat, home, Profile and admin contain hardcoded English. | lib/l10n/app_en.arb; app_rw.arb; app_fr.arb; audit/flutter_review.md FL-11 Original source: https://drive.google.com/file/d/1mjt5bSDzInV-jUfGUJohw56KAzStbtix/view?usp=drivesdk
M059 | P2 | Core | Secondary localization | Finish secondary/admin copy and locale-aware dates, pluralization and currency | Not started |  | Flutter + localization | M | M058 | Inventory of remaining hardcoded user-facing copy closed or explicitly deferred; each supported locale has reviewed plural/date/currency behavior and screenshots without truncation. | Partial localization creates uneven experience beyond the initial critical flows. | lib/features/admin; lib/features/profile; lib/features/chat; audit/flutter_review.md FL-11 Original source: https://drive.google.com/drive/folders/15N84L16_NCXcIFP2MilU6QMZYOKFGKzW https://drive.google.com/drive/folders/1AP0sh5lM_wR9WyxxdJKAUc9m0djWf3Fs
M060 | P1 | Core | Accessibility | Run existing accessibility coverage and physical assistive-technology journey acceptance | Not started |  | QA + design + Flutter | M | M053; M058; M076 | TalkBack/VoiceOver, keyboard, 200% text, contrast/touch targets, focus, error announcements and reduced motion pass across accepted journeys and screen sizes; intended automatic handoff is clearly announced. | Meaningful semantics/scale/reduced-motion tests exist but no current screen-reader or device result was produced by this audit. | design.md; test accessibility/semantics suites; audit/flutter_review.md Accessibility section; https://docs.flutter.dev/ui/accessibility Original source: https://drive.google.com/file/d/1MDlUp2tylgWDZ1AfN4ssXDOKSvLkdN5-/view?usp=drivesdk
M061 | P2 | Core | Chat reliability | Add stable client-message IDs, uncertain-send reconciliation and cursor history | Not started |  | Flutter + backend | M | M007; M054 | Lost acknowledgement/retry and restart yield one message; draft remains owner-scoped; reconnect recovery works; cursor pagination preserves ordering for conversations over 100 messages when full history is promised. | Timeout retries lack a message identity; history refresh is limited to the latest window. | lib/features/chat/data/chat_service.dart:193-221,306-347; lib/features/chat/presentation/chat_screen.dart; audit/flutter_review.md FL-12 Original source: https://drive.google.com/file/d/12n5FHLFgRu9NPOsRAb9HFFgWAIIaol3b/view?usp=drivesdk https://drive.google.com/file/d/1BrgbaLACv8-s6Hop1vdwBt8E9gvQ61E_/view?usp=drivesdk
M062 | P1 | Core | Operational switches | Implement exercised server feature controls and truthful client maintenance messaging | Not started |  | Backend + Flutter + SRE | M | M015; M016; approved enabled-feature scope | Already-running clients respond to scoped suspension; server rejects affected writes; manual/QR/read-only recovery remains as approved; expiry/rollback and operator ownership are tested. | Remote Config maintenance flag is declared but unused; a client flag alone cannot stop unsafe backend operations. | lib/core/firebase/firebase_remote_config_service.dart:51-58,94-97; audit/flutter_review.md FL-14; docs/operations/face-ussd-runbook.md Original source: https://drive.google.com/file/d/1ktk89YYNARL-mxcs3U1Z1AN7_BBX3CZS/view?usp=drivesdk https://drive.google.com/file/d/1vZVjzSVzBGDPvEDyH5wTO996VJbSCDGt/view?usp=drivesdk
M063 | P2 | Core | Maintainability | Refactor touched oversized screens and overloaded models into typed application/repository boundaries | Not started |  | Flutter technical lead | L | M006; M007; M054 | Typed person/trip/member-ID and RPC outcome contracts replace lossy seams; changed workflows have focused tests; preserve Riverpod/GoRouter and avoid an unrelated framework rewrite. | Mixed Trip/person fields and UI-owned persistence/network orchestration contribute to identity loss and inconsistent retry behavior. | packages/shared-types/lib/models/trip.dart:18-130; lib/features/profile/presentation/wallet_screen.dart; audit/flutter_review.md FL-15; https://docs.flutter.dev/app-architecture/recommendations Original source: https://drive.google.com/file/d/1LlppucPRV_7Kpp3kh07UDhWL39XAPyVI/view?usp=drivesdk https://drive.google.com/file/d/1o98InGRT4t8lKLoSczaM3cwtbKewfLj1/view?usp=drivesdk
M064 | P2 | Core | Mobile performance | Measure release/profile launch, frame timing, camera memory and location battery cost | Not started |  | Performance QA + Flutter/native | M | M053; M056; M060 | Representative lower-cost Android and iPhone reports include configuration and p50/p95; accepted budgets cover startup, jank, memory, upload size, battery/network and admin lists; optimize only demonstrated bottlenecks. | No device benchmark establishes current performance; framework replacement would not resolve measured contract defects. | audit/flutter_review.md performance section; audit/platform_review.md device matrix; https://docs.flutter.dev/perf/best-practices
M065 | P1 | Core | Privacy inventory and notices | Publish a current feature/data inventory and reconcile privacy, terms and deletion copy | Not started |  | Privacy + product + engineering | M | M068; M024 if paid features enabled; M067 for enabled high-risk features | Each enabled field/store/processor has purpose, role, destination, retention and deletion mapping; public/store/in-app copy matches actual scope; superseded statements are labelled historical and no anonymous-template claim remains. | May/June notices describe anonymous login and AWS verification while September code uses WhatsApp and Cloudflare recipient lookup. | landing/privacy-policy.html; landing/terms-and-conditions.html; landing/account-deletion.html; docs/compliance/data-inventory.md; audit/privacy_review.md PRIV-01,PRIV-06 Original source: https://drive.google.com/file/d/1zQH0mmbadmfJtnEBxNkyZUnkm3Uv2LQJ/view?usp=drivesdk https://drive.google.com/file/d/1cjZLmcOWDsYYYP_-f0mYAFww9QnZ4OHp/view?usp=drivesdk
M066 | P1 | Core | Governance evidence | Record operator/controller registration, overseas-storage scope and accountable DPO | Not started |  | Qualified Rwanda counsel + privacy lead | M | Operator and enabled-feature inventory draft | Current official requirements and entity applicability checked; certificate/expiry/conditions and DPO appointment/contact documented; outstanding conditions have owners and affected-feature decisions. | Organization-specific certificates and conditions were not supplied; missing evidence is not proof of nonregistration. | audit/privacy_review.md section 1; https://cyber.gov.rw/fileadmin/user_upload/NCSA/Documents/Laws/OG_Special_of_15.10.2021_Amakuru_bwite.pdf; https://www.risa.gov.rw/data-protection-and-privacy-law
M067 | P1 | Face | Impact assessment | Complete a scoped impact/risk assessment for face lookup, location and institutional SMS | Not started |  | Privacy lead + qualified counsel + security | M | M024; M026; M056; M066 | Document actual no-liveness lookup purpose, consent/withdrawal, false-match risk, unknown persons, retention, security and alternatives; approve residual risk before affected feature activation. | Sensitive templates, bystanders/third-party senders and live location require purpose-specific grounds, safeguards and residual-risk decisions. | docs/product/face-ussd-20260920/APPROVAL.md; audit/privacy_review.md section 1 and PR-T03; https://www.risa.gov.rw/data-protection-and-privacy-law Original source: https://drive.google.com/file/d/1Ql7MVmCXqbgiB8DwU11kDXAjNmRtYF-k/view?usp=drivesdk
M068 | P1 | Core | Processors and data location | Verify actual vendor regions, contracts, subprocessors and lawful overseas arrangements | Not started |  | Privacy + platform + qualified counsel | M | M066 | Supabase primary/backups/logs and Cloudflare inference/vectors/logs plus Meta/OpenAI/analytics data flows recorded; accepted agreements and lawful arrangements match actual use; unsupported Rwanda-only/region promises removed. | Configured providers do not establish data location or contractual authority; Vectorize is outside some Cloudflare locality controls. | audit/privacy_review.md section 3; https://developers.cloudflare.com/data-localization/compatibility/; https://developers.cloudflare.com/containers/concepts/placement/; https://supabase.com/docs/guides/platform/regions Original source: https://drive.google.com/drive/folders/1IOYNDX1ALDVg9Mx6zXM1yZe8HP0xl7CG https://drive.google.com/drive/folders/1VeEGNOl32YcDgwjU7FZhqwcj_7Vyqy6c
M069 | P1 | Core | Account deletion | Implement authenticated deletion initiation, status and cross-store completion | Not started |  | Backend + Flutter + privacy + support | L | M007; M008; M065; M039 if Face enabled | Synthetic account deletion covers Auth sessions, SQL, Storage, push, vectors and applicable analytics; retries and legal retention exceptions tracked; in-app and web initiation/status work without hidden manual-only steps. | Current support-mail surface and face-only removal do not prove full account deletion across enabled data classes. | lib/features/profile/presentation/profile_screen.dart; landing/account-deletion.html; audit/backend_review.md B-13; audit/flutter_review.md FL-09; audit/privacy_review.md PRIV-04 Original source: https://drive.google.com/file/d/18urTvEQkxOoO54RdPEqF3hG6P_FLgWYX/view?usp=drivesdk https://drive.google.com/file/d/1cwyLRfUildTAHReym4ReNQOWDOGYNq7K/view?usp=drivesdk
M070 | P1 | Core | Retention and requests | Set data-class retention and implement receipt-based request deadlines with verified purge | Not started |  | Privacy + backend + support | M | M065; M069; retention and backup design | Approve periods, triggers, exceptions, backup treatment and purge owners. Within 30 days of request receipt, provide written/electronic substantive erasure notification under applicable rules; acknowledgement alone is insufficient. Verify completed deletion or justified retained-data decisions, staging purges and deletion replay after restore. | Current retention is vague and deletion page starts the response clock after verification; restores can reintroduce deleted data. | docs/compliance/data-inventory.md; landing/account-deletion.html; audit/privacy_review.md PRIV-05,PRIV-07; Rwanda Law 058/2021 Arts 23,52 Original source: https://drive.google.com/file/d/1cjZLmcOWDsYYYP_-f0mYAFww9QnZ4OHp/view?usp=drivesdk https://drive.google.com/file/d/1cwyLRfUildTAHReym4ReNQOWDOGYNq7K/view?usp=drivesdk
M071 | P1 | Face | Retired AWS resources | Inventory and obtain scoped authorization to retire old face-only AWS data and credentials | Not started |  | Platform + security + privacy | M | M001; M065 | Read-only account/resource inventory and owner decision; separately authorized named-resource deletion/key retirement receipts; no active AWS fallback and no unrelated shared resource loss. | Retired source paths do not demonstrate deletion of live collections or old IAM authority. | docs/operations/face-ussd-runbook.md; audit/privacy_review.md PRIV-12; audit/operations_review.md O21 Original source: https://drive.google.com/file/d/1vZVjzSVzBGDPvEDyH5wTO996VJbSCDGt/view?usp=drivesdk
M072 | P1 | Core | Age boundaries | Decide and implement proportionate age rules for passenger, driver and face functions | Not started |  | Product + privacy + qualified counsel | M | M065; M067 | Consistent per-role policy and proportionate declaration/restriction; underage reports and applicable guardian handling documented; no unnecessary identity-document collection introduced. | Public policy says 16 but inspected account/face paths do not enforce an age-specific rule. | landing/terms-and-conditions.html; landing/privacy-policy.html; audit/privacy_review.md PRIV-11; Rwanda Law 058/2021 Art 9 Original source: https://drive.google.com/file/d/1zQH0mmbadmfJtnEBxNkyZUnkm3Uv2LQJ/view?usp=drivesdk https://drive.google.com/file/d/1QOqPjNkyg8GlrM5Nmh1pLQlqLHpKHeTY/view?usp=drivesdk
M073 | P1 | Core | WhatsApp operating contract | Verify live authentication templates/delivery and separate marketing permissions | Not started |  | Messaging operations + backend + privacy | M | M012; M068; M091 | Approved WABA/number/template/category/language/components and supported Graph version recorded; real device delivery/resend/expired-code/outage recovery tested; campaign opt-out suppresses future promotional sends. | Configurable template payloads and API version do not prove live approval; login intent is not permission for campaigns. | supabase/functions/_shared/whatsapp-cloud.ts; audit/privacy_review.md sections 4, PRIV-10; https://whatsappbusiness.com/policy/; https://whatsappbusiness.com/products/conversation-categories/authentication/ Original source: https://drive.google.com/file/d/12qJwdf1UXnXqeY3d1I9ttnFYZhMZ77pT/view?usp=drivesdk
M074 | P1 | Core | CI correctness | Repair Actions pin validation to permit local reusable workflows and reject unpinned remote actions | Not started |  | DevOps | S | None | Actual source pin gate exits zero; valid local fixture passes and tagged/unpinned remote fixtures fail; parser distinguishes reusable workflow and remote action syntax. | Mandatory current pin script fails on valid ./.github/workflows/cloudflare-pwa.yml and blocks its calling CI job. | scripts/ci/check_github_actions_pinned.sh:12-17; .github/workflows/cloudflare-pages.yml:18; audit/operations_review.md OPS-01; audit/operations_validation.json Original source: https://drive.google.com/file/d/1At2ltdJVK8kpZQsV92HybbTqStAYqLvs/view?usp=drivesdk https://drive.google.com/file/d/1-OxjhMZxQ5KAMfLShQpBK7KFY4hhAwk_/view?usp=drivesdk
M075 | P1 | Core | Release gate truth | Make skipped/unavailable required checks non-releasable and wire aggregate gates into promotion | Not started |  | Release engineer + DevOps | M | M074 | Production invocation rejects disabling mandatory child checks; pass/failed/skipped/unavailable have distinct status; Android/PWA/services promotion requires all applicable gates for one exact artifact. | Nested helper prints PASS when both tests are skipped; release paths do not uniformly require aggregate evidence. | scripts/qa/verify_mobio_feature_readiness.sh; scripts/release/go_no_go_check.sh; .github/workflows; audit/validation_review.md IV-06; audit/operations_review.md OPS-02 Original source: https://drive.google.com/file/d/1MjilpuX-zUbut_W8msIPYSkYByKKEDyS/view?usp=drivesdk https://drive.google.com/file/d/1yPZR9Gs5lDexBEVawYsye7XvWWZ4NvAj/view?usp=drivesdk
M076 | P1 | Core | Visual acceptance | Resolve unaccepted reference goldens against the approved design and rerun the full Flutter suite | Not started |  | QA + design + Flutter | M | M074 | Each difference classified as intended or regression; only reviewed baselines change; complete suite including reference goldens passes on pinned toolchain with revision-linked results. | Historical 812 passing tests excluded standalone reference goldens while regular CI includes them. | docs/product/face-ussd-20260920/IMPLEMENTATION_REPORT.md; test reference golden suite; .github/workflows/ci.yml; audit/operations_review.md OPS-11 Original source: https://drive.google.com/file/d/13toaULZ0qSRF3mcOySrbey9WeHRMSidj/view?usp=drivesdk https://drive.google.com/file/d/1M2OuVXPXNwY34djuk7wjKwcYCIb6BUUv/view?usp=drivesdk
M077 | P1 | Core | Coverage in CI | Add required checks for every shipped implementation and native collector | Not started |  | DevOps + subsystem owners | M | M074; M075 | Flutter/Deno/Node/Python, real Linux image/model smoke, Android bridge unit/component and native release jobs run on applicable changes; a deliberate regression in each implementation blocks promotion. | Worker/Python/container/face SQL and SMS bridge changes are not all represented in required current CI. | cloudflare/face-service; services/face-inference; apps/momobio_sms_bridge; .github/workflows; audit/operations_review.md OPS-03 Original source: https://drive.google.com/drive/folders/19o_yD0w45xyCjxqocqBX8S9_0aHuBfgO https://drive.google.com/drive/folders/11tIJA6XGeIAUuubqLpB4LNw2zwvt1qXT
M078 | P1 | Core | Database rehearsal | Run all migrations on clean PostgreSQL 17 and a representative forward-upgrade copy | Not started |  | DBA + backend QA | L | M003; M015; M017; M018; M019 | Clean reset and sanitized production-like upgrade succeed; effective functions/policies/grants/extensions/jobs diff to intended state; constraints and data reconciliation pass; rollback/forward-repair plan reviewed. | Static migration review cannot prove full effective schema, order, runtime compatibility or production drift. | supabase/migrations; audit/backend_effective_functions_static.json; audit/backend_review.md B-T09; audit/validation_review.md execution limits Original source: https://drive.google.com/drive/folders/1HA6rpjdCjYgaKurjtxuEgkL6y1DJRuU7
M079 | P1 | Core | Adversarial authorization | Run a real database/Edge authorization and transaction matrix after remediation | Not started |  | Security QA + backend | L | M003; M004; M015; M016; M078 | Anonymous, expired/revoked, passenger, driver, owner/nonowner, admin-purpose and service roles tested through real interfaces; identity, direct-update, concurrency, replay and cross-tenant negatives pass. | Mock/source reproduction is strong evidence of risk but not an executed RLS/transaction/security integration result. | audit/validation_review.md; audit/backend_review.md; supabase/functions; supabase/migrations Original source: https://drive.google.com/drive/folders/1HA6rpjdCjYgaKurjtxuEgkL6y1DJRuU7 https://drive.google.com/drive/folders/1l5OIu5zSjUzWrwkfS9W9cBN2ocmKUI07
M080 | P1 | Core | Production controls | Read back actual repository/environment protections, secrets and promotion roles | Not started |  | Security + release owner | S | M001; M002; M075 | Current branch/environment rules, required checks, reviewer separation and secret scope recorded for actual repository/account plan; least-privilege deployment roles and emergency path tested without publishing. | Workflow YAML and PROD_RELEASE_ENABLED variables do not establish remote protection rules or account authority. | audit/operations_review.md O14; .github/workflows; audit/git_metadata provenance Original source: https://drive.google.com/drive/folders/1Do2o7oLKmnkMMkm4NtPTCchKEN_zu4tK
M081 | P1 | Core | Release evidence | Bind source, artifacts, migrations, model policy and approvals in a structured release manifest | Not started |  | Release engineer | M | M075; M078; M080 | Exact commit plus working-tree state, artifact hashes, version equality, migration/model identifiers, environment, reviewer/date and full check receipts validated; stale/example/wrong-artifact/prefix fixtures rejected. | Current acknowledgement/file-presence checks accept weak evidence and a version prefix can match the wrong Play version. | scripts/release/go_no_go_check.sh:40-67,123; docs/product/face-ussd-20260920/IMPLEMENTATION_REPORT.md; audit/operations_review.md OPS-10 Original source: https://drive.google.com/file/d/13toaULZ0qSRF3mcOySrbey9WeHRMSidj/view?usp=drivesdk https://drive.google.com/file/d/1yPZR9Gs5lDexBEVawYsye7XvWWZ4NvAj/view?usp=drivesdk
M082 | P2 | Core | Dependency security | Pin reproducible toolchains and cover all dependency/container ecosystems with update and advisory review | Not started |  | DevSecOps + maintainers | M | M077 | Deno/Node/pnpm/Wrangler/container toolchain fixed to tested versions; update coverage and actual advisory triage documented; clean builds reproduce; upgrades are risk-reviewed rather than indiscriminate. | Current updates omit new npm/Python/Docker paths; Deno and Wrangler invocations can drift. | .github/dependabot.yml; .github/workflows; cloudflare/face-service/package.json; services/face-inference; audit/operations_review.md OPS-08 Original source: https://drive.google.com/file/d/1_LsmRout-ReXNuDQEpeAFl8lTKtAAImX/view?usp=drivesdk https://drive.google.com/drive/folders/1kQsuocMDtXnp20aRwLKuojC9WoYP7bjd
M083 | P2 | Core | Supply-chain records | Produce verified SBOM/provenance and retain licences, symbols and source maps for supported releases | Not started |  | DevSecOps + release | M | M081; M082 | Distributed artifact SBOM and provenance verify against release hashes; model/SDK licences archived; symbol/source-map access and crash symbolication tested for supported versions. | No repository workflow establishes release component inventory, attestations or long-lived diagnostic artifact retention. | audit/operations_review.md OPS-08,O16; https://docs.github.com/en/actions/concepts/security/artifact-attestations
M084 | P1 | Core | Observability | Instrument privacy-safe service and client health with owned actionable alerts | Not started |  | SRE + backend + mobile | M | M032; M034; M037; M056 | Dashboards cover auth, latency/errors, face busy/cleanup, receipt-to-credit, notification backlog, crashes/ANRs and stale presence; named owners/budgets; induced failure alerts correctly with no raw faces, vectors, OTPs or financial identifiers. | Face Worker observability is disabled and operational runbooks lack concrete SLO/alert ownership; provider platform metrics alone are insufficient. | cloudflare/face-service/wrangler.jsonc:8; services/face-inference/server.py:7; docs/operations/README.md; audit/operations_review.md OPS-06 Original source: https://drive.google.com/file/d/10XfUXtvPdRtBHiWA9yhRro_v6glk8XvJ/view?usp=drivesdk https://drive.google.com/file/d/1UjDIz7n8Uk4OhFXYNLmB3vShd_P1ziTY/view?usp=drivesdk
M085 | P1 | Core | Recovery | Define RPO/RTO and rehearse isolated database, Storage, configuration and vector recovery | Not started |  | DBA + SRE + privacy | L | M065; M070; M078 | Timed isolated restore with outbound jobs disabled meets approved loss/time objectives; SQL/objects/permissions/idempotency reconcile; deletion tombstones reapplied; explicitly choose protected vector restore or consented reenrollment. | Schema backup and database backup alone do not restore customer data, Storage objects, secrets/bindings or enrollment state. | docs/operations/face-ussd-runbook.md; audit/operations_review.md OPS-07; https://supabase.com/docs/guides/platform/backups Original source: https://drive.google.com/file/d/1vZVjzSVzBGDPvEDyH5wTO996VJbSCDGt/view?usp=drivesdk https://drive.google.com/drive/folders/1VeEGNOl32YcDgwjU7FZhqwcj_7Vyqy6c
M086 | P1 | Core | Incident response | Rehearse security/privacy/financial incident ownership and escalation | Not started |  | Security + privacy + SRE + payments | M | M001; M023; M066; M084 | Tabletop covers key exposure, wrong credit, lost collector and biometric/PII event; evidence preservation, containment and contacts tested; applicable Rwanda 48-hour notice/72-hour report clocks reviewed by counsel. | Public folder exposure and financial authority risks make an actionable response process necessary; organization-specific response evidence was not supplied. | audit/privacy_review.md PR-T19; audit/operations_review.md OPS-06; Rwanda Law 058/2021 Arts 43-44 Official source: https://cyber.gov.rw/fileadmin/user_upload/NCSA/Documents/Laws/OG_Special_of_15.10.2021_Amakuru_bwite.pdf
M087 | P1 | Core | Rollout and rollback | Exercise staged release, kill switches and compatible rollback for each enabled surface | Not started |  | Release + SRE + product | M | M062; M081; M084; M085 | Internal/staged promotion uses defined stop criteria; last-known-good artifacts/configs identified; schema compatibility or forward repair tested; face can be disabled while accepted manual/QR flows continue. | No current end-to-end rollback receipt proves coordinated recovery across app, web, Edge, schema and face services. | docs/operations/face-ussd-runbook.md; .github/workflows/android-release.yml; audit/operations_review.md O19 Original source: https://drive.google.com/file/d/1w_uWBznlC3jNzjHFewL1FSjnmE9qVCmO/view?usp=drivesdk https://drive.google.com/file/d/1vZVjzSVzBGDPvEDyH5wTO996VJbSCDGt/view?usp=drivesdk
M088 | P1 | Core | Launch acceptance | Run a version-bound end-to-end matrix on staging and release-candidate devices | Not started |  | QA lead + release + feature owners | L | M044; M046; M049; M052; M060; M073; M079; M081; M040 if Face enabled | Exact release journey results cover OTP, discovery/posting, chat/moderation, account lifecycle, manual/QR, chosen paid features and optional face/SMS; offline/denied/timeout/restart cases recorded with clear pass/blocked status. | Historical passes and fixture tests do not verify current real providers, migrations, operator handoff or signed devices. | audit/platform_review.md device matrix; audit/flutter_review.md acceptance; audit/validation_review.md section 3; docs/product/face-ussd-20260920/IMPLEMENTATION_REPORT.md Original source: https://drive.google.com/file/d/13toaULZ0qSRF3mcOySrbey9WeHRMSidj/view?usp=drivesdk
M089 | P1 | Core | Support and moderation | Operationalize existing report/block controls, account recovery and financial exception handling | Not started |  | Support operations + product + trust/safety | M | M009; M023; M069; M073; M084 | Named queues/response targets and escalation paths; staged report/block/unblock, lost WhatsApp access, deletion and disputed receipt drills close with an audit trail; no PIN collection or improvised auth bypass. | Client moderation controls exist, but launch requires staffed ownership, escalation and abuse/support outcomes. | lib/features/chat/data/chat_service.dart:63-143; lib/features/chat/presentation/chat_screen.dart; docs/operations/README.md; audit/flutter_review.md strengths; audit/privacy_review.md section 4 Original source: https://drive.google.com/file/d/12n5FHLFgRu9NPOsRAb9HFFgWAIIaol3b/view?usp=drivesdk https://drive.google.com/file/d/1BrgbaLACv8-s6Hop1vdwBt8E9gvQ61E_/view?usp=drivesdk
M090 | P2 | Core | Source and scope documentation | Publish a clean reproducible source manifest and one current feature/release status map | Not started |  | Repository maintainer + product + release | M | M001; M081 | Source, generated files and intentionally retained release evidence separated without indiscriminate deletion; exact provenance/dirty state recorded; current scope links superseded documents; clean checkout reproduces required builds. | Drive includes generated caches and older conflicting evidence; snapshot bytes are not automatically an immutable Git release. | audit/git_index_inventory.json; audit/root_inventory.json; README.md; AGENTS.md; docs/product/face-ussd-20260920/APPROVAL.md; audit/operations_review.md OPS-12 Original source: https://drive.google.com/file/d/1Ql7MVmCXqbgiB8DwU11kDXAjNmRtYF-k/view?usp=drivesdk https://drive.google.com/file/d/1vnBbpRv1TLxzzBiWw9oHhqdKtdegRYSa/view?usp=drivesdk
M091 | P1 | Core | Provider resilience and budgets | Bound external calls and enforce durable rate/cost controls for OTP, maps and AI paths | Not started |  | Backend + SRE + security | M | M012; M032 | Shared per-user/device/collector admission and cost limits survive cold starts; deadlines, bounded retries and circuit recovery tested; legitimate outage recovery works; retired route computation stays retired. | Maps uses process-memory rate state and lacks an application timeout; external failures and repeated calls can amplify latency and spend. | supabase/functions/maps-gateway/index.ts:52-85,244-255; supabase/functions/_shared/whatsapp-cloud.ts; audit/backend_review.md B-09,B-T15,B-T17 Original source: https://drive.google.com/file/d/12qJwdf1UXnXqeY3d1I9ttnFYZhMZ77pT/view?usp=drivesdk https://drive.google.com/file/d/190BYE2qz7Hc58j2hl-xYbAf9ELpsk-2j/view?usp=drivesdk
M092 | P2 | Core | Notification delivery | Use a durable notification outbox with leases, bounded retry and token lifecycle | Not started |  | Backend + SRE | M | M008; M084 | Notification/token idempotency, lease recovery, TTL, consent, backoff and invalid-token removal work under duplicate dispatch/provider outage; backlog age is visible; no unbounded OAuth/send loop. | Current HTTP dispatch can repeat sends and lacks a durable per-notification/token claim with bounded retry state. | supabase/migrations/20260914203228_repair_notification_trigger_http_dispatch.sql; supabase/functions/send-push/index.ts:363-462; audit/backend_review.md B-12 Original source: https://drive.google.com/file/d/1_8s_2FN71Qop1DxBFlwWEyQKzj6-S_EG/view?usp=drivesdk https://drive.google.com/file/d/16QDr4XE1T00Pm357hzMubBmi_sn1Op11/view?usp=drivesdk
M093 | P2 | Core | Database performance | Load-test bounded discovery, realtime, chat history and financial queries at launch/next-stage volume | Not started |  | DBA + performance + backend | M | M056; M078; M084 | Representative cardinalities and concurrency with EXPLAIN/query statistics meet chosen latency budget; indexes/caps/pagination based on measured plans; retention does not break reconciliation or deletion. | Unbounded nearby limits and growing tables can affect latency, privacy and resource cost; no current production-scale query evidence was executed. | supabase/migrations/20260915003031_harden_driver_discovery_identity.sql; audit/backend_review.md B-07,B-T23; audit/flutter_review.md FL-12 Original source: https://drive.google.com/file/d/13WznvHZhWTofuAfvMnxlKTPdDtwfs6AX/view?usp=drivesdk
M094 | P2 | Core | Operating economics | Build an observed launch cost model and usage budget with explicit assumptions | Not started |  | Product + finance + SRE | M | M023; M041; M084; M091 | Current account tariffs and observed requests per successful journey drive low/base/peak forecast; budget alerts and owner-approved service caps tested; no invented Rwanda rate or fixed per-scan promise. | No measured unit economics were established across paid OTP, AI parsing, containers, vectors, database, storage and egress. | audit/operations_review.md OPS-05; audit/privacy_review.md section 4; https://developers.cloudflare.com/containers/platform/pricing/; https://whatsappbusiness.com/products/platform-pricing/ Original source: https://drive.google.com/drive/folders/1IOYNDX1ALDVg9Mx6zXM1yZe8HP0xl7CG
M095 | P3 | Face | Measured optimization | Optimize inference pool/index checks only after accepted baseline capacity data | Not started |  | Performance + platform | M | M038; M041; M084; M094 | Measured bottleneck and benefit threshold documented; bounded pool or compatibility-cache change preserves model/consent correctness and cost cap; before/after load and failure results demonstrate improvement. | Single-instance serialized design is a controlled baseline; automatic scaling or broad rewrites are not justified without demand evidence. | cloudflare/face-service/src/handler.ts:90-165; services/face-inference/inference.py; audit/operations_review.md OPS-05; https://developers.cloudflare.com/containers/configuration/scaling-and-routing/ Original source: https://drive.google.com/file/d/1ZMe2Z6-28lqVhf4GD24uS02hOaPsgsYZ/view?usp=drivesdk https://drive.google.com/file/d/140d2FVWo8zH96uUG9K55Svsd5twTSLzR/view?usp=drivesdk

## Release gates
Release gates
Audit: 27 September 2026 |  |  | Human release decisions require artifact-bound evidence; task counts do not grant approval.
Core gates cover shared capabilities. Optional features remain disabled until their own acceptance is recorded.
Gate | Release decision | Scope | Required task IDs | Current assessment | Accountable role | Acceptance evidence | Limits / sequencing | Assigned owner | Gate status
G01 | Shared security containment | Core | M001; M002; M003; M004; M005; M006 | Blocked | Security lead | Named access, secret provenance/reset receipt and verified identity/recipient-authority regressions. | Source defects confirmed; no outsider access or successful live takeover asserted. |  | Not started
G02 | Common account and privacy readiness | Core | M007; M008; M009; M010; M012; M053; M055; M065; M066; M068; M069; M070; M072; M073 | Not evidenced | Product + privacy + security | Functional exit/deletion/account switch, verified messaging contract and current privacy/governance records. | Missing organization evidence must be resolved for the affected launch; code review is not legal clearance. |  | Not started
G03 | Paid transport integrity | Paid transport | M015; M017; M018; M022; M024; M078; M079 | Blocked | Payments + backend | Direct owner mutation denied, conserved seats, unique receipts, concurrency/refund tests and approved operating responsibility. | Disable paid booking features until this gate passes; no new route/dispatch/settlement engine required. |  | Not started
G04 | Institutional SMS ingestion | SMS | M016; M019; M020; M023; M025; M026; M027; M028; M029; M030; M031; M032; M033; M034 | Blocked | Payments + fleet + Android | Minimized approved collection, production signing/enrollment, durable delivery, strong receipt allocation and reconciliation. | Private fleet channel does not remove privacy/integrity controls; public Play requires separate policy evidence. |  | Not started
G05 | Face-USSD optional enablement | Face | M035; M036; M037; M038; M039; M040; M041; M043; M057; M067; M068; M071 | Not evidenced | Product + ML QA + privacy | Real model/image/schema health, consented calibration, cleanup, physical operator handoff and scope-specific approvals. | Keep policy disabled until accepted. No liveness or compulsory payment review is added to approved recipient lookup. |  | Not started
G06 | Android release artifact | Core | M002; M044; M045; M047; M048; M049; M050; M052; M060; M081 | Not evidenced | Android release + QA | Trusted signed target36 artifact, actual native compatibility, links/permissions, accessibility and version-bound evidence. | 16 KB actual artifact remains unverified; current official update enforcement date is 2027-02-01. |  | Not started
G07 | iOS release artifact | Core | M046; M048; M049; M050; M052; M060; M081 | Not evidenced | iOS release + QA | Signed Xcode26+/iOS26 SDK archive, entitlements, TestFlight/device APNs/camera/location and archive privacy review. | Existing no-codesign check is insufficient. No native macOS application was identified. |  | Not started
G08 | Reproducible protected promotion | Core | M074; M075; M076; M077; M078; M079; M080; M081 | Blocked | Release + DevOps | All mandatory current checks pass with no skipped substitute; exact artifact/migration/model and reviewer evidence validated. | Pin gate currently fails; nested helper can falsely PASS after skips; historical functional pass excluded goldens. |  | Not started
G09 | Operations and recovery | Core | M062; M084; M085; M086; M087; M089; M091 | Not evidenced | SRE + security + support | Actionable alerts, owned SLOs, timed restore, incident tabletop, staged rollback and staffed support drills. | Vendor dashboards or runbook prose alone do not establish operating readiness. |  | Not started
G10 | Launch journey acceptance | Core | M021; M051; M054; M056; M058; M060; M073; M088 | Not evidenced | QA lead + product | Exact release-candidate journeys and negative-path matrix on representative signed devices and current operator/provider configuration. | Execute only enabled feature scopes; every blocked/not-run result remains explicit. |  | Not started

## Validation
Validation register ¦ 27 September 2026
| Executed fixture/script tests |  | 107 |  | Fixture tests only; scope and limits are recorded below.
Current device / database / real-model production validation: not executed. This register is terminal evidence, not an automatic release gate.
ID | Check | Outcome | Count | Evidence date / stage | Runtime / scope | What it establishes | Limits / next action | Evidence source
V01 | Python script logic | Passed | 26 | Executed 2026-09-27 | Python 3.12.14; fixtures | runtime-defines 7, repository-boundary 5, version-assets 7, Android smoke 7. | Android cases use fake ADB/apksigner and fixture APKs; no device evidence. | audit/python_script_tests.txt; audit/validation_review.md section 3 Original source: https://drive.google.com/file/d/1WOgZLHs0VLWA8DpZLuV8Le4vDKzXHApL/view?usp=drivesdk
V02 | Pages/Admin Node tests | Passed | 69 | Executed 2026-09-27 | Node 24.19.0; fixtures | Routing, cache, shell and recovery behavior in existing tests. | No full persistent log was retained; root audit tool output and reviewer record exist. | audit/validation_review.md section 3 Original source: https://drive.google.com/file/d/1LfQjpZZo9Af-hfhR9vxQmd1PAAl5YFH1/view?usp=drivesdk https://drive.google.com/file/d/1AclcH-_QKjPYyyPzDbMD-36G3H2OV87A/view?usp=drivesdk
V03 | Pure MoMo parser tests | Passed | 5 | Executed 2026-09-27 | Node 24.19.0; minimal Deno env/test shim | Existing parser normalization and shared-secret tests. | Not the real Deno Edge runtime; one live provider test deliberately skipped. | audit/run_momo_parser_validation.mjs; audit/validation_review.md section 3 Original source: https://drive.google.com/file/d/1jy2qeudD4ypMt6bl6SltIQwb3KGpece7/view?usp=drivesdk
V04 | Face Worker tests | Passed | 7 | Executed 2026-09-27 | Node 24.19.0; mocked bindings | Existing Worker unit/contract fixtures. | No actual Linux container, model inference, Vectorize or production Worker execution. | audit/operations_validation.json; audit/operations_review.md Original source: https://drive.google.com/file/d/1KnIkiBpwFO23e1jfgihjkbw05KV00OQ2/view?usp=drivesdk
V05 | Bash syntax checks | Passed | 32 | Executed 2026-09-27 | bash -n | Shell syntax parses. | Syntax checks are not behavioral tests and are excluded from the 107-test total. | audit/operations_validation.json; audit/operations_review.md Original source: https://drive.google.com/drive/folders/1p301MZ_Wgt1MkSdxH5mMKWErb8jXgxYF
V06 | Python source AST checks | Passed | 21 | Executed 2026-09-27 | Python AST parser | Python syntax parses. | Syntax checks are not behavioral tests and are excluded from the 107-test total. | audit/operations_validation.json; audit/operations_review.md Original source: https://drive.google.com/drive/folders/1kQsuocMDtXnp20aRwLKuojC9WoYP7bjd
V07 | Actions pin release gate | Failed | 1 | Executed 2026-09-27 | Current repository script | Exit 1 rejects a valid local reusable-workflow reference. | Confirmed CI gate defect; no release was attempted. | scripts/ci/check_github_actions_pinned.sh; audit/operations_validation.json Original source: https://drive.google.com/file/d/1At2ltdJVK8kpZQsV92HybbTqStAYqLvs/view?usp=drivesdk
V08 | Negative/uncertain SMS fixtures | Reproduced | 2 | Executed 2026-09-27 | Node fixture parser input | Non-payment/low-confidence output with absent identifiers passes through parser. | No live AI parse, SQL credit, payment or financial effect executed. | audit/run_momo_parser_validation.mjs; audit/validation_review.md IV-02 Original source: https://drive.google.com/file/d/1jy2qeudD4ypMt6bl6SltIQwb3KGpece7/view?usp=drivesdk
V09 | Identity authority fixture | Reproduced | 2 | Executed 2026-09-27 | Extracted unchanged helper; mocked DB/Auth | Wrong alias wins selection; existing different phone does not prevent admin reassignment request. | No real Supabase/Auth mutation or successful takeover was demonstrated. | audit/run_identity_authority_validation.mjs; audit/identity_authority_fixture_result.json Original source: https://drive.google.com/file/d/1VzfemejMhTryu0KVQFVpt8lxcSH57O4N/view?usp=drivesdk
V10 | Nested readiness skip case | Reproduced | 1 | Executed 2026-09-27 | Bash; /usr/bin/true only satisfies executable existence guard | Both optional checks disabled yields two SKIPs, PASS and exit 0. | No Flutter test/build ran; not a passing real release gate or proof all outer gates are bypassed. | scripts/qa/verify_mobio_feature_readiness.sh; audit/validation_review.md IV-06 Original source: https://drive.google.com/file/d/1MjilpuX-zUbut_W8msIPYSkYByKKEDyS/view?usp=drivesdk
V11 | Synthetic member-ID collision | Reproduced | 1 | Executed 2026-09-27 | Python translation of exact client hash loop | Two synthetic distinct UUIDs map to the same six-digit client hash. | Not a Dart runtime test or evidence these users exist; server uniqueness absence separately reviewed. | audit/flutter_review.md FL-01 Original source: https://drive.google.com/file/d/1bq4ySgtsKMtZ_3C-dbEBtsgZV80gMLNZ/view?usp=drivesdk
V12 | Pure parser live provider case | Skipped | 1 | Deliberate audit boundary | Live AI/provider input | Live test excluded to avoid treating a fixture environment as deployed-provider evidence. | Must run controlled provider acceptance with authorized configuration before affected launch. | audit/run_momo_parser_validation.mjs; audit/validation_review.md Original source: https://drive.google.com/file/d/1jy2qeudD4ypMt6bl6SltIQwb3KGpece7/view?usp=drivesdk
V13 | PWA packaging check | Environment blocked | 1 | Attempted 2026-09-27 | Downloaded snapshot | Flutter executable and complete Git checkout identity unavailable. | Not counted as a repository defect or passing package build. | audit/validation_review.md section 3 Original source: https://drive.google.com/file/d/1qV2Ou35hP4wQYcYa2nhF8OAIoGYDd4H4/view?usp=drivesdk
V14 | PostgreSQL/RLS/concurrency | Not executed |  | Required next | Real PostgreSQL 17 + PostgREST | Clean/forward migrations, role matrix, booking/receipt/renewal races remain to execute. | SQL defects and race implications in this audit are source evidence/inference. | M078; M079; audit/backend_review.md; audit/validation_review.md Original source: https://drive.google.com/drive/folders/1HA6rpjdCjYgaKurjtxuEgkL6y1DJRuU7
V15 | Actual Deno Edge runtime | Not executed |  | Required next | Deno + staging Supabase | Real OTP/collector/function integration and provider failures remain to execute. | Node shims do not establish Deno deployment correctness. | M077; M079; M091; audit/validation_review.md Original source: https://drive.google.com/drive/folders/1l5OIu5zSjUzWrwkfS9W9cBN2ocmKUI07
V16 | Real face model/image/index | Not executed |  | Required before Face | Linux image + models + isolated Cloudflare/Vectorize | Build, actual embedding, gallery calibration, cleanup and load remain to execute. | Historical Worker/model fixtures and source policy guards are not accuracy or deployment proof. | M036-M043; audit/operations_review.md; audit/validation_review.md Original source: https://drive.google.com/drive/folders/1kQsuocMDtXnp20aRwLKuojC9WoYP7bjd https://drive.google.com/drive/folders/11tIJA6XGeIAUuubqLpB4LNw2zwvt1qXT
V17 | Flutter and signed mobile devices | Not executed |  | Required before launch | Flutter, Android/ADB, Xcode/iOS devices | Current full suite/goldens, signed packages, screen readers and real provider/operator journeys remain to execute. | No adb/flutter/xcode existed in audit runtime; no native macOS app identified. | M044-M052; M060; M076; M088; audit/platform_review.md Original source: https://drive.google.com/drive/folders/1a1rqKBm2lsOX2HKqCl-_OCKTs2zIAoAZ https://drive.google.com/drive/folders/1SH1CM2wJiUWWheCDDd4XDPmglQTHN4J3 https://drive.google.com/drive/folders/1unpxfG67ncp9_hRwZjwMofpLWUdcwaov
V18 | Historical September implementation evidence | Historical only |  | Source report dated 2026-09-20 | Prior implementation report | Reports 812 Flutter functional tests excluding reference goldens, 123 Deno + 1 ignored, 7 Worker, 8 model HTTP and signed Android. | Not independently rerun here; full image, deployment, accuracy and current operator acceptance remain unproven. Do not add historical counts to current totals. | docs/product/face-ussd-20260920/IMPLEMENTATION_REPORT.md; audit/operations_review.md Original source: https://drive.google.com/file/d/13toaULZ0qSRF3mcOySrbey9WeHRMSidj/view?usp=drivesdk