## Overview
MOBIO ¦ Implementation Increment04
28 September 2026 • Durable SMS receipt admission and worker • Source delivery with local evidence; not a production release.
AUDIT TASKS | ADVANCED NOW | LOCAL CHECKS | PRODUCTION ACCEPTED
95 | 8 | 180 | 0
Release blocker: the source folder still permits anyone with its link to edit. Restrict access and review exposed signing material. No permissions or live credentials were changed.
DELIVERY STATUS — NOT A COMPLETION PERCENTAGE
Updated in Increment04 |  |  | 8
Earlier source work; acceptance open |  |  | 29
Open; no completion evidence |  |  | 58
Implemented: atomic receipt admission, separate authorized worker, duplicate protection, claim fencing, bounded retries and budgets, health visibility, operational trigger, CI fixtures and a guarded source applier. PostgreSQL transactional behaviour is not yet verified.
Next gates: real PostgreSQL 17/full-schema and Auth tests; actual operator receipt validation; approved review/replay and retention; staging end-to-end; signed Android/iOS/device acceptance; hosted required CI and controlled rollout. Allocation defaults remain OFF.
Read the Verification tab before interpreting test counts. No production acceptance is evidenced by these delivery packages; this does not assert that external organizational approvals do not exist.

## All 95 tasks
Mobio ¦ Full task register
28 September 2026 • Eight tasks advanced by Increment04. Earlier source work and new local tests are not production acceptance.
ID | Priority | Area | Original task | Delivery status | New Increment04 evidence | Next acceptance / remaining work | Owner role | Dependencies | Prior delivery evidence | Production acceptance | Original backlog source
M001 | P0 | Source access | Restrict the public Drive working-copy folder and preserve an access-review record | Open; no completion evidence | No new completion claim in this increment. | Named access replaces anyone-writer; inherited/child permissions and link access are verified; preserve activity evidence and an incident decision without asserting outsider use. | Security lead + folder owner | None | No completion claimed by these increments. Original audit acceptance criteria remain applicable. | Not evidenced by these deliveries | https://drive.google.com/file/d/15X3_uSbHztLL57IL_d3Xo9hc9zInJuyN/view
M002 | P0 | Signing and secrets | Inventory exposed credentials and replace or revoke affected secrets using their actual provenance | Open; no completion evidence | No new completion claim in this increment. | Identify owner, purpose, exposure window and actual upload/app-signing role; reset upload keys or revoke credentials as warranted; prove a trusted signed update path and remove exposed copies under retention policy. | Security + Android release owner | M001 | No completion claimed by these increments. Original audit acceptance criteria remain applicable. | Not evidenced by these deliveries | https://drive.google.com/file/d/15X3_uSbHztLL57IL_d3Xo9hc9zInJuyN/view
M003 | P0 | Identity authority | Bind verified WhatsApp/phone identity to an immutable, unique Auth identity | Earlier source work; acceptance open | No new completion claim in this increment. | Separate editable contact data from verified login authority; migrate duplicate aliases; verification cannot select or reassign another account; negative fixtures plus real Auth collision behavior pass. Phone-based BioPay discovery also resolves only the canonical verified recipient authority, never an editable contact alias. | Backend + security | M001 | Auth-owned verified phone identity implemented locally; handler fixtures pass; live Auth collision/race and deployed RPC not tested. | Not evidenced by these deliveries | https://drive.google.com/file/d/15X3_uSbHztLL57IL_d3Xo9hc9zInJuyN/view
M004 | P1 | Authorization | Protect identity and privilege columns and audit effective table/RPC grants | Earlier source work; acceptance open | No new completion claim in this increment. | Publish effective role/table/column/function matrix; default-deny sensitive updates and security-definer execution; ordinary sessions cannot mutate verified aliases, creation order, member ID or admin authority. Test fn_biopay_discover against attempted editable-phone impersonation. | Backend + security | M003 | Identity/member-id authority guard candidate prepared; database grants/RLS effective state not executed. | Not evidenced by these deliveries | https://drive.google.com/file/d/15X3_uSbHztLL57IL_d3Xo9hc9zInJuyN/view
M005 | P1 | Member identity | Reconcile duplicate member IDs and enforce atomic unique six-digit allocation | Earlier source work; acceptance open | No new completion claim in this increment. | Duplicate inventory reviewed; controlled remediation preserves account UUIDs and references; unique constraint plus concurrent allocation tests pass; ambiguous recipient lookup fails safely. | Backend + data migration owner | M003; M004 | Canonical unique six-digit member-ID forward body + assertions implemented; database reconciliation not executed. | Not evidenced by these deliveries | https://drive.google.com/file/d/15X3_uSbHztLL57IL_d3Xo9hc9zInJuyN/view
M006 | P1 | Member identity | Display the authoritative member ID consistently across all client surfaces | Earlier source work; acceptance open | No new completion claim in this increment. | One fixture displays one server-issued six-digit ID in profile, nearby, trip, chat and wallet; no fabricated fallback; wrong/missing/ambiguous recipient regression cases pass. | Flutter + QA | M005 | Production UUID/hash member-ID fallbacks removed; source-contract tests pass; Flutter runtime/goldens not run. | Not evidenced by these deliveries | https://drive.google.com/file/d/15X3_uSbHztLL57IL_d3Xo9hc9zInJuyN/view
M007 | P1 | Account lifecycle | Implement ordinary sign-out with finally-safe local and native cleanup | Earlier source work; acceptance open | No new completion claim in this increment. | Offline exit clears local credentials, account state, drafts/listeners and camera/NFC/location activity; cleanup failures cannot restore access; account A data never appears after B signs in. | Flutter + native platform owners | M003 | Ordinary sign-out and finally-safe cleanup implemented; account-switch/device tests not run. | Not evidenced by these deliveries | https://drive.google.com/file/d/15X3_uSbHztLL57IL_d3Xo9hc9zInJuyN/view
M008 | P1 | Push identity | Revoke FCM association before losing its owning session and atomically bind device ownership | Earlier source work; acceptance open | No new completion claim in this increment. | Two-account device test receives only current-owner messages; captured identity is rechecked around token retrieval/upsert; anonymous registration rejected; stale-token expiry and revocation verified. | Flutter + backend | M007 | FCM registration/unregister now owner-bound; real two-account push test not run. | Not evidenced by these deliveries | https://drive.google.com/file/d/15X3_uSbHztLL57IL_d3Xo9hc9zInJuyN/view
M009 | P1 | Admin security | Define and enforce admin idle, absolute lifetime and sensitive-action authentication | Open; no completion evidence | No new completion claim in this increment. | Retained timeout requirements are enforced server-side and reflected in UI; idle/background/resume/refresh/role-revocation tests pass; high-impact operations require the agreed admin purpose. | Security + backend + Flutter | M003; M007 | No completion claimed by these increments. Original audit acceptance criteria remain applicable. | Not evidenced by these deliveries | https://drive.google.com/file/d/15X3_uSbHztLL57IL_d3Xo9hc9zInJuyN/view
M010 | P1 | Credential storage | Migrate native refresh-session persistence to supported OS-protected storage | Open; no completion evidence | No new completion claim in this increment. | At-rest/backup inspection and migration, restart, sign-out, reinstall and revocation tests pass on Android/iOS; recovery behavior is documented; browser storage is addressed separately. | Flutter + security | M007 | No completion claimed by these increments. Original audit acceptance criteria remain applicable. | Not evidenced by these deliveries | https://drive.google.com/file/d/15X3_uSbHztLL57IL_d3Xo9hc9zInJuyN/view
M011 | P1 | Review access | Constrain the store-review identity to monitored synthetic data and rotate its access | Open; no completion evidence | No new completion claim in this increment. | Review account has approved minimal access and no real-user financial/biometric records; rate cap, audit monitoring and rotation procedure work; live OTP-claim semantics remain enforced. | Security + release + backend | M003; M009 | No completion claimed by these increments. Original audit acceptance criteria remain applicable. | Not evidenced by these deliveries | https://drive.google.com/file/d/15X3_uSbHztLL57IL_d3Xo9hc9zInJuyN/view
M012 | P1 | OTP production config | Reject OTP dry-run in production and redact all authentication secrets | Earlier source work; acceptance open | No new completion claim in this increment. | Deployment gate rejects WHATSAPP_CLOUD_DRY_RUN in production; sanitized config readback and log fixtures show no OTP/full phone; testing still uses explicitly isolated fixtures. | Backend + DevOps | M002 | Production OTP dry-run guard/redaction implementation locally tested; deployment pending. | Not evidenced by these deliveries | https://drive.google.com/file/d/15X3_uSbHztLL57IL_d3Xo9hc9zInJuyN/view
M013 | P2 | Abuse prevention | Choose an explicit Play Integrity policy and bind/consume protected requests | Open; no completion evidence | No new completion claim in this increment. | Document acceptable device/app verdicts and exceptions; replay/content-substitution fixtures fail where required; monitor-to-enforce decision uses measured false rejects and does not indiscriminately block users. | Android + backend + security | M003; M091 | No completion claimed by these increments. Original audit acceptance criteria remain applicable. | Not evidenced by these deliveries | https://drive.google.com/file/d/15X3_uSbHztLL57IL_d3Xo9hc9zInJuyN/view
M014 | P2 | Web session security | Verify admin browser persistence, CSP and session revocation against an explicit threat model | Open; no completion evidence | No new completion claim in this increment. | Approved persistence policy, effective headers and browser expiry/revoke/role-change tests recorded; cached pages and service workers expose no prior-account sensitive data. | Web + security | M009 | No completion claimed by these increments. Original audit acceptance criteria remain applicable. | Not evidenced by these deliveries | https://drive.google.com/file/d/15X3_uSbHztLL57IL_d3Xo9hc9zInJuyN/view
M015 | P0 | Booking authorization | Remove passenger authority to self-confirm or mark a booking paid | Earlier source work; acceptance open | No new completion claim in this increment. | Direct PostgREST attempts to set confirmed/paid, paid_at, receipt, price, route or seat authority fail for passengers; only trusted transactional RPCs can make valid transitions. | Backend + security | M004 | Direct booking-write containment body prepared; database/PostgREST authorization matrix not run. | Not evidenced by these deliveries | https://drive.google.com/file/d/15X3_uSbHztLL57IL_d3Xo9hc9zInJuyN/view
M016 | P0 | Receipt integrity | Require strong payment evidence before automatic subscription activation | Earlier source work; acceptance open | No new completion claim in this increment. | Non-payment, uncertain, missing-reference, wrong merchant/currency and ambiguous fixtures cannot credit; require classified payment plus stable provider reference and intended payer/invoice binding; quarantine for reviewed resolution. | Backend + payments owner | M020; M026 | Strong SMS receipt eligibility implemented in Edge/SQL candidate; operator evidence and DB activation tests pending. | Not evidenced by these deliveries | https://drive.google.com/file/d/15X3_uSbHztLL57IL_d3Xo9hc9zInJuyN/view
M017 | P1 | Seat inventory | Make booking holds idempotent and durably expire/release seats | Earlier source work; acceptance open | No new completion claim in this increment. | Bounded expiry job, cancellation and hold idempotency work; concurrent last-seat/expiry/confirmation tests conserve inventory and never produce negative or stranded seats. | Backend + database QA | M015 | Idempotent holds and durable expiry/release implemented in forward SQL body; concurrency DB test pending. | Not evidenced by these deliveries | https://drive.google.com/file/d/15X3_uSbHztLL57IL_d3Xo9hc9zInJuyN/view
M018 | P1 | Payment receipts | Bind one provider receipt atomically to one intended booking and exact amount/currency | Earlier source work; acceptance open | No new completion claim in this increment. | Duplicate reference on same booking is idempotent; reference reuse on another booking is rejected; amount/currency and issuer authority are checked under concurrent confirmation. | Backend + payments owner | M015; M020 | Receipt-to-booking binding and cross-booking reuse rejection implemented; real DB concurrency/payment tests pending. | Not evidenced by these deliveries | https://drive.google.com/file/d/15X3_uSbHztLL57IL_d3Xo9hc9zInJuyN/view
M019 | P1 | Subscription periods | Serialize paid subscription renewals by profile and vehicle type | Earlier source work; acceptance open | No new completion claim in this increment. | Deterministic two-session test with distinct receipts preserves both paid durations without overlap; duplicate invoice retry creates exactly one activation; expiry boundaries are explicit. | Backend + database QA | M016 | Entitlement serialization candidate exists in strict receipt body; real two-session DB test pending. | Not evidenced by these deliveries | https://drive.google.com/file/d/15X3_uSbHztLL57IL_d3Xo9hc9zInJuyN/view
M020 | P1 | Merchant configuration | Make merchant identity, currency and receipt formats explicit validated configuration | Earlier source work; acceptance open | No new completion claim in this increment. | Each enabled collector maps to approved merchant/account/operator/currency and parser fixtures; missing or wrong configuration blocks auto-credit with visible reason; no guessed merchant identifier. | Payments operations + backend | Approved merchant/operator inventory | Explicit merchant/sender policy structure implemented; approved live operator configuration not supplied. | Not evidenced by these deliveries | https://drive.google.com/file/d/15X3_uSbHztLL57IL_d3Xo9hc9zInJuyN/view
M021 | P1 | Financial retries | Use durable account-scoped wallet operation IDs and reconcile uncertain outcomes | Open; no completion evidence | No new completion claim in this increment. | Response loss, process restart, account switch and failed storage retain correct operation identity or block unsafe retry; committed operation is discoverable; duplicate retry cannot charge twice. | Flutter + backend | M003; M006; M054 | No completion claimed by these increments. Original audit acceptance criteria remain applicable. | Not evidenced by these deliveries | https://drive.google.com/file/d/15X3_uSbHztLL57IL_d3Xo9hc9zInJuyN/view
M022 | P1 | Financial boundaries | Specify and test refunds, cancellation, monetary precision and time boundaries | Open; no completion evidence | No new completion claim in this increment. | Approved rules and tests cover invalid/zero/negative/large amounts, currency, timezone/day rollover, duplicate refund, cancellation after payment and reconciliation; no new settlement engine is introduced. | Product + payments + backend | M017; M018; M019; M024 | No completion claimed by these increments. Original audit acceptance criteria remain applicable. | Not evidenced by these deliveries | https://drive.google.com/file/d/15X3_uSbHztLL57IL_d3Xo9hc9zInJuyN/view
M023 | P1 | Financial reconciliation | Reconcile collector receipts, ingestion outcomes and activated invoices with operator records | Open; no completion evidence | No new completion claim in this increment. | Daily exception report reconciles eligible receipts, duplicate/rejected/quarantined cases and credits to trusted operator evidence; lost receipt/manual resolution is audited without permissive auto-match. | Payments operations + backend | M016; M028; M034 | No completion claimed by these increments. Original audit acceptance criteria remain applicable. | Not evidenced by these deliveries | https://drive.google.com/file/d/15X3_uSbHztLL57IL_d3Xo9hc9zInJuyN/view
M024 | P1 | Operating authority | Obtain a feature-specific payments/transport classification and responsibility decision | Open; no completion evidence | No new completion claim in this increment. | Current primary rules and actual funds flow support a written decision for each enabled paid feature; provider/agency contracts, responsible entity and customer promises are recorded; unresolved features stay disabled. | Product lead + qualified Rwanda counsel | Feature and funds-flow draft; coordinate with refund design | No completion claimed by these increments. Original audit acceptance criteria remain applicable. | Not evidenced by these deliveries | https://drive.google.com/file/d/15X3_uSbHztLL57IL_d3Xo9hc9zInJuyN/view
M025 | P1 | Collector signing | Replace debug-keystore operational packaging with a managed production signing/update path | Earlier source work; acceptance open | No new completion claim in this increment. | Distribution artifact uses approved managed signing; signature/version verified; enrolled request-signing identity and pending receipts survive supported updates or a documented controlled migration. | Android release + fleet operations | M002 | Managed collector signing guard; non-destructive installer verifies independently approved certificate. Six parser tests pass; no signed APK/key rotation/fleet update observed. | Not evidenced by these deliveries | https://drive.google.com/file/d/15X3_uSbHztLL57IL_d3Xo9hc9zInJuyN/view
M026 | P1 | Collection minimization | Filter eligible receipt data on-device and present a clear upload/AI-processing notice | Earlier source work; acceptance open | No new completion claim in this increment. | Unrelated sender/content fixtures never enter queue or network; notice explains purpose, recipients, retention and support before access; changed formats route to minimal controlled review without auto-credit. | Android + privacy + payments | M020 | Literal on-device sender/marker filter, opt-in fingerprinted notice and pause control implemented. Pure policy tests pass; Android permission/device behavior and actual operator formats not accepted. | Not evidenced by these deliveries | https://drive.google.com/file/d/15X3_uSbHztLL57IL_d3Xo9hc9zInJuyN/view
M027 | P1 | Distribution policy | Document private fleet distribution and obtain SMS/FGS approval if using public Play | Earlier source work; acceptance open | No new completion claim in this increment. | Actual channel and authorized device population recorded; applicable Play exception/permission and foreground-service review evidence supplied before public distribution; private-policy claims match access controls. | Android release + compliance | M025; M026 | Private-fleet/public-store boundary documented. No channel approval, SMS exception or FGS approval obtained. | Not evidenced by these deliveries | https://drive.google.com/file/d/15X3_uSbHztLL57IL_d3Xo9hc9zInJuyN/view
M028 | P1 | Durable queue | Use a transactional bounded receipt queue with corruption quarantine and retained acknowledgement state | Earlier source work; acceptance open | No new completion claim in this increment. | Crash/restart/disk-full/corrupt-row and partial-ack tests preserve eligible records; bounded batches/age/bytes and dedupe retention verified; capacity alerts precede exhaustion; migration is lossless. | Android + backend | M026 | Bounded transactional SQLite adapter with legacy migration/quarantine and raw-body removal on acknowledgement implemented. Fifteen actual SQLite schema/DML tests pass; Android adapter tests authored but not run; supervised recovery still required. | Not evidenced by these deliveries | https://drive.google.com/file/d/15X3_uSbHztLL57IL_d3Xo9hc9zInJuyN/view
M029 | P1 | Retry coordination | Centralize collector work leasing, backoff and response handling | Updated in Increment04 | Durable worker retry/lease code and sanitized retry outcomes; provider and database acceptance remain open. | Test actual retry/timeout/offline delivery and operator reconciliation. | Android + backend | M028 | Shared OS file lease including separate-process tests, persisted jitter/backoff, bounded batches and KEEP scheduling implemented. Android/WorkManager lifecycle acceptance not run. | Not evidenced by these deliveries | https://drive.google.com/file/d/15X3_uSbHztLL57IL_d3Xo9hc9zInJuyN/view
M030 | P1 | Collector lifecycle | Verify boot, force-stop, OEM battery and Android job-quota behavior on managed devices | Earlier source work; acceptance open | No new completion claim in this increment. | Real fleet models pass reboot/update/offline/process-death/Doze/restricted-permission cases; force-stop and OEM limitations are visible with reconciliation instructions; no fictitious always-on guarantee. | Android QA + fleet operations | M025; M028; M029 | Version-bound device/OEM/reboot/update acceptance matrix and isolated QA tests added. No physical-device result. | Not evidenced by these deliveries | https://drive.google.com/file/d/15X3_uSbHztLL57IL_d3Xo9hc9zInJuyN/view
M031 | P1 | Legacy ingest authority | Inventory deployed legacy SMS callers and retire or harden shared-secret ingest aliases | Earlier source work; acceptance open | No new completion claim in this increment. | Deployed endpoint/caller inventory complete; unused routes return a controlled retirement response; retained routes use registered collector authority, replay/body/rate bounds and monitored migration. | Backend + security + operations | M016; M029 | Legacy global-secret SMS POST routes return controlled retirement; local handler fixtures pass; deployment/caller inventory pending. | Not evidenced by these deliveries | https://drive.google.com/file/d/15X3_uSbHztLL57IL_d3Xo9hc9zInJuyN/view
M032 | P1 | Backend intake | Persist authenticated receipt admission before asynchronous parsing and allocation | Updated in Increment04 | Asynchronous batch admission, private persistent queue, separate worker and lease-fenced allocator completion implemented. 86 Node handler fixtures pass; SQL not executed. | Execute body07, full-schema financial tests and real collector-to-worker staging end to end; then approve rollout. | Backend + SRE | M016; M028; M029 | Full asynchronous durable backend intake/worker is NOT implemented. Eligible batch parsing remains sequential; health/admission preflight does not close this task. | Not evidenced by these deliveries | https://drive.google.com/file/d/15X3_uSbHztLL57IL_d3Xo9hc9zInJuyN/view
M033 | P1 | Fleet security | Establish dedicated institutional devices/SIMs, enrollment, revocation and replacement procedures | Earlier source work; acceptance open | No new completion claim in this increment. | Named custodians and inventory; dedicated SIM restriction, screen/device protection, enrollment approval, lost-device revocation, replacement/export policy and staff training rehearsed with no personal-SMS collection. | Fleet operations + security | M025; M026; M027 | Fleet custodian/enrollment/revocation/recovery responsibilities documented; actual organizational inventory and exercises remain open. | Not evidenced by these deliveries | https://drive.google.com/file/d/15X3_uSbHztLL57IL_d3Xo9hc9zInJuyN/view
M034 | P1 | Collector health | Expose truthful enrolled/configured/connected/acknowledged state and backlog age | Updated in Increment04 | Signed health now reads intake storage, queue/review counts and worker heartbeat; scheduling templates supplied. | Exercise real fleet health, alerts, worker scheduling and acknowledgement semantics on devices. | Android + operations | M028; M029; M032 | Signed server-health handshake, separate allocation state, freshness, queue/review/capacity status and safe UI failure state implemented. Actual handler fixtures pass; Android UI not run. | Not evidenced by these deliveries | https://drive.google.com/file/d/15X3_uSbHztLL57IL_d3Xo9hc9zInJuyN/view
M035 | P1 | Face release policy | Keep Face-USSD disabled until exact current scope is accepted and health surfaces agree | Open; no completion evidence | No new completion claim in this increment. | One versioned decision binds approved no-liveness recipient lookup, model/policy/index and health semantics; enablement requires acceptance; manual/QR alternatives remain usable; dialer launch never means settlement. | Product + backend + release | M036; M037; M038; M039; M040; M067; M068 | No completion claimed by these increments. Original audit acceptance criteria remain applicable. | Not evidenced by these deliveries | https://drive.google.com/file/d/15X3_uSbHztLL57IL_d3Xo9hc9zInJuyN/view
M036 | P1 | Inference artifact | Build and verify the exact Linux inference image, models and private service bindings | Open; no completion evidence | No new completion claim in this increment. | Immutable image/model digests and licences recorded; real health/embed tests pass in Linux container; Worker authentication, private binding, index dimension/version and environment isolation verified. | Platform + ML engineer | M077; M082 | No completion claimed by these increments. Original audit acceptance criteria remain applicable. | Not evidenced by these deliveries | https://drive.google.com/file/d/15X3_uSbHztLL57IL_d3Xo9hc9zInJuyN/view
M037 | P1 | Deployment contracts | Rehearse latest face migrations, PostgREST/Edge, Vault and scheduled maintenance together | Open; no completion evidence | No new completion claim in this increment. | Full-schema rehearsal verifies exact RPC argument/privilege/session contract; deployment history, secrets presence and scheduled execution read back; activation and deletion converge after provider interruption. | Backend + platform + database QA | M036; M078 | No completion claimed by these increments. Original audit acceptance criteria remain applicable. | Not evidenced by these deliveries | https://drive.google.com/file/d/15X3_uSbHztLL57IL_d3Xo9hc9zInJuyN/view
M038 | P1 | Matching acceptance | Calibrate and independently accept matching thresholds and cross-owner margins | Open; no completion evidence | No new completion claim in this increment. | Pre-agreed error/latency criteria; held-out consented cohort covering lighting, skin tones, age and devices; report denominators, gallery size, uncertainty and thresholds/model hash; ambiguous matches fail safely. | ML QA + product + privacy | M036; M067; M068 | No completion claimed by these increments. Original audit acceptance criteria remain applicable. | Not evidenced by these deliveries | https://drive.google.com/file/d/15X3_uSbHztLL57IL_d3Xo9hc9zInJuyN/view
M039 | P1 | Biometric deletion | Exercise pause/remove/replacement and delayed-upsert cleanup end to end | Open; no completion evidence | No new completion claim in this increment. | Immediate discovery exclusion plus eventual verified vector absence; cancellation, replacement, delayed insert, provider outage and restored-backup cases pass; cleanup owner/SLA and tombstone retention approved. | Backend QA + privacy + operations | M036; M037 | No completion claimed by these increments. Original audit acceptance criteria remain applicable. | Not evidenced by these deliveries | https://drive.google.com/file/d/15X3_uSbHztLL57IL_d3Xo9hc9zInJuyN/view
M040 | P1 | Camera-to-USSD acceptance | Run physical-device face capture through one correct operator dialer handoff | Open; no completion evidence | No new completion claim in this increment. | Selected receiving method/number resolves correctly; changed/paused payee, timeout, interruption, cancellation, restart, dual-SIM and denial cases pass; one amount-free Android handoff; iOS fallback is clear. | Mobile QA + operator liaison | M036; M037; M038; M046; M051 | No completion claimed by these increments. Original audit acceptance criteria remain applicable. | Not evidenced by these deliveries | https://drive.google.com/file/d/15X3_uSbHztLL57IL_d3Xo9hc9zInJuyN/view
M041 | P1 | Launch capacity | Measure cold/warm latency, burst admission and regional network performance at the launch workload | Open; no completion evidence | No new completion claim in this increment. | Approved workload and p95/error budget met from target Rwandan networks; report busy/cold-start/index latency/memory/CPU; bounded capacity and safe retry decisions use results rather than autoscaling assumptions. | Performance + platform + ML | M036; M038 | No completion claimed by these increments. Original audit acceptance criteria remain applicable. | Not evidenced by these deliveries | https://drive.google.com/file/d/15X3_uSbHztLL57IL_d3Xo9hc9zInJuyN/view
M042 | P2 | Inference serving | Use bounded production HTTP serving with graceful drain and failure limits | Earlier source work; acceptance open | No new completion claim in this increment. | Saturation, slow/truncated/oversized body, concurrent request, termination during inference and restart tests pass; no raw payload logs or arbitrary URL fetch; concurrency and deadlines remain bounded. | Backend + platform | M036; M041 | Inference HTTP service bounded/draining behavior implemented and 16 tests pass; real Linux model/image and load acceptance pending. | Not evidenced by these deliveries | https://drive.google.com/file/d/15X3_uSbHztLL57IL_d3Xo9hc9zInJuyN/view
M043 | P1 | Face state consistency | Test cross-system enrollment/lookup races and fail-closed identity transitions | Open; no completion evidence | No new completion claim in this increment. | Concurrent enrollment/replacement, account switch, consent withdrawal, route change, expired ticket, model mismatch and ambiguous result cannot produce a stale payee handoff; retries preserve at-most-once semantics. | Backend + Flutter QA | M037; M039; M055 | No completion claimed by these increments. Original audit acceptance criteria remain applicable. | Not evidenced by these deliveries | https://drive.google.com/file/d/15X3_uSbHztLL57IL_d3Xo9hc9zInJuyN/view
M044 | P1 | Android release | Target API 36 and verify Android 16 behavior for the consumer release | Earlier source work; acceptance open | No new completion claim in this increment. | Release manifest confirms target36; edge-to-edge, predictive back, large-screen layouts, foreground services and permissions pass; actual Play preflight/extension status recorded separately from existing-app availability. | Android + Flutter + QA | M074; M077 | Consumer targetSdk set to 36; signed Android 16 build/device/Play preflight not run. | Not evidenced by these deliveries | https://drive.google.com/file/d/15X3_uSbHztLL57IL_d3Xo9hc9zInJuyN/view
M045 | P1 | Android native libraries | Verify every shipped native library and release package on 16 KB pages | Open; no completion evidence | No new completion claim in this increment. | Inspect exact AAB/APKs and ELF/RELRO alignment, run zip alignment checks, install and exercise native/camera paths on 16 KB device/emulator; retain artifact evidence before 2027-02-01 update enforcement. | Android release + QA | M044; M081 | No completion claimed by these increments. Original audit acceptance criteria remain applicable. | Not evidenced by these deliveries | https://drive.google.com/file/d/15X3_uSbHztLL57IL_d3Xo9hc9zInJuyN/view
M046 | P1 | iOS release | Produce a signed Xcode 26+ archive and verify production entitlements/device behavior | Open; no completion evidence | No new completion claim in this increment. | Xcode/iOS SDK versions asserted; signed archive entitlements/provisioning verified; TestFlight install, APNs, camera/location/NFC and recovery pass on supported iPhones; no native macOS product is implied. | iOS release + QA | M002; M077; M081 | No completion claimed by these increments. Original audit acceptance criteria remain applicable. | Not evidenced by these deliveries | https://drive.google.com/file/d/15X3_uSbHztLL57IL_d3Xo9hc9zInJuyN/view
M047 | P1 | NFC lifecycle | Enforce NFC advertisement expiry and owner lifecycle in the native APDU service | Earlier source work; acceptance open | No new completion claim in this increment. | Expired, signed-out, reset, changed-owner and restarted states cannot serve stale payload; exact APDU validation tested; explicit stop clears persistent material and UI reflects current state. | Android + Flutter | M007; M055 | NFC native expiry/APDU policy implemented and 20 JVM scenarios pass; hardware/process/device acceptance pending. | Not evidenced by these deliveries | https://drive.google.com/file/d/15X3_uSbHztLL57IL_d3Xo9hc9zInJuyN/view
M048 | P1 | Verified links | Verify Android App Links and iOS Universal Links against actual signed application identities | Open; no completion evidence | No new completion claim in this increment. | Production association files match package/bundle and current signing identities; payment/auth/admin link open, malformed link, browser fallback and reinstall cases pass without open redirects or account confusion. | Mobile + web release QA | M002; M044; M046 | No completion claimed by these increments. Original audit acceptance criteria remain applicable. | Not evidenced by these deliveries | https://drive.google.com/file/d/15X3_uSbHztLL57IL_d3Xo9hc9zInJuyN/view
M049 | P1 | Permissions and FGS | Align minimum permissions, background location and foreground-service declarations with visible product use | Open; no completion evidence | No new completion claim in this increment. | Permission-denied/revoked/background states behave safely; background location disclosure/video and applicable FGS purpose declarations accepted for actual release; no unused permissions or misleading always-on promise. | Android/iOS + privacy + release | M056; M065 | No completion claimed by these increments. Original audit acceptance criteria remain applicable. | Not evidenced by these deliveries | https://drive.google.com/file/d/15X3_uSbHztLL57IL_d3Xo9hc9zInJuyN/view
M050 | P1 | SDK privacy | Audit bundled SDK data collection, required-reason APIs and archive privacy manifests | Open; no completion evidence | No new completion claim in this increment. | Final archive privacy report and Android SDK inventory map actual collection to notices/store answers; necessary manifests/reasons present; analytics/ads dependencies and consent choices are justified by measured configuration. | iOS/Android + privacy | M046; M065; M068 | No completion claimed by these increments. Original audit acceptance criteria remain applicable. | Not evidenced by these deliveries | https://drive.google.com/file/d/15X3_uSbHztLL57IL_d3Xo9hc9zInJuyN/view
M051 | P1 | Operator continuity | Validate USSD/SMS on current Rwanda operators, SIM options and 4G/VoLTE devices | Open; no completion evidence | No new completion claim in this increment. | Approved handset/SIM/operator matrix covers dual-SIM, permission defaults, low coverage and 4G/VoLTE; track 2027-06-30 3G transition guidance without claiming USSD disappears; collector hardware choice is evidence-based. | Operator liaison + mobile QA | M044; M046 | No completion claimed by these increments. Original audit acceptance criteria remain applicable. | Not evidenced by these deliveries | https://drive.google.com/file/d/15X3_uSbHztLL57IL_d3Xo9hc9zInJuyN/view
M052 | P1 | Store readiness | Reconcile store content, version identity, age-rating questions and reviewer instructions | Open; no completion evidence | No new completion claim in this increment. | Current feature scope, screenshots, support/privacy/deletion URLs, permissions and age-rating answers agree with signed artifact; exact version/build and review access verified; draft/internal submission reviewed before publication. | Release + product + privacy | M011; M044; M046; M050; M065 | No completion claimed by these increments. Original audit acceptance criteria remain applicable. | Not evidenced by these deliveries | https://drive.google.com/file/d/15X3_uSbHztLL57IL_d3Xo9hc9zInJuyN/view
M053 | P1 | Startup resilience | Bound minimum bootstrap and defer optional Firebase/config/push work | Open; no completion evidence | No new completion claim in this increment. | Airplane mode, slow DNS, captive portal and Firebase outage produce usable cached/retry states; mandatory configuration still fails closed; cold/warm release launch measurements meet agreed budget. | Flutter | M012 | No completion claimed by these increments. Original audit acceptance criteria remain applicable. | Not evidenced by these deliveries | https://drive.google.com/file/d/15X3_uSbHztLL57IL_d3Xo9hc9zInJuyN/view
M054 | P1 | Request outcomes | Standardize request deadlines and distinguish unknown mutation outcomes from failure | Open; no completion evidence | No new completion claim in this increment. | Read timeouts show recoverable unavailable states; writes retain operation identity and query status after response loss; no false payment-success label or blind duplicated mutation. | Flutter + backend | M091; shared operation-outcome contract | No completion claimed by these increments. Original audit acceptance criteria remain applicable. | Not evidenced by these deliveries | https://drive.google.com/file/d/15X3_uSbHztLL57IL_d3Xo9hc9zInJuyN/view
M055 | P1 | Account-bound async work | Apply account and generation checks across Profile, shell, bookings and pending operations | Open; no completion evidence | No new completion claim in this increment. | Delay A responses until after B signs in; no A profile/role/data changes B UI; rapid mode/search changes discard stale results and disposed work cannot restore listeners. | Flutter | M007 | No completion claimed by these increments. Original audit acceptance criteria remain applicable. | Not evidenced by these deliveries | https://drive.google.com/file/d/15X3_uSbHztLL57IL_d3Xo9hc9zInJuyN/view
M056 | P1 | Location authority | Bind driver sharing to its account and enforce server freshness, radius and result caps | Earlier source work; acceptance open | No new completion claim in this increment. | Concurrent start/stop/account changes cannot resurrect sharing; stale presence excluded on all surfaces; bounded radius/limit and coordinate precision follow purpose; denied/revoked permission marks unavailable/offline. | Flutter + backend + privacy | M007; M055 | Nearby RPC freshness/10km/50 cap and direct-read restriction body prepared; real DB/geospatial/load/device test pending. | Not evidenced by these deliveries | https://drive.google.com/file/d/15X3_uSbHztLL57IL_d3Xo9hc9zInJuyN/view
M057 | P1 | Truthful status | Represent unknown/unavailable face state distinctly from not enrolled | Earlier source work; acceptance open | No new completion claim in this increment. | Existing enrollment is never displayed as absent solely from service failure; loading, unavailable and approved cached state are distinct; retry and pause/remove recovery remain usable. | Flutter | M055 | Face-service outage represented as unavailable rather than not-started; Flutter UI runtime test pending. | Not evidenced by these deliveries | https://drive.google.com/file/d/15X3_uSbHztLL57IL_d3Xo9hc9zInJuyN/view
M058 | P1 | Launch localization | Complete and review critical journeys in each promised launch language | Open; no completion evidence | No new completion claim in this increment. | Supported language promise documented; login, money, consent, permission, deletion, moderation, support and error journeys translated and fluent-reviewed; Kinyarwanda/French formatting and text expansion accepted where promised. | Flutter + localization + product | M065 | No completion claimed by these increments. Original audit acceptance criteria remain applicable. | Not evidenced by these deliveries | https://drive.google.com/file/d/15X3_uSbHztLL57IL_d3Xo9hc9zInJuyN/view
M059 | P2 | Secondary localization | Finish secondary/admin copy and locale-aware dates, pluralization and currency | Open; no completion evidence | No new completion claim in this increment. | Inventory of remaining hardcoded user-facing copy closed or explicitly deferred; each supported locale has reviewed plural/date/currency behavior and screenshots without truncation. | Flutter + localization | M058 | No completion claimed by these increments. Original audit acceptance criteria remain applicable. | Not evidenced by these deliveries | https://drive.google.com/file/d/15X3_uSbHztLL57IL_d3Xo9hc9zInJuyN/view
M060 | P1 | Accessibility | Run existing accessibility coverage and physical assistive-technology journey acceptance | Open; no completion evidence | No new completion claim in this increment. | TalkBack/VoiceOver, keyboard, 200% text, contrast/touch targets, focus, error announcements and reduced motion pass across accepted journeys and screen sizes; intended automatic handoff is clearly announced. | QA + design + Flutter | M053; M058; M076 | No completion claimed by these increments. Original audit acceptance criteria remain applicable. | Not evidenced by these deliveries | https://drive.google.com/file/d/15X3_uSbHztLL57IL_d3Xo9hc9zInJuyN/view
M061 | P2 | Chat reliability | Add stable client-message IDs, uncertain-send reconciliation and cursor history | Open; no completion evidence | No new completion claim in this increment. | Lost acknowledgement/retry and restart yield one message; draft remains owner-scoped; reconnect recovery works; cursor pagination preserves ordering for conversations over 100 messages when full history is promised. | Flutter + backend | M007; M054 | No completion claimed by these increments. Original audit acceptance criteria remain applicable. | Not evidenced by these deliveries | https://drive.google.com/file/d/15X3_uSbHztLL57IL_d3Xo9hc9zInJuyN/view
M062 | P1 | Operational switches | Implement exercised server feature controls and truthful client maintenance messaging | Open; no completion evidence | No new completion claim in this increment. | Already-running clients respond to scoped suspension; server rejects affected writes; manual/QR/read-only recovery remains as approved; expiry/rollback and operator ownership are tested. | Backend + Flutter + SRE | M015; M016; approved enabled-feature scope | No completion claimed by these increments. Original audit acceptance criteria remain applicable. | Not evidenced by these deliveries | https://drive.google.com/file/d/15X3_uSbHztLL57IL_d3Xo9hc9zInJuyN/view
M063 | P2 | Maintainability | Refactor touched oversized screens and overloaded models into typed application/repository boundaries | Open; no completion evidence | No new completion claim in this increment. | Typed person/trip/member-ID and RPC outcome contracts replace lossy seams; changed workflows have focused tests; preserve Riverpod/GoRouter and avoid an unrelated framework rewrite. | Flutter technical lead | M006; M007; M054 | No completion claimed by these increments. Original audit acceptance criteria remain applicable. | Not evidenced by these deliveries | https://drive.google.com/file/d/15X3_uSbHztLL57IL_d3Xo9hc9zInJuyN/view
M064 | P2 | Mobile performance | Measure release/profile launch, frame timing, camera memory and location battery cost | Open; no completion evidence | No new completion claim in this increment. | Representative lower-cost Android and iPhone reports include configuration and p50/p95; accepted budgets cover startup, jank, memory, upload size, battery/network and admin lists; optimize only demonstrated bottlenecks. | Performance QA + Flutter/native | M053; M056; M060 | No completion claimed by these increments. Original audit acceptance criteria remain applicable. | Not evidenced by these deliveries | https://drive.google.com/file/d/15X3_uSbHztLL57IL_d3Xo9hc9zInJuyN/view
M065 | P1 | Privacy inventory and notices | Publish a current feature/data inventory and reconcile privacy, terms and deletion copy | Open; no completion evidence | No new completion claim in this increment. | Each enabled field/store/processor has purpose, role, destination, retention and deletion mapping; public/store/in-app copy matches actual scope; superseded statements are labelled historical and no anonymous-template claim remains. | Privacy + product + engineering | M068; M024 if paid features enabled; M067 for enabled high-risk features | No completion claimed by these increments. Original audit acceptance criteria remain applicable. | Not evidenced by these deliveries | https://drive.google.com/file/d/15X3_uSbHztLL57IL_d3Xo9hc9zInJuyN/view
M066 | P1 | Governance evidence | Record operator/controller registration, overseas-storage scope and accountable DPO | Open; no completion evidence | No new completion claim in this increment. | Current official requirements and entity applicability checked; certificate/expiry/conditions and DPO appointment/contact documented; outstanding conditions have owners and affected-feature decisions. | Qualified Rwanda counsel + privacy lead | Operator and enabled-feature inventory draft | No completion claimed by these increments. Original audit acceptance criteria remain applicable. | Not evidenced by these deliveries | https://drive.google.com/file/d/15X3_uSbHztLL57IL_d3Xo9hc9zInJuyN/view
M067 | P1 | Impact assessment | Complete a scoped impact/risk assessment for face lookup, location and institutional SMS | Open; no completion evidence | No new completion claim in this increment. | Document actual no-liveness lookup purpose, consent/withdrawal, false-match risk, unknown persons, retention, security and alternatives; approve residual risk before affected feature activation. | Privacy lead + qualified counsel + security | M024; M026; M056; M066 | No completion claimed by these increments. Original audit acceptance criteria remain applicable. | Not evidenced by these deliveries | https://drive.google.com/file/d/15X3_uSbHztLL57IL_d3Xo9hc9zInJuyN/view
M068 | P1 | Processors and data location | Verify actual vendor regions, contracts, subprocessors and lawful overseas arrangements | Open; no completion evidence | No new completion claim in this increment. | Supabase primary/backups/logs and Cloudflare inference/vectors/logs plus Meta/OpenAI/analytics data flows recorded; accepted agreements and lawful arrangements match actual use; unsupported Rwanda-only/region promises removed. | Privacy + platform + qualified counsel | M066 | No completion claimed by these increments. Original audit acceptance criteria remain applicable. | Not evidenced by these deliveries | https://drive.google.com/file/d/15X3_uSbHztLL57IL_d3Xo9hc9zInJuyN/view
M069 | P1 | Account deletion | Implement authenticated deletion initiation, status and cross-store completion | Open; no completion evidence | No new completion claim in this increment. | Synthetic account deletion covers Auth sessions, SQL, Storage, push, vectors and applicable analytics; retries and legal retention exceptions tracked; in-app and web initiation/status work without hidden manual-only steps. | Backend + Flutter + privacy + support | M007; M008; M065; M039 if Face enabled | No completion claimed by these increments. Original audit acceptance criteria remain applicable. | Not evidenced by these deliveries | https://drive.google.com/file/d/15X3_uSbHztLL57IL_d3Xo9hc9zInJuyN/view
M070 | P1 | Retention and requests | Set data-class retention and implement receipt-based request deadlines with verified purge | Open; no completion evidence | No new completion claim in this increment. | Approve periods, triggers, exceptions, backup treatment and purge owners. Within 30 days of request receipt, provide written/electronic substantive erasure notification under applicable rules; acknowledgement alone is insufficient. Verify completed deletion or justified retained-data decisions, staging purges and deletion replay after restore. | Privacy + backend + support | M065; M069; retention and backup design | No completion claimed by these increments. Original audit acceptance criteria remain applicable. | Not evidenced by these deliveries | https://drive.google.com/file/d/15X3_uSbHztLL57IL_d3Xo9hc9zInJuyN/view
M071 | P1 | Retired AWS resources | Inventory and obtain scoped authorization to retire old face-only AWS data and credentials | Open; no completion evidence | No new completion claim in this increment. | Read-only account/resource inventory and owner decision; separately authorized named-resource deletion/key retirement receipts; no active AWS fallback and no unrelated shared resource loss. | Platform + security + privacy | M001; M065 | No completion claimed by these increments. Original audit acceptance criteria remain applicable. | Not evidenced by these deliveries | https://drive.google.com/file/d/15X3_uSbHztLL57IL_d3Xo9hc9zInJuyN/view
M072 | P1 | Age boundaries | Decide and implement proportionate age rules for passenger, driver and face functions | Open; no completion evidence | No new completion claim in this increment. | Consistent per-role policy and proportionate declaration/restriction; underage reports and applicable guardian handling documented; no unnecessary identity-document collection introduced. | Product + privacy + qualified counsel | M065; M067 | No completion claimed by these increments. Original audit acceptance criteria remain applicable. | Not evidenced by these deliveries | https://drive.google.com/file/d/15X3_uSbHztLL57IL_d3Xo9hc9zInJuyN/view
M073 | P1 | WhatsApp operating contract | Verify live authentication templates/delivery and separate marketing permissions | Open; no completion evidence | No new completion claim in this increment. | Approved WABA/number/template/category/language/components and supported Graph version recorded; real device delivery/resend/expired-code/outage recovery tested; campaign opt-out suppresses future promotional sends. | Messaging operations + backend + privacy | M012; M068; M091 | No completion claimed by these increments. Original audit acceptance criteria remain applicable. | Not evidenced by these deliveries | https://drive.google.com/file/d/15X3_uSbHztLL57IL_d3Xo9hc9zInJuyN/view
M074 | P1 | CI correctness | Repair Actions pin validation to permit local reusable workflows and reject unpinned remote actions | Earlier source work; acceptance open | No new completion claim in this increment. | Actual source pin gate exits zero; valid local fixture passes and tagged/unpinned remote fixtures fail; parser distinguishes reusable workflow and remote action syntax. | DevOps | None | Actions pin checker repaired and 29 source/fixture tests plus repo check pass; remote CI run pending. | Not evidenced by these deliveries | https://drive.google.com/file/d/15X3_uSbHztLL57IL_d3Xo9hc9zInJuyN/view
M075 | P1 | Release gate truth | Make skipped/unavailable required checks non-releasable and wire aggregate gates into promotion | Earlier source work; acceptance open | No new completion claim in this increment. | Production invocation rejects disabling mandatory child checks; pass/failed/skipped/unavailable have distinct status; Android/PWA/services promotion requires all applicable gates for one exact artifact. | Release engineer + DevOps | M074 | Integrated gate rejects disabled/invalid required checks; fixture tests pass; promotion workflow execution pending. | Not evidenced by these deliveries | https://drive.google.com/file/d/15X3_uSbHztLL57IL_d3Xo9hc9zInJuyN/view
M076 | P1 | Visual acceptance | Resolve unaccepted reference goldens against the approved design and rerun the full Flutter suite | Open; no completion evidence | No new completion claim in this increment. | Each difference classified as intended or regression; only reviewed baselines change; complete suite including reference goldens passes on pinned toolchain with revision-linked results. | QA + design + Flutter | M074 | No completion claimed by these increments. Original audit acceptance criteria remain applicable. | Not evidenced by these deliveries | https://drive.google.com/file/d/15X3_uSbHztLL57IL_d3Xo9hc9zInJuyN/view
M077 | P1 | Coverage in CI | Add required checks for every shipped implementation and native collector | Updated in Increment04 | New 86 Node tests and 28 Python operational/applier/source checks are wired into the existing CI workflow. Hosted CI not run. | Run hosted required checks plus full native/database/Deno lanes; configure protected-branch requirements. | DevOps + subsystem owners | M074; M075 | Native collector QA compilation/JUnit/package-isolation job and portable SQLite/JVM checks added to CI. Local portable tests pass; hosted CI and Android build have not run. | Not evidenced by these deliveries | https://drive.google.com/file/d/15X3_uSbHztLL57IL_d3Xo9hc9zInJuyN/view
M078 | P1 | Database rehearsal | Run all migrations on clean PostgreSQL 17 and a representative forward-upgrade copy | Updated in Increment04 | Seventh forward SQL body, manifest, post-install assertions and guarded PostgreSQL17 component/concurrency runner supplied; runtime unavailable. | Rehearse full original schema plus bodies01-07 and sanitized forward upgrade on PostgreSQL17. | DBA + backend QA | M003; M015; M017; M018; M019 | Ordered migration preparer, manifest and post-install assertions implemented; PostgreSQL/Supabase rehearsal pending. | Not evidenced by these deliveries | https://drive.google.com/file/d/15X3_uSbHztLL57IL_d3Xo9hc9zInJuyN/view
M079 | P1 | Adversarial authorization | Run a real database/Edge authorization and transaction matrix after remediation | Updated in Increment04 | Service-only queue grants and catalog probes added to the existing authorization work. No real user-role matrix executed. | Execute the complete real Auth/PostgREST ownership, revocation, role and privilege matrix. | Security QA + backend | M003; M004; M015; M016; M078 | Adversarial fixtures added, but live database/Auth/PostgREST authorization matrix pending. | Not evidenced by these deliveries | https://drive.google.com/file/d/15X3_uSbHztLL57IL_d3Xo9hc9zInJuyN/view
M080 | P1 | Production controls | Read back actual repository/environment protections, secrets and promotion roles | Open; no completion evidence | No new completion claim in this increment. | Current branch/environment rules, required checks, reviewer separation and secret scope recorded for actual repository/account plan; least-privilege deployment roles and emergency path tested without publishing. | Security + release owner | M001; M002; M075 | No completion claimed by these increments. Original audit acceptance criteria remain applicable. | Not evidenced by these deliveries | https://drive.google.com/file/d/15X3_uSbHztLL57IL_d3Xo9hc9zInJuyN/view
M081 | P1 | Release evidence | Bind source, artifacts, migrations, model policy and approvals in a structured release manifest | Earlier source work; acceptance open | No new completion claim in this increment. | Exact commit plus working-tree state, artifact hashes, version equality, migration/model identifiers, environment, reviewer/date and full check receipts validated; stale/example/wrong-artifact/prefix fixtures rejected. | Release engineer | M075; M078; M080 | Exact version-evidence parser and checks strengthened; complete artifact-bound release manifest still pending. | Not evidenced by these deliveries | https://drive.google.com/file/d/15X3_uSbHztLL57IL_d3Xo9hc9zInJuyN/view
M082 | P2 | Dependency security | Pin reproducible toolchains and cover all dependency/container ecosystems with update and advisory review | Earlier source work; acceptance open | No new completion claim in this increment. | Deno/Node/pnpm/Wrangler/container toolchain fixed to tested versions; update coverage and actual advisory triage documented; clean builds reproduce; upgrades are risk-reviewed rather than indiscriminate. | DevSecOps + maintainers | M077 | Additional dependency/toolchain pinning and update coverage added; complete advisory/SBOM review pending. | Not evidenced by these deliveries | https://drive.google.com/file/d/15X3_uSbHztLL57IL_d3Xo9hc9zInJuyN/view
M083 | P2 | Supply-chain records | Produce verified SBOM/provenance and retain licences, symbols and source maps for supported releases | Open; no completion evidence | No new completion claim in this increment. | Distributed artifact SBOM and provenance verify against release hashes; model/SDK licences archived; symbol/source-map access and crash symbolication tested for supported versions. | DevSecOps + release | M081; M082 | No completion claimed by these increments. Original audit acceptance criteria remain applicable. | Not evidenced by these deliveries | https://drive.google.com/file/d/15X3_uSbHztLL57IL_d3Xo9hc9zInJuyN/view
M084 | P1 | Observability | Instrument privacy-safe service and client health with owned actionable alerts | Open; no completion evidence | No new completion claim in this increment. | Dashboards cover auth, latency/errors, face busy/cleanup, receipt-to-credit, notification backlog, crashes/ANRs and stale presence; named owners/budgets; induced failure alerts correctly with no raw faces, vectors, OTPs or financial identifiers. | SRE + backend + mobile | M032; M034; M037; M056 | No completion claimed by these increments. Original audit acceptance criteria remain applicable. | Not evidenced by these deliveries | https://drive.google.com/file/d/15X3_uSbHztLL57IL_d3Xo9hc9zInJuyN/view
M085 | P1 | Recovery | Define RPO/RTO and rehearse isolated database, Storage, configuration and vector recovery | Open; no completion evidence | No new completion claim in this increment. | Timed isolated restore with outbound jobs disabled meets approved loss/time objectives; SQL/objects/permissions/idempotency reconcile; deletion tombstones reapplied; explicitly choose protected vector restore or consented reenrollment. | DBA + SRE + privacy | M065; M070; M078 | No completion claimed by these increments. Original audit acceptance criteria remain applicable. | Not evidenced by these deliveries | https://drive.google.com/file/d/15X3_uSbHztLL57IL_d3Xo9hc9zInJuyN/view
M086 | P1 | Incident response | Rehearse security/privacy/financial incident ownership and escalation | Open; no completion evidence | No new completion claim in this increment. | Tabletop covers key exposure, wrong credit, lost collector and biometric/PII event; evidence preservation, containment and contacts tested; applicable Rwanda 48-hour notice/72-hour report clocks reviewed by counsel. | Security + privacy + SRE + payments | M001; M023; M066; M084 | No completion claimed by these increments. Original audit acceptance criteria remain applicable. | Not evidenced by these deliveries | https://drive.google.com/file/d/15X3_uSbHztLL57IL_d3Xo9hc9zInJuyN/view
M087 | P1 | Rollout and rollback | Exercise staged release, kill switches and compatible rollback for each enabled surface | Open; no completion evidence | No new completion claim in this increment. | Internal/staged promotion uses defined stop criteria; last-known-good artifacts/configs identified; schema compatibility or forward repair tested; face can be disabled while accepted manual/QR flows continue. | Release + SRE + product | M062; M081; M084; M085 | No completion claimed by these increments. Original audit acceptance criteria remain applicable. | Not evidenced by these deliveries | https://drive.google.com/file/d/15X3_uSbHztLL57IL_d3Xo9hc9zInJuyN/view
M088 | P1 | Launch acceptance | Run a version-bound end-to-end matrix on staging and release-candidate devices | Open; no completion evidence | No new completion claim in this increment. | Exact release journey results cover OTP, discovery/posting, chat/moderation, account lifecycle, manual/QR, chosen paid features and optional face/SMS; offline/denied/timeout/restart cases recorded with clear pass/blocked status. | QA lead + release + feature owners | M044; M046; M049; M052; M060; M073; M079; M081; M040 if Face enabled | No completion claimed by these increments. Original audit acceptance criteria remain applicable. | Not evidenced by these deliveries | https://drive.google.com/file/d/15X3_uSbHztLL57IL_d3Xo9hc9zInJuyN/view
M089 | P1 | Support and moderation | Operationalize existing report/block controls, account recovery and financial exception handling | Open; no completion evidence | No new completion claim in this increment. | Named queues/response targets and escalation paths; staged report/block/unblock, lost WhatsApp access, deletion and disputed receipt drills close with an audit trail; no PIN collection or improvised auth bypass. | Support operations + product + trust/safety | M009; M023; M069; M073; M084 | No completion claimed by these increments. Original audit acceptance criteria remain applicable. | Not evidenced by these deliveries | https://drive.google.com/file/d/15X3_uSbHztLL57IL_d3Xo9hc9zInJuyN/view
M090 | P2 | Source and scope documentation | Publish a clean reproducible source manifest and one current feature/release status map | Updated in Increment04 | New delta/cumulative overlays, before/after hashes, guarded applier, source provenance and evidence logs packaged. | Reconcile with the actual upstream checkout/commit; remove historical secrets and review export permissions. | Repository maintainer + product + release | M001; M081 | Versioned hardening manifest/evidence package produced; canonical repository/source-scope cleanup remains. | Not evidenced by these deliveries | https://drive.google.com/file/d/15X3_uSbHztLL57IL_d3Xo9hc9zInJuyN/view
M091 | P1 | Provider resilience and budgets | Bound external calls and enforce durable rate/cost controls for OTP, maps and AI paths | Updated in Increment04 | Bounded batch/queue capacity, worker concurrency and fixed-hour parser budget implemented in the SQL candidate; bounded trigger supplied. | Measure latency, database contention, receipt volume and provider costs; validate limits and overload recovery. | Backend + SRE + security | M012; M032 | Unapproved sender, missing merchant policy and disabled allocation stop AI parsing before provider disclosure. Retry/response/connect/read bounds added; overall wall-clock deadline and full durable provider budget work remain open. | Not evidenced by these deliveries | https://drive.google.com/file/d/15X3_uSbHztLL57IL_d3Xo9hc9zInJuyN/view
M092 | P2 | Notification delivery | Use a durable notification outbox with leases, bounded retry and token lifecycle | Open; no completion evidence | No new completion claim in this increment. | Notification/token idempotency, lease recovery, TTL, consent, backoff and invalid-token removal work under duplicate dispatch/provider outage; backlog age is visible; no unbounded OAuth/send loop. | Backend + SRE | M008; M084 | No completion claimed by these increments. Original audit acceptance criteria remain applicable. | Not evidenced by these deliveries | https://drive.google.com/file/d/15X3_uSbHztLL57IL_d3Xo9hc9zInJuyN/view
M093 | P2 | Database performance | Load-test bounded discovery, realtime, chat history and financial queries at launch/next-stage volume | Open; no completion evidence | No new completion claim in this increment. | Representative cardinalities and concurrency with EXPLAIN/query statistics meet chosen latency budget; indexes/caps/pagination based on measured plans; retention does not break reconciliation or deletion. | DBA + performance + backend | M056; M078; M084 | No completion claimed by these increments. Original audit acceptance criteria remain applicable. | Not evidenced by these deliveries | https://drive.google.com/file/d/15X3_uSbHztLL57IL_d3Xo9hc9zInJuyN/view
M094 | P2 | Operating economics | Build an observed launch cost model and usage budget with explicit assumptions | Open; no completion evidence | No new completion claim in this increment. | Current account tariffs and observed requests per successful journey drive low/base/peak forecast; budget alerts and owner-approved service caps tested; no invented Rwanda rate or fixed per-scan promise. | Product + finance + SRE | M023; M041; M084; M091 | No completion claimed by these increments. Original audit acceptance criteria remain applicable. | Not evidenced by these deliveries | https://drive.google.com/file/d/15X3_uSbHztLL57IL_d3Xo9hc9zInJuyN/view
M095 | P3 | Measured optimization | Optimize inference pool/index checks only after accepted baseline capacity data | Open; no completion evidence | No new completion claim in this increment. | Measured bottleneck and benefit threshold documented; bounded pool or compatibility-cache change preserves model/consent correctness and cost cap; before/after load and failure results demonstrate improvement. | Performance + platform | M038; M041; M084; M094 | No completion claimed by these increments. Original audit acceptance criteria remain applicable. | Not evidenced by these deliveries | https://drive.google.com/file/d/15X3_uSbHztLL57IL_d3Xo9hc9zInJuyN/view

## Verification
Verification ¦ What actually ran
Counts exclude historical package claims. Database, native-device and deployed acceptance are explicitly separated from local checks.
Lane | Result | Count | Boundary / qualification | Evidence
New Node admission/worker fixtures | PASS | 86 | Actual TypeScript handler logic and WebCrypto RSA; explicit registry/database/parser fixtures. | evidence/ and VALIDATION_RESULTS.json
Existing Edge pure-module regressions | PASS | 66 | Rerun locally; does not include all prior package tests. | evidence/ and VALIDATION_RESULTS.json
Python operational/DSN/SQL-source checks | PASS | 20 | 11 executable guard tests and 9 source-contract assertions; no SQL engine. | evidence/ and VALIDATION_RESULTS.json
Guarded delta applier | PASS | 8 | Actual temporary-file checks, drift rejection, symlink/path protection and idempotent application. | evidence/ and VALIDATION_RESULTS.json
TypeScript strict compile | PASS |  | Runtime/Supabase declarations are explicitly substituted; not real SDK or Deno validation. | evidence/ and VALIDATION_RESULTS.json
GitHub action pin check and TOML/shell syntax | PASS |  | Local configuration checks only. | evidence/ and VALIDATION_RESULTS.json
PostgreSQL 17 queue and separate-session tests | UNAVAILABLE | 0 | psql absent; runner returned exit 2. SQL body and concurrency tests NOT executed. | evidence/ and VALIDATION_RESULTS.json
Full schema, real Auth/PostgREST, Deno and model integration | NOT RUN | 0 | No full application/deployed environment acceptance. | evidence/ and VALIDATION_RESULTS.json
Signed Android/iOS, physical-device SMS, USSD and fleet tests | NOT RUN | 0 | No native build or device acceptance in this increment. | evidence/ and VALIDATION_RESULTS.json
Production deployment and hosted required CI | NOT RUN | 0 | No live database, provider, payment or deployed application changes. | evidence/ and VALIDATION_RESULTS.json
The 20 Python guard/source checks comprise 11 executable guard tests and 9 source assertions. They do not execute SQL. The 8 applier tests use real temporary files.

## Sources
Sources ¦ Version and scope
The follow-on review used the latest complete cumulative overlay, the full 95-task register and selected original dependencies.
Source | Use | URL / package path | Qualification
Mobio target folder | Live folder metadata and source tree | https://drive.google.com/drive/folders/120JIOTyeNX6nHaHPDqS3UgbaTWyJAE57 | Anyone-with-link writer permission verified September 28; permissions were not changed.
Prior complete Increment03 ZIP | Source baseline for this increment | https://drive.google.com/file/d/19b78ZKRec3FG_N1fGbDFpu2SwpYUUHWu/view | Cumulative overlay, not a full standalone app repository.
Original backlog XLSX | 95 original tasks and acceptance criteria | https://drive.google.com/file/d/15X3_uSbHztLL57IL_d3Xo9hc9zInJuyN/view | Original task rows retained in this workbook.
Original production report | Earlier findings and scope | https://drive.google.com/file/d/1QGQeKDZ_139Nw1DzXiEhfbggCVB301tz/view | September 27 assessment; not a current production attestation.
Increment04 destination | Produced code, register and verification | https://drive.google.com/drive/folders/14lsaqxYMJutws1GNQQYHZka0ZOZgjXNf | Uploaded artifacts do not constitute deployment.
Selected baseline dependencies | Config, HTTP, validation, collector signatures, Supabase client | sources.json | Exact Drive IDs and archive checksums included in the package.

## Original audit criteria
Original audit ¦ Acceptance criteria preserved
Verbatim task rows from the September 27 backlog. Original status is historical; use the current delivery register for Increment04 evidence.
ID | Priority | Release scope | Area | Task | Original status | Assigned owner | Owner role | Effort | Dependencies | Original acceptance criteria | Why it matters | Original evidence
M001 | P0 | Core | Source access | Restrict the public Drive working-copy folder and preserve an access-review record | Not started |  | Security lead + folder owner | S | None | Named access replaces anyone-writer; inherited/child permissions and link access are verified; preserve activity evidence and an incident decision without asserting outsider use. | Root permission metadata confirms anyone-with-link writer access; source and signing material share that folder. | Drive root metadata reviewed 2026-09-27; https://drive.google.com/drive/folders/120JIOTyeNX6nHaHPDqS3UgbaTWyJAE57; audit/platform_review.md PL-01
M002 | P0 | Core | Signing and secrets | Inventory exposed credentials and replace or revoke affected secrets using their actual provenance | Not started |  | Security + Android release owner | M | M001 | Identify owner, purpose, exposure window and actual upload/app-signing role; reset upload keys or revoke credentials as warranted; prove a trusted signed update path and remove exposed copies under retention policy. | Signing configuration and two keystores exist in the publicly editable working-copy upload; current Git index does not track them. | android/key.properties; android/mobi-upload.jks; android/app/upload-keystore.jks; audit/git_index_inventory.json; https://support.google.com/googleplay/android-developer/answer/9842756?hl=en Original source: https://drive.google.com/file/d/1eV0tMds3GICIBCp0yGnF-GDre8fAckk2/view?usp=drivesdk https://drive.google.com/file/d/1Hc8W34L5NqaydBHLhTJN9MXwuk4dwEtJ/view?usp=drivesdk
M003 | P0 | Core | Identity authority | Bind verified WhatsApp/phone identity to an immutable, unique Auth identity | Not started |  | Backend + security | L | M001 | Separate editable contact data from verified login authority; migrate duplicate aliases; verification cannot select or reassign another account; negative fixtures plus real Auth collision behavior pass. Phone-based BioPay discovery also resolves only the canonical verified recipient authority, never an editable contact alias. | Editable profile aliases and newest-created selection can misdirect OTP resolution; mocked helper reproduced wrong selection and a reassignment attempt. | supabase/functions/verify-login-otp/index.ts:80-229; supabase/migrations/20260614153000_rentals_vehicle_type_onboarding.sql:193-243; audit/validation_review.md IV-01; supabase/migrations/20260908090000_biopay_payment_discovery.sql:239-245 Original source: https://drive.google.com/file/d/1rLnSrgP58oGUWfhbZqV18wBkV-xUvuGO/view?usp=drivesdk https://drive.google.com/file/d/1rgP7K6iACtSIV9YJI6_7tmzawe63L1r6/view?usp=drivesdk https://drive.google.com/file/d/1VzfemejMhTryu0KVQFVpt8lxcSH57O4N/view?usp=drivesdk
M004 | P1 | Core | Authorization | Protect identity and privilege columns and audit effective table/RPC grants | Not started |  | Backend + security | M | M003 | Publish effective role/table/column/function matrix; default-deny sensitive updates and security-definer execution; ordinary sessions cannot mutate verified aliases, creation order, member ID or admin authority. Test fn_biopay_discover against attempted editable-phone impersonation. | Own-row policies do not by themselves protect sensitive column authority; accumulated migrations can preserve broad grants. | supabase/migrations/20260501080000_backend_security_payment_rls_hardening.sql; supabase/migrations/20260501110000_security_profile_chat_dashboard_hardening.sql; audit/backend_review.md B-02; supabase/migrations/20260908090000_biopay_payment_discovery.sql:239-245 Original source: https://drive.google.com/file/d/1iPUAzOiUANdBMpfbyHZgffrhTR3njUz1/view?usp=drivesdk https://drive.google.com/file/d/1h4svjoUNZVOu5_kZOWH3XMtGKfnOqP2l/view?usp=drivesdk https://drive.google.com/file/d/1rgP7K6iACtSIV9YJI6_7tmzawe63L1r6/view?usp=drivesdk
M005 | P1 | Core | Member identity | Reconcile duplicate member IDs and enforce atomic unique six-digit allocation | Not started |  | Backend + data migration owner | M | M003; M004 | Duplicate inventory reviewed; controlled remediation preserves account UUIDs and references; unique constraint plus concurrent allocation tests pass; ambiguous recipient lookup fails safely. | Server allocation lacks a uniqueness constraint and existing lookups can choose one ambiguous match. | supabase/migrations/20260324175000_comprehensive_rpcs.sql:40-72; audit/flutter_review.md FL-01; audit/backend_review.md Original source: https://drive.google.com/file/d/13yI6aGP0ZoPmYKSFL-PiftK-FD0VkBO-/view?usp=drivesdk
M006 | P1 | Core | Member identity | Display the authoritative member ID consistently across all client surfaces | Not started |  | Flutter + QA | M | M005 | One fixture displays one server-issued six-digit ID in profile, nearby, trip, chat and wallet; no fabricated fallback; wrong/missing/ambiguous recipient regression cases pass. | Driver cards hash UUIDs, Trips truncates them, and Profile uses different or fixed fallbacks. | lib/shared/widgets/driver_card.dart; lib/features/profile/presentation/profile_screen.dart; lib/features/bookings/presentation/bookings_screen.dart; audit/flutter_review.md FL-01, FL-08 Original source: https://drive.google.com/file/d/133jijD3OWgkiq8kvYppJsiGdn427lgiK/view?usp=drivesdk https://drive.google.com/file/d/18urTvEQkxOoO54RdPEqF3hG6P_FLgWYX/view?usp=drivesdk
M007 | P1 | Core | Account lifecycle | Implement ordinary sign-out with finally-safe local and native cleanup | Not started |  | Flutter + native platform owners | M | M003 | Offline exit clears local credentials, account state, drafts/listeners and camera/NFC/location activity; cleanup failures cannot restore access; account A data never appears after B signs in. | Only Exit Admin invokes account exit; failed cleanup can prevent sign-out and current helper can retain the prior authenticated session. | lib/app/router/screen_wrappers.dart:120-130; lib/core/auth/supabase_session_service.dart:61-81; audit/flutter_review.md FL-02 Original source: https://drive.google.com/file/d/1q4klsIHCcBSAx3BdaRdwzqNC3X2zD7jq/view?usp=drivesdk https://drive.google.com/file/d/1yXHyXe8vVhu5ITKzP5IYgndcRKLU0V5O/view?usp=drivesdk
M008 | P1 | Core | Push identity | Revoke FCM association before losing its owning session and atomically bind device ownership | Not started |  | Flutter + backend | M | M007 | Two-account device test receives only current-owner messages; captured identity is rechecked around token retrieval/upsert; anonymous registration rejected; stale-token expiry and revocation verified. | Current signed-out cleanup runs under an identity that cannot delete the prior own-row token; anonymous refresh also needs rejection. | lib/app/shell.dart; lib/features/notifications/data/push_notification_service.dart:343-418; audit/flutter_review.md FL-03 Original source: https://drive.google.com/file/d/1g_9q58Z-2302LqjJteF3pqrzqIRnUCUA/view?usp=drivesdk https://drive.google.com/file/d/1pMxjMX11Yc0j6Gmpp5TvuMC7eVce0itE/view?usp=drivesdk
M009 | P1 | Core | Admin security | Define and enforce admin idle, absolute lifetime and sensitive-action authentication | Not started |  | Security + backend + Flutter | M | M003; M007 | Retained timeout requirements are enforced server-side and reflected in UI; idle/background/resume/refresh/role-revocation tests pass; high-impact operations require the agreed admin purpose. | Advertised 15-minute timeout affects a fallback flag while an admin role can remain authoritative indefinitely in the client guard. | lib/core/auth/admin_session_guard.dart; lib/app/router/app_router.dart; audit/flutter_review.md FL-04; audit/backend_review.md Original source: https://drive.google.com/file/d/1X7sWfPgFxAKSm-EZLwKq7SmuvRQHnOlH/view?usp=drivesdk https://drive.google.com/file/d/10iUOdZWSzYH51vT01fjN0BBQsTULtV9D/view?usp=drivesdk
M010 | P1 | Core | Credential storage | Migrate native refresh-session persistence to supported OS-protected storage | Not started |  | Flutter + security | M | M007 | At-rest/backup inspection and migration, restart, sign-out, reinstall and revocation tests pass on Android/iOS; recovery behavior is documented; browser storage is addressed separately. | Supabase initialization uses default local storage; no custom protected native adapter is configured. | lib/app/bootstrap.dart:79-82; audit/flutter_review.md FL-10; https://pub.dev/packages/supabase_flutter Original source: https://drive.google.com/file/d/16rAbretfd1HwG3q_qLdo6WHrvbIB061u/view?usp=drivesdk https://drive.google.com/drive/folders/1VeEGNOl32YcDgwjU7FZhqwcj_7Vyqy6c
M011 | P1 | Core | Review access | Constrain the store-review identity to monitored synthetic data and rotate its access | Not started |  | Security + release + backend | M | M003; M009 | Review account has approved minimal access and no real-user financial/biometric records; rate cap, audit monitoring and rotation procedure work; live OTP-claim semantics remain enforced. | Fixed review OTP flow still creates an ordinary consumer identity and bypasses some send throttling/Integrity checks; no admin bypass was demonstrated. | supabase/functions/_shared/play-review-login.ts; supabase/functions/send-login-otp/index.ts; audit/backend_review.md B-11 Original source: https://drive.google.com/file/d/1GNs7SS0ZnkVMp96ZipCG6lOqW77dNTcK/view?usp=drivesdk https://drive.google.com/file/d/14OGjfqPCwD8YXGL1_8RJVacWZZLazQZ1/view?usp=drivesdk
M012 | P1 | Core | OTP production config | Reject OTP dry-run in production and redact all authentication secrets | Not started |  | Backend + DevOps | S | M002 | Deployment gate rejects WHATSAPP_CLOUD_DRY_RUN in production; sanitized config readback and log fixtures show no OTP/full phone; testing still uses explicitly isolated fixtures. | Dry-run logs complete phone/code and reports send success, creating an unsafe production configuration. | supabase/functions/_shared/whatsapp-cloud.ts:218-220; audit/privacy_review.md PRIV-09 Original source: https://drive.google.com/file/d/12qJwdf1UXnXqeY3d1I9ttnFYZhMZ77pT/view?usp=drivesdk
M013 | P2 | Core | Abuse prevention | Choose an explicit Play Integrity policy and bind/consume protected requests | Not started |  | Android + backend + security | M | M003; M091 | Document acceptable device/app verdicts and exceptions; replay/content-substitution fixtures fail where required; monitor-to-enforce decision uses measured false rejects and does not indiscriminately block users. | Classic token validation logs device verdicts without policy checks; nonce is not bound to request content or consumed once. | supabase/functions/_shared/play-integrity.ts:66-72,118-298; audit/backend_review.md B-10; https://developer.android.com/google/play/integrity/classic Original source: https://drive.google.com/file/d/1D17M-jpEvOSKaBtoBJFHNSl_V1u-p1zf/view?usp=drivesdk
M014 | P2 | Core | Web session security | Verify admin browser persistence, CSP and session revocation against an explicit threat model | Not started |  | Web + security | M | M009 | Approved persistence policy, effective headers and browser expiry/revoke/role-change tests recorded; cached pages and service workers expose no prior-account sensitive data. | Native secure storage does not address web token exposure, cached admin content or long-lived browser sessions. | audit/flutter_review.md FL-10; scripts/web/admin_service_worker.js; scripts/tests/admin_service_worker.test.mjs; audit/validation_review.md Node Pages/Admin scope Original source: https://drive.google.com/file/d/1AclcH-_QKjPYyyPzDbMD-36G3H2OV87A/view?usp=drivesdk https://drive.google.com/file/d/16ZESpb117vIxtZrIiAGQhMaJiPaz_oh3/view?usp=drivesdk
M015 | P0 | Paid transport | Booking authorization | Remove passenger authority to self-confirm or mark a booking paid | Not started |  | Backend + security | M | M004 | Direct PostgREST attempts to set confirmed/paid, paid_at, receipt, price, route or seat authority fail for passengers; only trusted transactional RPCs can make valid transitions. | Owner UPDATE grant and row policy permit mutation beyond legitimate held-booking fields. | supabase/migrations/20260608093000_public_transport_booking_foundation.sql:253,401-413; audit/backend_review.md B-01; audit/validation_review.md IV-03 Original source: https://drive.google.com/file/d/1PcLY4jkG2pCwPilr22NSbzjK9LsjgnEV/view?usp=drivesdk
M016 | P0 | SMS | Receipt integrity | Require strong payment evidence before automatic subscription activation | Not started |  | Backend + payments owner | L | M020; M026 | Non-payment, uncertain, missing-reference, wrong merchant/currency and ambiguous fixtures cannot credit; require classified payment plus stable provider reference and intended payer/invoice binding; quarantine for reviewed resolution. | Parser forwards negative/low-confidence messages; allocator can match only amount/time without payer/member/reference. | supabase/functions/_shared/momo-sms.ts:155-200; supabase/functions/momobio-sms-ingest/index.ts:52-73; supabase/migrations/20260906145000_subscription_receipt_integrity.sql:156-219; audit/validation_review.md IV-02 Original source: https://drive.google.com/file/d/1VLrjCisiaiRqSAoExNMKwOtQXGdWo2TW/view?usp=drivesdk https://drive.google.com/file/d/1ABtcrIk1N1ve9MSKEpHlyDgu4FLI8yKi/view?usp=drivesdk
M017 | P1 | Paid transport | Seat inventory | Make booking holds idempotent and durably expire/release seats | Not started |  | Backend + database QA | M | M015 | Bounded expiry job, cancellation and hold idempotency work; concurrent last-seat/expiry/confirmation tests conserve inventory and never produce negative or stranded seats. | Repeated holds decrement inventory; an expired status update is rolled back by a raised exception; no durable sweeper was found. | supabase/migrations/20260611170000_public_transport_rpc_column_qualification.sql:7-160; audit/backend_review.md B-04; audit/validation_review.md IV-05 Original source: https://drive.google.com/file/d/1FyZe9Prez95TVZQwyrYGKgBf7Fw0XAm3/view?usp=drivesdk
M018 | P1 | Paid transport | Payment receipts | Bind one provider receipt atomically to one intended booking and exact amount/currency | Not started |  | Backend + payments owner | M | M015; M020 | Duplicate reference on same booking is idempotent; reference reuse on another booking is rejected; amount/currency and issuer authority are checked under concurrent confirmation. | Receipt upsert conflict handling does not prevent a reused reference from confirming another booking. | supabase/migrations/20260611170000_public_transport_rpc_column_qualification.sql:163-204; audit/backend_review.md B-05 Original source: https://drive.google.com/file/d/1FyZe9Prez95TVZQwyrYGKgBf7Fw0XAm3/view?usp=drivesdk
M019 | P1 | SMS | Subscription periods | Serialize paid subscription renewals by profile and vehicle type | Not started |  | Backend + database QA | M | M016 | Deterministic two-session test with distinct receipts preserves both paid durations without overlap; duplicate invoice retry creates exactly one activation; expiry boundaries are explicit. | Distinct invoices lock distinct requests and can read the same maximum period end before insertion. | supabase/migrations/20260906145000_subscription_receipt_integrity.sql:298-390; audit/backend_review.md B-06; audit/validation_review.md IV-04 Original source: https://drive.google.com/file/d/1VLrjCisiaiRqSAoExNMKwOtQXGdWo2TW/view?usp=drivesdk
M020 | P1 | SMS | Merchant configuration | Make merchant identity, currency and receipt formats explicit validated configuration | Not started |  | Payments operations + backend | M | Approved merchant/operator inventory | Each enabled collector maps to approved merchant/account/operator/currency and parser fixtures; missing or wrong configuration blocks auto-credit with visible reason; no guessed merchant identifier. | A missing merchant code can become a fabricated default, weakening invoice matching and auditability. | supabase/migrations/20260906145000_subscription_receipt_integrity.sql; supabase/functions/_shared/momo-sms.ts; audit/backend_review.md B-03 Original source: https://drive.google.com/file/d/1VLrjCisiaiRqSAoExNMKwOtQXGdWo2TW/view?usp=drivesdk https://drive.google.com/file/d/1jy2qeudD4ypMt6bl6SltIQwb3KGpece7/view?usp=drivesdk
M021 | P1 | Core | Financial retries | Use durable account-scoped wallet operation IDs and reconcile uncertain outcomes | Not started |  | Flutter + backend | M | M003; M006; M054 | Response loss, process restart, account switch and failed storage retain correct operation identity or block unsafe retry; committed operation is discoverable; duplicate retry cannot charge twice. | Existing keys omit owner identity, expose raw note in preference keys and ignore persistence failure; UI promises stronger retry safety. | lib/features/profile/presentation/wallet_screen.dart:782-828; audit/flutter_review.md FL-13 Original source: https://drive.google.com/file/d/1LlppucPRV_7Kpp3kh07UDhWL39XAPyVI/view?usp=drivesdk
M022 | P1 | Paid transport | Financial boundaries | Specify and test refunds, cancellation, monetary precision and time boundaries | Not started |  | Product + payments + backend | M | M017; M018; M019; M024 | Approved rules and tests cover invalid/zero/negative/large amounts, currency, timezone/day rollover, duplicate refund, cancellation after payment and reconciliation; no new settlement engine is introduced. | Release needs a complete operating contract for already implemented paid booking/subscription/reward paths. | audit/backend_review.md recommended tasks; docs/product/public_transport_tracking_booking_scope_2026-06-08.md; audit/privacy_review.md section 5 Original source: https://drive.google.com/file/d/11YYuUj98ZIEPP48aikNWMtWIGKOcwybM/view?usp=drivesdk
M023 | P1 | SMS | Financial reconciliation | Reconcile collector receipts, ingestion outcomes and activated invoices with operator records | Not started |  | Payments operations + backend | M | M016; M028; M034 | Daily exception report reconciles eligible receipts, duplicate/rejected/quarantined cases and credits to trusted operator evidence; lost receipt/manual resolution is audited without permissive auto-match. | A missed SMS broadcast, device failure or ambiguous match can otherwise silently deny or misapply a paid entitlement. | apps/momobio_sms_bridge/app/src/main/java/com/momobio/app/SmsReceiver.kt; audit/platform_review.md PL-06; audit/backend_review.md B-03 Original source: https://drive.google.com/file/d/14Xk8YpNg33EJncxUz4ZFh08gXr_v_0gT/view?usp=drivesdk
M024 | P1 | Paid transport | Operating authority | Obtain a feature-specific payments/transport classification and responsibility decision | Not started |  | Product lead + qualified Rwanda counsel | M | Feature and funds-flow draft; coordinate with refund design | Current primary rules and actual funds flow support a written decision for each enabled paid feature; provider/agency contracts, responsible entity and customer promises are recorded; unresolved features stay disabled. | Actual funds flow, merchant ownership, agency agreements, refunds and reward terms were not supplied; no licence conclusion was possible. | audit/privacy_review.md section 5; docs/product/public_transport_tracking_booking_scope_2026-06-08.md Original source: https://drive.google.com/file/d/11YYuUj98ZIEPP48aikNWMtWIGKOcwybM/view?usp=drivesdk
M025 | P1 | SMS | Collector signing | Replace debug-keystore operational packaging with a managed production signing/update path | Not started |  | Android release + fleet operations | M | M002 | Distribution artifact uses approved managed signing; signature/version verified; enrolled request-signing identity and pending receipts survive supported updates or a documented controlled migration. | device_uat.sh signs release output with the standard debug keystore; enrolled keys and queued receipts need a safe upgrade. | apps/momobio_sms_bridge/scripts/device_uat.sh:69-76; apps/momobio_sms_bridge/app/build.gradle.kts; audit/platform_review.md PL-04 Original source: https://drive.google.com/file/d/1MLWnXsRSeoudgNb9hkGCqMeXVXFZumKJ/view?usp=drivesdk https://drive.google.com/file/d/13unWV3K7o-vQdJnFfdpVzk5xZckDNc47/view?usp=drivesdk
M026 | P1 | SMS | Collection minimization | Filter eligible receipt data on-device and present a clear upload/AI-processing notice | Not started |  | Android + privacy + payments | M | M020 | Unrelated sender/content fixtures never enter queue or network; notice explains purpose, recipients, retention and support before access; changed formats route to minimal controlled review without auto-credit. | Receiver currently queues and uploads all new SMS before server filtering; dedicated private distribution does not justify unrelated collection. | apps/momobio_sms_bridge/app/src/main/java/com/momobio/app/SmsReceiver.kt; SmsReceiptDecoder.kt; UploadClient.kt; audit/platform_review.md PL-05; audit/privacy_review.md PRIV-03 Original source: https://drive.google.com/file/d/14Xk8YpNg33EJncxUz4ZFh08gXr_v_0gT/view?usp=drivesdk
M027 | P1 | SMS | Distribution policy | Document private fleet distribution and obtain SMS/FGS approval if using public Play | Not started |  | Android release + compliance | S | M025; M026 | Actual channel and authorized device population recorded; applicable Play exception/permission and foreground-service review evidence supplied before public distribution; private-policy claims match access controls. | Bridge is documented in-house; public Play distribution would introduce restricted SMS permissions and declaration requirements. | apps/momobio_sms_bridge/README.md; app/src/main/AndroidManifest.xml; https://support.google.com/googleplay/android-developer/answer/10208820; audit/platform_review.md PL-05 Original source: https://drive.google.com/file/d/1THqrvAz2dVb6sLK6RTD8BeIcaQEcY1pG/view?usp=drivesdk https://drive.google.com/file/d/1qFn0W9M6GEXpT3ZhuSm-AyB38Qxnkqah/view?usp=drivesdk
M028 | P1 | SMS | Durable queue | Use a transactional bounded receipt queue with corruption quarantine and retained acknowledgement state | Not started |  | Android + backend | M | M026 | Crash/restart/disk-full/corrupt-row and partial-ack tests preserve eligible records; bounded batches/age/bytes and dedupe retention verified; capacity alerts precede exhaustion; migration is lossless. | Whole-queue preference JSON and unbounded hash history are fragile; malformed rows can disappear during a later save. | apps/momobio_sms_bridge/app/src/main/java/com/momobio/app/SmsQueue.kt; audit/platform_review.md PL-06; audit/privacy_review.md PRIV-08 Original source: https://drive.google.com/file/d/1-yEWiItXERM_jmBtgePmT13WZUNUb0g-/view?usp=drivesdk
M029 | P1 | SMS | Retry coordination | Centralize collector work leasing, backoff and response handling | Not started |  | Android + backend | M | M028 | One shared batch lease prevents concurrent uploads; bounded jitter/backoff handles 429/503/network loss; each attempt retains fresh nonce/signature; partial-success retries cannot duplicate credits. | UI, service and WorkManager retries can compete; per-instance flags do not coordinate work or honor Retry-After. | apps/momobio_sms_bridge/app/src/main/java/com/momobio/app/BridgeSupervisor.kt; BridgeForegroundService.kt; BridgeSyncWorker.kt; UploadClient.kt; audit/platform_review.md PL-07 Original source: https://drive.google.com/file/d/1TCLP0gLC0lyCHAF9vvir7CxcwCzRi3Ob/view?usp=drivesdk
M030 | P1 | SMS | Collector lifecycle | Verify boot, force-stop, OEM battery and Android job-quota behavior on managed devices | Not started |  | Android QA + fleet operations | M | M025; M028; M029 | Real fleet models pass reboot/update/offline/process-death/Doze/restricted-permission cases; force-stop and OEM limitations are visible with reconciliation instructions; no fictitious always-on guarantee. | WorkManager and foreground services do not guarantee timely capture under every device state; receipt history is not reread. | apps/momobio_sms_bridge/app/src/main/java/com/momobio/app/BridgeBootReceiver.kt; audit/platform_review.md device matrix; https://developer.android.com/about/versions/16/behavior-changes-all Original source: https://drive.google.com/file/d/1SOpL0EkATxERvbJo2lw_eXGk2mIefSgp/view?usp=drivesdk
M031 | P1 | SMS | Legacy ingest authority | Inventory deployed legacy SMS callers and retire or harden shared-secret ingest aliases | Not started |  | Backend + security + operations | M | M016; M029 | Deployed endpoint/caller inventory complete; unused routes return a controlled retirement response; retained routes use registered collector authority, replay/body/rate bounds and monitored migration. | parse-sms and reconcile-momo-sms preserve older global-secret paths without per-collector replay/revocation controls. | supabase/functions/parse-sms/index.ts:22-42; supabase/functions/reconcile-momo-sms/index.ts:22-42; audit/backend_review.md B-08 Original source: https://drive.google.com/file/d/1snmFTu4PpKv7cY09FBswSVfAuSWoy_-f/view?usp=drivesdk https://drive.google.com/file/d/1Q_gKdjfTVAO5JjxLkfYPMHPt1hfo1vtr/view?usp=drivesdk
M032 | P1 | SMS | Backend intake | Persist authenticated receipt admission before asynchronous parsing and allocation | Not started |  | Backend + SRE | M | M016; M028; M029 | Durable per-message intake/outcome identity; bounded worker with leases/retry/dead-letter handling; crash after first item or lost final acknowledgement yields one financial effect and reproducible status. | Sequential AI/SQL processing can partially commit a batch then return a transient failure; repeat parsing increases cost and uncertainty. | supabase/functions/momobio-sms-ingest/index.ts; audit/backend_review.md collector strengths and partial-batch risk Original source: https://drive.google.com/file/d/1ABtcrIk1N1ve9MSKEpHlyDgu4FLI8yKi/view?usp=drivesdk
M033 | P1 | SMS | Fleet security | Establish dedicated institutional devices/SIMs, enrollment, revocation and replacement procedures | Not started |  | Fleet operations + security | M | M025; M026; M027 | Named custodians and inventory; dedicated SIM restriction, screen/device protection, enrollment approval, lost-device revocation, replacement/export policy and staff training rehearsed with no personal-SMS collection. | Financial SMS and enrolled collector authority need controlled hardware ownership and incident handling. | apps/momobio_sms_bridge/README.md; audit/privacy_review.md PR-T06; audit/platform_review.md PL-04 to PL-07 Original source: https://drive.google.com/file/d/1THqrvAz2dVb6sLK6RTD8BeIcaQEcY1pG/view?usp=drivesdk https://drive.google.com/file/d/1qFn0W9M6GEXpT3ZhuSm-AyB38Qxnkqah/view?usp=drivesdk
M034 | P1 | SMS | Collector health | Expose truthful enrolled/configured/connected/acknowledged state and backlog age | Not started |  | Android + operations | M | M028; M029; M032 | Missing config, expired/revoked key, denied permission and server outage have distinct states; last successful server acknowledgement and oldest eligible receipt are visible and alertable. | Empty queues can report success before configuration is checked and UI may show Running without a usable enrolled backend. | apps/momobio_sms_bridge/app/src/main/java/com/momobio/app/MainActivity.kt; UploadClient.kt; audit/platform_review.md PL-07 Original source: https://drive.google.com/file/d/1VaIxl4s-bYjAbwW0zj8QP29_x09Ag4sb/view?usp=drivesdk
M035 | P1 | Face | Face release policy | Keep Face-USSD disabled until exact current scope is accepted and health surfaces agree | Not started |  | Product + backend + release | M | M036; M037; M038; M039; M040; M067; M068 | One versioned decision binds approved no-liveness recipient lookup, model/policy/index and health semantics; enablement requires acceptance; manual/QR alternatives remain usable; dialer launch never means settlement. | September policy is intentionally disabled/unthresholded; older admin status still hardcodes not-ready and historical AWS requirements are superseded. | docs/product/face-ussd-20260920/APPROVAL.md; supabase/migrations/20260920150000_biopay_face_shortcut.sql; audit/validation_review.md section 2 Original source: https://drive.google.com/file/d/1xop9aCYCPDg70qLFnM9fyHhWzGvx-Vc1/view?usp=drivesdk https://drive.google.com/file/d/1Ql7MVmCXqbgiB8DwU11kDXAjNmRtYF-k/view?usp=drivesdk
M036 | P1 | Face | Inference artifact | Build and verify the exact Linux inference image, models and private service bindings | Not started |  | Platform + ML engineer | M | M077; M082 | Immutable image/model digests and licences recorded; real health/embed tests pass in Linux container; Worker authentication, private binding, index dimension/version and environment isolation verified. | Historical implementation report did not complete the Docker image or production model deployment. | services/face-inference/Dockerfile; cloudflare/face-service/wrangler.jsonc; docs/product/face-ussd-20260920/IMPLEMENTATION_REPORT.md; audit/operations_review.md OPS-04 Original source: https://drive.google.com/file/d/13toaULZ0qSRF3mcOySrbey9WeHRMSidj/view?usp=drivesdk https://drive.google.com/file/d/10XfUXtvPdRtBHiWA9yhRro_v6glk8XvJ/view?usp=drivesdk
M037 | P1 | Face | Deployment contracts | Rehearse latest face migrations, PostgREST/Edge, Vault and scheduled maintenance together | Not started |  | Backend + platform + database QA | M | M036; M078 | Full-schema rehearsal verifies exact RPC argument/privilege/session contract; deployment history, secrets presence and scheduled execution read back; activation and deletion converge after provider interruption. | Source health checks and cleanup implementations do not establish target schema parity or an executing maintenance schedule. | supabase/migrations/20260920150000_biopay_face_shortcut.sql; supabase/functions/biopay-face-provider/index.ts; docs/operations/face-ussd-runbook.md; audit/operations_review.md O05,O08 Original source: https://drive.google.com/file/d/1xop9aCYCPDg70qLFnM9fyHhWzGvx-Vc1/view?usp=drivesdk https://drive.google.com/file/d/1rDo-iJSUPd_QhiakftQOghMtlmsk2P6S/view?usp=drivesdk
M038 | P1 | Face | Matching acceptance | Calibrate and independently accept matching thresholds and cross-owner margins | Not started |  | ML QA + product + privacy | L | M036; M067; M068 | Pre-agreed error/latency criteria; held-out consented cohort covering lighting, skin tones, age and devices; report denominators, gallery size, uncertainty and thresholds/model hash; ambiguous matches fail safely. | No consented held-out cohort or gallery-scale false-match/false-nonmatch evidence was established for the active SFace path. | services/face-inference/inference.py; cloudflare/face-service/src/handler.ts; docs/product/face-ussd-20260920/IMPLEMENTATION_REPORT.md; audit/operations_review.md OPS-04 Original source: https://drive.google.com/file/d/13toaULZ0qSRF3mcOySrbey9WeHRMSidj/view?usp=drivesdk https://drive.google.com/file/d/1ZMe2Z6-28lqVhf4GD24uS02hOaPsgsYZ/view?usp=drivesdk
M039 | P1 | Face | Biometric deletion | Exercise pause/remove/replacement and delayed-upsert cleanup end to end | Not started |  | Backend QA + privacy + operations | M | M036; M037 | Immediate discovery exclusion plus eventual verified vector absence; cancellation, replacement, delayed insert, provider outage and restored-backup cases pass; cleanup owner/SLA and tombstone retention approved. | SQL exclusion and retryable vector cleanup exist but observed external absence and production cleanup SLA are not proven. | docs/operations/face-ussd-runbook.md; supabase/functions/biopay-face-maintenance; audit/privacy_review.md PR-T10; audit/validation_review.md section 2 Original source: https://drive.google.com/drive/folders/1Yd3ushY1JBVNcm_zloDSgVpLwQt-k867 https://drive.google.com/file/d/1vZVjzSVzBGDPvEDyH5wTO996VJbSCDGt/view?usp=drivesdk
M040 | P1 | Face | Camera-to-USSD acceptance | Run physical-device face capture through one correct operator dialer handoff | Not started |  | Mobile QA + operator liaison | M | M036; M037; M038; M046; M051 | Selected receiving method/number resolves correctly; changed/paused payee, timeout, interruption, cancellation, restart, dual-SIM and denial cases pass; one amount-free Android handoff; iOS fallback is clear. | Lifecycle and at-most-once safeguards are strong in source, but current build/operator/dual-SIM evidence was not executed. | lib/features/biopay/presentation/biopay_face_scan_screen.dart; lib/features/biopay/domain/face_shortcut.dart; android/app/src/main/kotlin; audit/flutter_review.md strengths; audit/platform_review.md Original source: https://drive.google.com/file/d/1VQx1_L_ad_B0ir4GoXgkwo9Em7fVeaMh/view?usp=drivesdk https://drive.google.com/file/d/1FpuSdHRpxtU6abvwywD3Q0WKOZWat9ma/view?usp=drivesdk
M041 | P1 | Face | Launch capacity | Measure cold/warm latency, burst admission and regional network performance at the launch workload | Not started |  | Performance + platform + ML | M | M036; M038 | Approved workload and p95/error budget met from target Rwandan networks; report busy/cold-start/index latency/memory/CPU; bounded capacity and safe retry decisions use results rather than autoscaling assumptions. | Single serialized container and repeated index compatibility calls impose an unmeasured capacity limit. | cloudflare/face-service/wrangler.jsonc:9; src/handler.ts:90-165; services/face-inference/inference.py:32-88; audit/operations_review.md OPS-05 Original source: https://drive.google.com/file/d/10XfUXtvPdRtBHiWA9yhRro_v6glk8XvJ/view?usp=drivesdk https://drive.google.com/file/d/140d2FVWo8zH96uUG9K55Svsd5twTSLzR/view?usp=drivesdk
M042 | P2 | Face | Inference serving | Use bounded production HTTP serving with graceful drain and failure limits | Not started |  | Backend + platform | M | M036; M041 | Saturation, slow/truncated/oversized body, concurrent request, termination during inference and restart tests pass; no raw payload logs or arbitrary URL fetch; concurrency and deadlines remain bounded. | ThreadingHTTPServer lacks a bounded serving pool and graceful process drain; private binding reduces exposure but does not prove robust serving. | services/face-inference/server.py:1,35; audit/operations_review.md OPS-09; https://docs.python.org/3.12/library/http.server.html Original source: https://drive.google.com/file/d/1UjDIz7n8Uk4OhFXYNLmB3vShd_P1ziTY/view?usp=drivesdk
M043 | P1 | Face | Face state consistency | Test cross-system enrollment/lookup races and fail-closed identity transitions | Not started |  | Backend + Flutter QA | M | M037; M039; M055 | Concurrent enrollment/replacement, account switch, consent withdrawal, route change, expired ticket, model mismatch and ambiguous result cannot produce a stale payee handoff; retries preserve at-most-once semantics. | Vector availability, SQL consent/owner/method state and client ticket state must agree despite asynchronous work. | lib/features/biopay/domain/face_shortcut.dart; supabase/migrations/20260920150000_biopay_face_shortcut.sql; cloudflare/face-service/src/handler.ts; audit/flutter_review.md Original source: https://drive.google.com/file/d/1xop9aCYCPDg70qLFnM9fyHhWzGvx-Vc1/view?usp=drivesdk https://drive.google.com/file/d/1FpuSdHRpxtU6abvwywD3Q0WKOZWat9ma/view?usp=drivesdk
M044 | P1 | Core | Android release | Target API 36 and verify Android 16 behavior for the consumer release | Not started |  | Android + Flutter + QA | M | M074; M077 | Release manifest confirms target36; edge-to-edge, predictive back, large-screen layouts, foreground services and permissions pass; actual Play preflight/extension status recorded separately from existing-app availability. | Main app compiles with 36 but targets 35; current Play new/update submission requirement is 36 from 2026-08-31, absent a verified extension. | android/app/build.gradle.kts; https://support.google.com/googleplay/android-developer/answer/11926878?hl=en; https://developer.android.com/about/versions/16/behavior-changes-16; audit/platform_review.md PL-02 Original source: https://drive.google.com/file/d/1v5ftCzLKueY28L_0UpgcByPB0Hc4qHF5/view?usp=drivesdk
M045 | P1 | Core | Android native libraries | Verify every shipped native library and release package on 16 KB pages | Not started |  | Android release + QA | M | M044; M081 | Inspect exact AAB/APKs and ELF/RELRO alignment, run zip alignment checks, install and exercise native/camera paths on 16 KB device/emulator; retain artifact evidence before 2027-02-01 update enforcement. | Modern AGP supports packaging but does not prove all Flutter/plugin prebuilts and ELF segments comply. The current Play requirement concerns API35+ apps on 64-bit devices. | android/settings.gradle.kts; android/app/build.gradle.kts; https://developer.android.com/guide/practices/page-sizes; audit/platform_review.md PL-09 Original source: https://drive.google.com/file/d/1v5ftCzLKueY28L_0UpgcByPB0Hc4qHF5/view?usp=drivesdk https://drive.google.com/file/d/1Cr3nlB2FWbztO4CXBBZMibfRduyk2Rfa/view?usp=drivesdk
M046 | P1 | Core | iOS release | Produce a signed Xcode 26+ archive and verify production entitlements/device behavior | Not started |  | iOS release + QA | M | M002; M077; M081 | Xcode/iOS SDK versions asserted; signed archive entitlements/provisioning verified; TestFlight install, APNs, camera/location/NFC and recovery pass on supported iPhones; no native macOS product is implied. | Current iOS check is --no-codesign; a build on a macOS host is not proof of signing, APNs, NFC or TestFlight operation. | scripts/ci/verify_ios_release.sh:51; ios/Runner/Info.plist; ios/Runner/Runner.entitlements; https://developer.apple.com/news/upcoming-requirements/; audit/platform_review.md PL-03 Original source: https://drive.google.com/file/d/1A2RP5xT5ZyUTrF_MafKUGssYZ_4pWp8k/view?usp=drivesdk https://drive.google.com/file/d/1BVpHj8Sp2PkZtlB_oR1YIVBzyihEFZRJ/view?usp=drivesdk
M047 | P1 | Core | NFC lifecycle | Enforce NFC advertisement expiry and owner lifecycle in the native APDU service | Not started |  | Android + Flutter | M | M007; M055 | Expired, signed-out, reset, changed-owner and restarted states cannot serve stale payload; exact APDU validation tested; explicit stop clears persistent material and UI reflects current state. | Persistent enabled/raw USSD payload can survive navigation or process restart; native read does not enforce expiry. | android/app/src/main/kotlin/rw/mobi/app/BioPayHostApduService.kt; MainActivity.kt; lib/features/biopay/presentation/biopay_nfc_screen.dart:51-62; audit/platform_review.md PL-08 Original source: https://drive.google.com/file/d/1E9pNYeMyNT7Wn5T7DP805IDmicfiFVEc/view?usp=drivesdk https://drive.google.com/file/d/13xDP1FXYO1bq-kP2l81oWO6ytezyfSTZ/view?usp=drivesdk
M048 | P1 | Core | Verified links | Verify Android App Links and iOS Universal Links against actual signed application identities | Not started |  | Mobile + web release QA | S | M002; M044; M046 | Production association files match package/bundle and current signing identities; payment/auth/admin link open, malformed link, browser fallback and reinstall cases pass without open redirects or account confusion. | Source associations and deep-link routes do not establish deployed domain verification or safe behavior in every installation state. | android/app/src/main/AndroidManifest.xml; ios/Runner/Runner.entitlements; landing/.well-known; https://developer.android.com/training/app-links/verify-applinks; audit/platform_review.md Original source: https://drive.google.com/file/d/1CshVCQSVniVLcrD_P0He9olWV0jRsK5f/view?usp=drivesdk https://drive.google.com/file/d/1BVpHj8Sp2PkZtlB_oR1YIVBzyihEFZRJ/view?usp=drivesdk
M049 | P1 | Core | Permissions and FGS | Align minimum permissions, background location and foreground-service declarations with visible product use | Not started |  | Android/iOS + privacy + release | M | M056; M065 | Permission-denied/revoked/background states behave safely; background location disclosure/video and applicable FGS purpose declarations accepted for actual release; no unused permissions or misleading always-on promise. | Main app requests background location and native features that require accurate disclosures and real device/state acceptance. | android/app/src/main/AndroidManifest.xml; ios/Runner/Info.plist; https://support.google.com/googleplay/android-developer/answer/9799150?hl=en; https://developer.android.com/develop/background-work/services/fgs/service-types; audit/platform_review.md PL-10 Original source: https://drive.google.com/file/d/1CshVCQSVniVLcrD_P0He9olWV0jRsK5f/view?usp=drivesdk https://drive.google.com/file/d/171_14QerVA_QQJxoY7pX9do6v_YMrT5c/view?usp=drivesdk
M050 | P1 | Core | SDK privacy | Audit bundled SDK data collection, required-reason APIs and archive privacy manifests | Not started |  | iOS/Android + privacy | M | M046; M065; M068 | Final archive privacy report and Android SDK inventory map actual collection to notices/store answers; necessary manifests/reasons present; analytics/ads dependencies and consent choices are justified by measured configuration. | No first-party manifest was found; Firebase/analytics/conversion SDK footprint requires actual archive and behavior review, not an assumption of tracking. | ios/Podfile.lock; ios/Runner; pubspec.lock; audit/platform_review.md PL-10; https://developer.apple.com/documentation/bundleresources/privacy-manifest-files Original source: https://drive.google.com/file/d/1Zkr32UrCgElDUhIuBrQVciYfKFsxCaZp/view?usp=drivesdk https://drive.google.com/file/d/11FVzDpJjUtz-PxJtvaPmIsqcYDCZq3WC/view?usp=drivesdk
M051 | P1 | Core | Operator continuity | Validate USSD/SMS on current Rwanda operators, SIM options and 4G/VoLTE devices | Not started |  | Operator liaison + mobile QA | M | M044; M046 | Approved handset/SIM/operator matrix covers dual-SIM, permission defaults, low coverage and 4G/VoLTE; track 2027-06-30 3G transition guidance without claiming USSD disappears; collector hardware choice is evidence-based. | Dialer and collector behavior is operator/device dependent; announced 3G sunset changes procurement and regression needs. | audit/platform_review.md device matrix; audit/privacy_review.md section 6; https://www.minict.gov.rw/news-detail/rwanda-to-switch-off-3g-networks-on-30-june-2027
M052 | P1 | Core | Store readiness | Reconcile store content, version identity, age-rating questions and reviewer instructions | Not started |  | Release + product + privacy | M | M011; M044; M046; M050; M065 | Current feature scope, screenshots, support/privacy/deletion URLs, permissions and age-rating answers agree with signed artifact; exact version/build and review access verified; draft/internal submission reviewed before publication. | Store text omits current features and iOS camera copy still names retired AWS; exact submitted artifact/version evidence is required. | ios/Runner/Info.plist; android/fastlane/metadata; docs/release; audit/platform_review.md PL-10; https://developer.apple.com/news/upcoming-requirements/ Original source: https://drive.google.com/drive/folders/1zahDeIbIAOW55lWawkAqajb_BhrPLZsg https://drive.google.com/file/d/171_14QerVA_QQJxoY7pX9do6v_YMrT5c/view?usp=drivesdk
M053 | P1 | Core | Startup resilience | Bound minimum bootstrap and defer optional Firebase/config/push work | Not started |  | Flutter | M | M012 | Airplane mode, slow DNS, captive portal and Firebase outage produce usable cached/retry states; mandatory configuration still fails closed; cold/warm release launch measurements meet agreed budget. | Optional initialization precedes mounting the app and some awaits have no deadline; failure can strand the launch screen. | lib/app/bootstrap.dart:39-160; lib/core/firebase/firebase_bootstrap_service.dart; firebase_remote_config_service.dart; audit/flutter_review.md FL-05 Original source: https://drive.google.com/file/d/1cmH3dI_QSwTvgj-22nU3q1Nb26915hjh/view?usp=drivesdk https://drive.google.com/file/d/16rAbretfd1HwG3q_qLdo6WHrvbIB061u/view?usp=drivesdk
M054 | P1 | Core | Request outcomes | Standardize request deadlines and distinguish unknown mutation outcomes from failure | Not started |  | Flutter + backend | M | M091; shared operation-outcome contract | Read timeouts show recoverable unavailable states; writes retain operation identity and query status after response loss; no false payment-success label or blind duplicated mutation. | Payment-discovery/admin calls lack explicit bounded UI recovery; timing out a future does not cancel a committed write. | lib/features/biopay/data/payment_discovery_service.dart:41-107; lib/features/bookings/data/trip_service.dart:138-145; audit/flutter_review.md FL-06 Original source: https://drive.google.com/file/d/1VUan_d6DaBvOdyaJaPwIUhYmYIVpNgfH/view?usp=drivesdk https://drive.google.com/file/d/18TwBSLp6s-TqZ8Ny_zPOREtE7Ql13kn-/view?usp=drivesdk
M055 | P1 | Core | Account-bound async work | Apply account and generation checks across Profile, shell, bookings and pending operations | Not started |  | Flutter | M | M007 | Delay A responses until after B signs in; no A profile/role/data changes B UI; rapid mode/search changes discard stale results and disposed work cannot restore listeners. | Older responses can overwrite current user/mode state after asynchronous work; stronger notification/face patterns already exist. | lib/features/bookings/presentation/bookings_screen.dart:67-132; lib/features/profile/presentation/profile_screen.dart:77-114; lib/app/shell.dart:68-96; audit/flutter_review.md FL-07 Original source: https://drive.google.com/file/d/133jijD3OWgkiq8kvYppJsiGdn427lgiK/view?usp=drivesdk https://drive.google.com/file/d/18urTvEQkxOoO54RdPEqF3hG6P_FLgWYX/view?usp=drivesdk
M056 | P1 | Core | Location authority | Bind driver sharing to its account and enforce server freshness, radius and result caps | Not started |  | Flutter + backend + privacy | M | M007; M055 | Concurrent start/stop/account changes cannot resurrect sharing; stale presence excluded on all surfaces; bounded radius/limit and coordinate precision follow purpose; denied/revoked permission marks unavailable/offline. | Client start/stop races can install obsolete subscriptions; discovery trusts online flags without a server TTL and exposes broad precise-location results. | lib/features/nearby/data/driver_location_sharing_service.dart; supabase/migrations/20260915003031_harden_driver_discovery_identity.sql:5-102; audit/flutter_review.md FL-07; audit/backend_review.md B-07 Original source: https://drive.google.com/file/d/13WznvHZhWTofuAfvMnxlKTPdDtwfs6AX/view?usp=drivesdk https://drive.google.com/file/d/1YxrFAODfP5TOTqAo9h72e7UZh8p2uEt5/view?usp=drivesdk
M057 | P1 | Face | Truthful status | Represent unknown/unavailable face state distinctly from not enrolled | Not started |  | Flutter | S | M055 | Existing enrollment is never displayed as absent solely from service failure; loading, unavailable and approved cached state are distinct; retry and pause/remove recovery remain usable. | Profile replaces a failed face-status request with not_started, misleading enrolled users during outages. | lib/features/profile/presentation/profile_screen.dart:89-108,371-374,547-557; audit/flutter_review.md FL-08 Original source: https://drive.google.com/file/d/18urTvEQkxOoO54RdPEqF3hG6P_FLgWYX/view?usp=drivesdk
M058 | P1 | Core | Launch localization | Complete and review critical journeys in each promised launch language | Not started |  | Flutter + localization + product | M | M065 | Supported language promise documented; login, money, consent, permission, deletion, moderation, support and error journeys translated and fluent-reviewed; Kinyarwanda/French formatting and text expansion accepted where promised. | Three translation catalogs exist but authentication, chat, home, Profile and admin contain hardcoded English. | lib/l10n/app_en.arb; app_rw.arb; app_fr.arb; audit/flutter_review.md FL-11 Original source: https://drive.google.com/file/d/1mjt5bSDzInV-jUfGUJohw56KAzStbtix/view?usp=drivesdk
M059 | P2 | Core | Secondary localization | Finish secondary/admin copy and locale-aware dates, pluralization and currency | Not started |  | Flutter + localization | M | M058 | Inventory of remaining hardcoded user-facing copy closed or explicitly deferred; each supported locale has reviewed plural/date/currency behavior and screenshots without truncation. | Partial localization creates uneven experience beyond the initial critical flows. | lib/features/admin; lib/features/profile; lib/features/chat; audit/flutter_review.md FL-11 Original source: https://drive.google.com/drive/folders/15N84L16_NCXcIFP2MilU6QMZYOKFGKzW https://drive.google.com/drive/folders/1AP0sh5lM_wR9WyxxdJKAUc9m0djWf3Fs
M060 | P1 | Core | Accessibility | Run existing accessibility coverage and physical assistive-technology journey acceptance | Not started |  | QA + design + Flutter | M | M053; M058; M076 | TalkBack/VoiceOver, keyboard, 200% text, contrast/touch targets, focus, error announcements and reduced motion pass across accepted journeys and screen sizes; intended automatic handoff is clearly announced. | Meaningful semantics/scale/reduced-motion tests exist but no current screen-reader or device result was produced by this audit. | design.md; test accessibility/semantics suites; audit/flutter_review.md Accessibility section; https://docs.flutter.dev/ui/accessibility Original source: https://drive.google.com/file/d/1MDlUp2tylgWDZ1AfN4ssXDOKSvLkdN5-/view?usp=drivesdk
M061 | P2 | Core | Chat reliability | Add stable client-message IDs, uncertain-send reconciliation and cursor history | Not started |  | Flutter + backend | M | M007; M054 | Lost acknowledgement/retry and restart yield one message; draft remains owner-scoped; reconnect recovery works; cursor pagination preserves ordering for conversations over 100 messages when full history is promised. | Timeout retries lack a message identity; history refresh is limited to the latest window. | lib/features/chat/data/chat_service.dart:193-221,306-347; lib/features/chat/presentation/chat_screen.dart; audit/flutter_review.md FL-12 Original source: https://drive.google.com/file/d/12n5FHLFgRu9NPOsRAb9HFFgWAIIaol3b/view?usp=drivesdk https://drive.google.com/file/d/1BrgbaLACv8-s6Hop1vdwBt8E9gvQ61E_/view?usp=drivesdk
M062 | P1 | Core | Operational switches | Implement exercised server feature controls and truthful client maintenance messaging | Not started |  | Backend + Flutter + SRE | M | M015; M016; approved enabled-feature scope | Already-running clients respond to scoped suspension; server rejects affected writes; manual/QR/read-only recovery remains as approved; expiry/rollback and operator ownership are tested. | Remote Config maintenance flag is declared but unused; a client flag alone cannot stop unsafe backend operations. | lib/core/firebase/firebase_remote_config_service.dart:51-58,94-97; audit/flutter_review.md FL-14; docs/operations/face-ussd-runbook.md Original source: https://drive.google.com/file/d/1ktk89YYNARL-mxcs3U1Z1AN7_BBX3CZS/view?usp=drivesdk https://drive.google.com/file/d/1vZVjzSVzBGDPvEDyH5wTO996VJbSCDGt/view?usp=drivesdk
M063 | P2 | Core | Maintainability | Refactor touched oversized screens and overloaded models into typed application/repository boundaries | Not started |  | Flutter technical lead | L | M006; M007; M054 | Typed person/trip/member-ID and RPC outcome contracts replace lossy seams; changed workflows have focused tests; preserve Riverpod/GoRouter and avoid an unrelated framework rewrite. | Mixed Trip/person fields and UI-owned persistence/network orchestration contribute to identity loss and inconsistent retry behavior. | packages/shared-types/lib/models/trip.dart:18-130; lib/features/profile/presentation/wallet_screen.dart; audit/flutter_review.md FL-15; https://docs.flutter.dev/app-architecture/recommendations Original source: https://drive.google.com/file/d/1LlppucPRV_7Kpp3kh07UDhWL39XAPyVI/view?usp=drivesdk https://drive.google.com/file/d/1o98InGRT4t8lKLoSczaM3cwtbKewfLj1/view?usp=drivesdk
M064 | P2 | Core | Mobile performance | Measure release/profile launch, frame timing, camera memory and location battery cost | Not started |  | Performance QA + Flutter/native | M | M053; M056; M060 | Representative lower-cost Android and iPhone reports include configuration and p50/p95; accepted budgets cover startup, jank, memory, upload size, battery/network and admin lists; optimize only demonstrated bottlenecks. | No device benchmark establishes current performance; framework replacement would not resolve measured contract defects. | audit/flutter_review.md performance section; audit/platform_review.md device matrix; https://docs.flutter.dev/perf/best-practices
M065 | P1 | Core | Privacy inventory and notices | Publish a current feature/data inventory and reconcile privacy, terms and deletion copy | Not started |  | Privacy + product + engineering | M | M068; M024 if paid features enabled; M067 for enabled high-risk features | Each enabled field/store/processor has purpose, role, destination, retention and deletion mapping; public/store/in-app copy matches actual scope; superseded statements are labelled historical and no anonymous-template claim remains. | May/June notices describe anonymous login and AWS verification while September code uses WhatsApp and Cloudflare recipient lookup. | landing/privacy-policy.html; landing/terms-and-conditions.html; landing/account-deletion.html; docs/compliance/data-inventory.md; audit/privacy_review.md PRIV-01,PRIV-06 Original source: https://drive.google.com/file/d/1zQH0mmbadmfJtnEBxNkyZUnkm3Uv2LQJ/view?usp=drivesdk https://drive.google.com/file/d/1cjZLmcOWDsYYYP_-f0mYAFww9QnZ4OHp/view?usp=drivesdk
M066 | P1 | Core | Governance evidence | Record operator/controller registration, overseas-storage scope and accountable DPO | Not started |  | Qualified Rwanda counsel + privacy lead | M | Operator and enabled-feature inventory draft | Current official requirements and entity applicability checked; certificate/expiry/conditions and DPO appointment/contact documented; outstanding conditions have owners and affected-feature decisions. | Organization-specific certificates and conditions were not supplied; missing evidence is not proof of nonregistration. | audit/privacy_review.md section 1; https://cyber.gov.rw/fileadmin/user_upload/NCSA/Documents/Laws/OG_Special_of_15.10.2021_Amakuru_bwite.pdf; https://www.risa.gov.rw/data-protection-and-privacy-law
M067 | P1 | Face | Impact assessment | Complete a scoped impact/risk assessment for face lookup, location and institutional SMS | Not started |  | Privacy lead + qualified counsel + security | M | M024; M026; M056; M066 | Document actual no-liveness lookup purpose, consent/withdrawal, false-match risk, unknown persons, retention, security and alternatives; approve residual risk before affected feature activation. | Sensitive templates, bystanders/third-party senders and live location require purpose-specific grounds, safeguards and residual-risk decisions. | docs/product/face-ussd-20260920/APPROVAL.md; audit/privacy_review.md section 1 and PR-T03; https://www.risa.gov.rw/data-protection-and-privacy-law Original source: https://drive.google.com/file/d/1Ql7MVmCXqbgiB8DwU11kDXAjNmRtYF-k/view?usp=drivesdk
M068 | P1 | Core | Processors and data location | Verify actual vendor regions, contracts, subprocessors and lawful overseas arrangements | Not started |  | Privacy + platform + qualified counsel | M | M066 | Supabase primary/backups/logs and Cloudflare inference/vectors/logs plus Meta/OpenAI/analytics data flows recorded; accepted agreements and lawful arrangements match actual use; unsupported Rwanda-only/region promises removed. | Configured providers do not establish data location or contractual authority; Vectorize is outside some Cloudflare locality controls. | audit/privacy_review.md section 3; https://developers.cloudflare.com/data-localization/compatibility/; https://developers.cloudflare.com/containers/concepts/placement/; https://supabase.com/docs/guides/platform/regions Original source: https://drive.google.com/drive/folders/1IOYNDX1ALDVg9Mx6zXM1yZe8HP0xl7CG https://drive.google.com/drive/folders/1VeEGNOl32YcDgwjU7FZhqwcj_7Vyqy6c
M069 | P1 | Core | Account deletion | Implement authenticated deletion initiation, status and cross-store completion | Not started |  | Backend + Flutter + privacy + support | L | M007; M008; M065; M039 if Face enabled | Synthetic account deletion covers Auth sessions, SQL, Storage, push, vectors and applicable analytics; retries and legal retention exceptions tracked; in-app and web initiation/status work without hidden manual-only steps. | Current support-mail surface and face-only removal do not prove full account deletion across enabled data classes. | lib/features/profile/presentation/profile_screen.dart; landing/account-deletion.html; audit/backend_review.md B-13; audit/flutter_review.md FL-09; audit/privacy_review.md PRIV-04 Original source: https://drive.google.com/file/d/18urTvEQkxOoO54RdPEqF3hG6P_FLgWYX/view?usp=drivesdk https://drive.google.com/file/d/1cwyLRfUildTAHReym4ReNQOWDOGYNq7K/view?usp=drivesdk
M070 | P1 | Core | Retention and requests | Set data-class retention and implement receipt-based request deadlines with verified purge | Not started |  | Privacy + backend + support | M | M065; M069; retention and backup design | Approve periods, triggers, exceptions, backup treatment and purge owners. Within 30 days of request receipt, provide written/electronic substantive erasure notification under applicable rules; acknowledgement alone is insufficient. Verify completed deletion or justified retained-data decisions, staging purges and deletion replay after restore. | Current retention is vague and deletion page starts the response clock after verification; restores can reintroduce deleted data. | docs/compliance/data-inventory.md; landing/account-deletion.html; audit/privacy_review.md PRIV-05,PRIV-07; Rwanda Law 058/2021 Arts 23,52 Original source: https://drive.google.com/file/d/1cjZLmcOWDsYYYP_-f0mYAFww9QnZ4OHp/view?usp=drivesdk https://drive.google.com/file/d/1cwyLRfUildTAHReym4ReNQOWDOGYNq7K/view?usp=drivesdk
M071 | P1 | Face | Retired AWS resources | Inventory and obtain scoped authorization to retire old face-only AWS data and credentials | Not started |  | Platform + security + privacy | M | M001; M065 | Read-only account/resource inventory and owner decision; separately authorized named-resource deletion/key retirement receipts; no active AWS fallback and no unrelated shared resource loss. | Retired source paths do not demonstrate deletion of live collections or old IAM authority. | docs/operations/face-ussd-runbook.md; audit/privacy_review.md PRIV-12; audit/operations_review.md O21 Original source: https://drive.google.com/file/d/1vZVjzSVzBGDPvEDyH5wTO996VJbSCDGt/view?usp=drivesdk
M072 | P1 | Core | Age boundaries | Decide and implement proportionate age rules for passenger, driver and face functions | Not started |  | Product + privacy + qualified counsel | M | M065; M067 | Consistent per-role policy and proportionate declaration/restriction; underage reports and applicable guardian handling documented; no unnecessary identity-document collection introduced. | Public policy says 16 but inspected account/face paths do not enforce an age-specific rule. | landing/terms-and-conditions.html; landing/privacy-policy.html; audit/privacy_review.md PRIV-11; Rwanda Law 058/2021 Art 9 Original source: https://drive.google.com/file/d/1zQH0mmbadmfJtnEBxNkyZUnkm3Uv2LQJ/view?usp=drivesdk https://drive.google.com/file/d/1QOqPjNkyg8GlrM5Nmh1pLQlqLHpKHeTY/view?usp=drivesdk
M073 | P1 | Core | WhatsApp operating contract | Verify live authentication templates/delivery and separate marketing permissions | Not started |  | Messaging operations + backend + privacy | M | M012; M068; M091 | Approved WABA/number/template/category/language/components and supported Graph version recorded; real device delivery/resend/expired-code/outage recovery tested; campaign opt-out suppresses future promotional sends. | Configurable template payloads and API version do not prove live approval; login intent is not permission for campaigns. | supabase/functions/_shared/whatsapp-cloud.ts; audit/privacy_review.md sections 4, PRIV-10; https://whatsappbusiness.com/policy/; https://whatsappbusiness.com/products/conversation-categories/authentication/ Original source: https://drive.google.com/file/d/12qJwdf1UXnXqeY3d1I9ttnFYZhMZ77pT/view?usp=drivesdk
M074 | P1 | Core | CI correctness | Repair Actions pin validation to permit local reusable workflows and reject unpinned remote actions | Not started |  | DevOps | S | None | Actual source pin gate exits zero; valid local fixture passes and tagged/unpinned remote fixtures fail; parser distinguishes reusable workflow and remote action syntax. | Mandatory current pin script fails on valid ./.github/workflows/cloudflare-pwa.yml and blocks its calling CI job. | scripts/ci/check_github_actions_pinned.sh:12-17; .github/workflows/cloudflare-pages.yml:18; audit/operations_review.md OPS-01; audit/operations_validation.json Original source: https://drive.google.com/file/d/1At2ltdJVK8kpZQsV92HybbTqStAYqLvs/view?usp=drivesdk https://drive.google.com/file/d/1-OxjhMZxQ5KAMfLShQpBK7KFY4hhAwk_/view?usp=drivesdk
M075 | P1 | Core | Release gate truth | Make skipped/unavailable required checks non-releasable and wire aggregate gates into promotion | Not started |  | Release engineer + DevOps | M | M074 | Production invocation rejects disabling mandatory child checks; pass/failed/skipped/unavailable have distinct status; Android/PWA/services promotion requires all applicable gates for one exact artifact. | Nested helper prints PASS when both tests are skipped; release paths do not uniformly require aggregate evidence. | scripts/qa/verify_mobio_feature_readiness.sh; scripts/release/go_no_go_check.sh; .github/workflows; audit/validation_review.md IV-06; audit/operations_review.md OPS-02 Original source: https://drive.google.com/file/d/1MjilpuX-zUbut_W8msIPYSkYByKKEDyS/view?usp=drivesdk https://drive.google.com/file/d/1yPZR9Gs5lDexBEVawYsye7XvWWZ4NvAj/view?usp=drivesdk
M076 | P1 | Core | Visual acceptance | Resolve unaccepted reference goldens against the approved design and rerun the full Flutter suite | Not started |  | QA + design + Flutter | M | M074 | Each difference classified as intended or regression; only reviewed baselines change; complete suite including reference goldens passes on pinned toolchain with revision-linked results. | Historical 812 passing tests excluded standalone reference goldens while regular CI includes them. | docs/product/face-ussd-20260920/IMPLEMENTATION_REPORT.md; test reference golden suite; .github/workflows/ci.yml; audit/operations_review.md OPS-11 Original source: https://drive.google.com/file/d/13toaULZ0qSRF3mcOySrbey9WeHRMSidj/view?usp=drivesdk https://drive.google.com/file/d/1M2OuVXPXNwY34djuk7wjKwcYCIb6BUUv/view?usp=drivesdk
M077 | P1 | Core | Coverage in CI | Add required checks for every shipped implementation and native collector | Not started |  | DevOps + subsystem owners | M | M074; M075 | Flutter/Deno/Node/Python, real Linux image/model smoke, Android bridge unit/component and native release jobs run on applicable changes; a deliberate regression in each implementation blocks promotion. | Worker/Python/container/face SQL and SMS bridge changes are not all represented in required current CI. | cloudflare/face-service; services/face-inference; apps/momobio_sms_bridge; .github/workflows; audit/operations_review.md OPS-03 Original source: https://drive.google.com/drive/folders/19o_yD0w45xyCjxqocqBX8S9_0aHuBfgO https://drive.google.com/drive/folders/11tIJA6XGeIAUuubqLpB4LNw2zwvt1qXT
M078 | P1 | Core | Database rehearsal | Run all migrations on clean PostgreSQL 17 and a representative forward-upgrade copy | Not started |  | DBA + backend QA | L | M003; M015; M017; M018; M019 | Clean reset and sanitized production-like upgrade succeed; effective functions/policies/grants/extensions/jobs diff to intended state; constraints and data reconciliation pass; rollback/forward-repair plan reviewed. | Static migration review cannot prove full effective schema, order, runtime compatibility or production drift. | supabase/migrations; audit/backend_effective_functions_static.json; audit/backend_review.md B-T09; audit/validation_review.md execution limits Original source: https://drive.google.com/drive/folders/1HA6rpjdCjYgaKurjtxuEgkL6y1DJRuU7
M079 | P1 | Core | Adversarial authorization | Run a real database/Edge authorization and transaction matrix after remediation | Not started |  | Security QA + backend | L | M003; M004; M015; M016; M078 | Anonymous, expired/revoked, passenger, driver, owner/nonowner, admin-purpose and service roles tested through real interfaces; identity, direct-update, concurrency, replay and cross-tenant negatives pass. | Mock/source reproduction is strong evidence of risk but not an executed RLS/transaction/security integration result. | audit/validation_review.md; audit/backend_review.md; supabase/functions; supabase/migrations Original source: https://drive.google.com/drive/folders/1HA6rpjdCjYgaKurjtxuEgkL6y1DJRuU7 https://drive.google.com/drive/folders/1l5OIu5zSjUzWrwkfS9W9cBN2ocmKUI07
M080 | P1 | Core | Production controls | Read back actual repository/environment protections, secrets and promotion roles | Not started |  | Security + release owner | S | M001; M002; M075 | Current branch/environment rules, required checks, reviewer separation and secret scope recorded for actual repository/account plan; least-privilege deployment roles and emergency path tested without publishing. | Workflow YAML and PROD_RELEASE_ENABLED variables do not establish remote protection rules or account authority. | audit/operations_review.md O14; .github/workflows; audit/git_metadata provenance Original source: https://drive.google.com/drive/folders/1Do2o7oLKmnkMMkm4NtPTCchKEN_zu4tK
M081 | P1 | Core | Release evidence | Bind source, artifacts, migrations, model policy and approvals in a structured release manifest | Not started |  | Release engineer | M | M075; M078; M080 | Exact commit plus working-tree state, artifact hashes, version equality, migration/model identifiers, environment, reviewer/date and full check receipts validated; stale/example/wrong-artifact/prefix fixtures rejected. | Current acknowledgement/file-presence checks accept weak evidence and a version prefix can match the wrong Play version. | scripts/release/go_no_go_check.sh:40-67,123; docs/product/face-ussd-20260920/IMPLEMENTATION_REPORT.md; audit/operations_review.md OPS-10 Original source: https://drive.google.com/file/d/13toaULZ0qSRF3mcOySrbey9WeHRMSidj/view?usp=drivesdk https://drive.google.com/file/d/1yPZR9Gs5lDexBEVawYsye7XvWWZ4NvAj/view?usp=drivesdk
M082 | P2 | Core | Dependency security | Pin reproducible toolchains and cover all dependency/container ecosystems with update and advisory review | Not started |  | DevSecOps + maintainers | M | M077 | Deno/Node/pnpm/Wrangler/container toolchain fixed to tested versions; update coverage and actual advisory triage documented; clean builds reproduce; upgrades are risk-reviewed rather than indiscriminate. | Current updates omit new npm/Python/Docker paths; Deno and Wrangler invocations can drift. | .github/dependabot.yml; .github/workflows; cloudflare/face-service/package.json; services/face-inference; audit/operations_review.md OPS-08 Original source: https://drive.google.com/file/d/1_LsmRout-ReXNuDQEpeAFl8lTKtAAImX/view?usp=drivesdk https://drive.google.com/drive/folders/1kQsuocMDtXnp20aRwLKuojC9WoYP7bjd
M083 | P2 | Core | Supply-chain records | Produce verified SBOM/provenance and retain licences, symbols and source maps for supported releases | Not started |  | DevSecOps + release | M | M081; M082 | Distributed artifact SBOM and provenance verify against release hashes; model/SDK licences archived; symbol/source-map access and crash symbolication tested for supported versions. | No repository workflow establishes release component inventory, attestations or long-lived diagnostic artifact retention. | audit/operations_review.md OPS-08,O16; https://docs.github.com/en/actions/concepts/security/artifact-attestations
M084 | P1 | Core | Observability | Instrument privacy-safe service and client health with owned actionable alerts | Not started |  | SRE + backend + mobile | M | M032; M034; M037; M056 | Dashboards cover auth, latency/errors, face busy/cleanup, receipt-to-credit, notification backlog, crashes/ANRs and stale presence; named owners/budgets; induced failure alerts correctly with no raw faces, vectors, OTPs or financial identifiers. | Face Worker observability is disabled and operational runbooks lack concrete SLO/alert ownership; provider platform metrics alone are insufficient. | cloudflare/face-service/wrangler.jsonc:8; services/face-inference/server.py:7; docs/operations/README.md; audit/operations_review.md OPS-06 Original source: https://drive.google.com/file/d/10XfUXtvPdRtBHiWA9yhRro_v6glk8XvJ/view?usp=drivesdk https://drive.google.com/file/d/1UjDIz7n8Uk4OhFXYNLmB3vShd_P1ziTY/view?usp=drivesdk
M085 | P1 | Core | Recovery | Define RPO/RTO and rehearse isolated database, Storage, configuration and vector recovery | Not started |  | DBA + SRE + privacy | L | M065; M070; M078 | Timed isolated restore with outbound jobs disabled meets approved loss/time objectives; SQL/objects/permissions/idempotency reconcile; deletion tombstones reapplied; explicitly choose protected vector restore or consented reenrollment. | Schema backup and database backup alone do not restore customer data, Storage objects, secrets/bindings or enrollment state. | docs/operations/face-ussd-runbook.md; audit/operations_review.md OPS-07; https://supabase.com/docs/guides/platform/backups Original source: https://drive.google.com/file/d/1vZVjzSVzBGDPvEDyH5wTO996VJbSCDGt/view?usp=drivesdk https://drive.google.com/drive/folders/1VeEGNOl32YcDgwjU7FZhqwcj_7Vyqy6c
M086 | P1 | Core | Incident response | Rehearse security/privacy/financial incident ownership and escalation | Not started |  | Security + privacy + SRE + payments | M | M001; M023; M066; M084 | Tabletop covers key exposure, wrong credit, lost collector and biometric/PII event; evidence preservation, containment and contacts tested; applicable Rwanda 48-hour notice/72-hour report clocks reviewed by counsel. | Public folder exposure and financial authority risks make an actionable response process necessary; organization-specific response evidence was not supplied. | audit/privacy_review.md PR-T19; audit/operations_review.md OPS-06; Rwanda Law 058/2021 Arts 43-44 Official source: https://cyber.gov.rw/fileadmin/user_upload/NCSA/Documents/Laws/OG_Special_of_15.10.2021_Amakuru_bwite.pdf
M087 | P1 | Core | Rollout and rollback | Exercise staged release, kill switches and compatible rollback for each enabled surface | Not started |  | Release + SRE + product | M | M062; M081; M084; M085 | Internal/staged promotion uses defined stop criteria; last-known-good artifacts/configs identified; schema compatibility or forward repair tested; face can be disabled while accepted manual/QR flows continue. | No current end-to-end rollback receipt proves coordinated recovery across app, web, Edge, schema and face services. | docs/operations/face-ussd-runbook.md; .github/workflows/android-release.yml; audit/operations_review.md O19 Original source: https://drive.google.com/file/d/1w_uWBznlC3jNzjHFewL1FSjnmE9qVCmO/view?usp=drivesdk https://drive.google.com/file/d/1vZVjzSVzBGDPvEDyH5wTO996VJbSCDGt/view?usp=drivesdk
M088 | P1 | Core | Launch acceptance | Run a version-bound end-to-end matrix on staging and release-candidate devices | Not started |  | QA lead + release + feature owners | L | M044; M046; M049; M052; M060; M073; M079; M081; M040 if Face enabled | Exact release journey results cover OTP, discovery/posting, chat/moderation, account lifecycle, manual/QR, chosen paid features and optional face/SMS; offline/denied/timeout/restart cases recorded with clear pass/blocked status. | Historical passes and fixture tests do not verify current real providers, migrations, operator handoff or signed devices. | audit/platform_review.md device matrix; audit/flutter_review.md acceptance; audit/validation_review.md section 3; docs/product/face-ussd-20260920/IMPLEMENTATION_REPORT.md Original source: https://drive.google.com/file/d/13toaULZ0qSRF3mcOySrbey9WeHRMSidj/view?usp=drivesdk
M089 | P1 | Core | Support and moderation | Operationalize existing report/block controls, account recovery and financial exception handling | Not started |  | Support operations + product + trust/safety | M | M009; M023; M069; M073; M084 | Named queues/response targets and escalation paths; staged report/block/unblock, lost WhatsApp access, deletion and disputed receipt drills close with an audit trail; no PIN collection or improvised auth bypass. | Client moderation controls exist, but launch requires staffed ownership, escalation and abuse/support outcomes. | lib/features/chat/data/chat_service.dart:63-143; lib/features/chat/presentation/chat_screen.dart; docs/operations/README.md; audit/flutter_review.md strengths; audit/privacy_review.md section 4 Original source: https://drive.google.com/file/d/12n5FHLFgRu9NPOsRAb9HFFgWAIIaol3b/view?usp=drivesdk https://drive.google.com/file/d/1BrgbaLACv8-s6Hop1vdwBt8E9gvQ61E_/view?usp=drivesdk
M090 | P2 | Core | Source and scope documentation | Publish a clean reproducible source manifest and one current feature/release status map | Not started |  | Repository maintainer + product + release | M | M001; M081 | Source, generated files and intentionally retained release evidence separated without indiscriminate deletion; exact provenance/dirty state recorded; current scope links superseded documents; clean checkout reproduces required builds. | Drive includes generated caches and older conflicting evidence; snapshot bytes are not automatically an immutable Git release. | audit/git_index_inventory.json; audit/root_inventory.json; README.md; AGENTS.md; docs/product/face-ussd-20260920/APPROVAL.md; audit/operations_review.md OPS-12 Original source: https://drive.google.com/file/d/1Ql7MVmCXqbgiB8DwU11kDXAjNmRtYF-k/view?usp=drivesdk https://drive.google.com/file/d/1vnBbpRv1TLxzzBiWw9oHhqdKtdegRYSa/view?usp=drivesdk
M091 | P1 | Core | Provider resilience and budgets | Bound external calls and enforce durable rate/cost controls for OTP, maps and AI paths | Not started |  | Backend + SRE + security | M | M012; M032 | Shared per-user/device/collector admission and cost limits survive cold starts; deadlines, bounded retries and circuit recovery tested; legitimate outage recovery works; retired route computation stays retired. | Maps uses process-memory rate state and lacks an application timeout; external failures and repeated calls can amplify latency and spend. | supabase/functions/maps-gateway/index.ts:52-85,244-255; supabase/functions/_shared/whatsapp-cloud.ts; audit/backend_review.md B-09,B-T15,B-T17 Original source: https://drive.google.com/file/d/12qJwdf1UXnXqeY3d1I9ttnFYZhMZ77pT/view?usp=drivesdk https://drive.google.com/file/d/190BYE2qz7Hc58j2hl-xYbAf9ELpsk-2j/view?usp=drivesdk
M092 | P2 | Core | Notification delivery | Use a durable notification outbox with leases, bounded retry and token lifecycle | Not started |  | Backend + SRE | M | M008; M084 | Notification/token idempotency, lease recovery, TTL, consent, backoff and invalid-token removal work under duplicate dispatch/provider outage; backlog age is visible; no unbounded OAuth/send loop. | Current HTTP dispatch can repeat sends and lacks a durable per-notification/token claim with bounded retry state. | supabase/migrations/20260914203228_repair_notification_trigger_http_dispatch.sql; supabase/functions/send-push/index.ts:363-462; audit/backend_review.md B-12 Original source: https://drive.google.com/file/d/1_8s_2FN71Qop1DxBFlwWEyQKzj6-S_EG/view?usp=drivesdk https://drive.google.com/file/d/16QDr4XE1T00Pm357hzMubBmi_sn1Op11/view?usp=drivesdk
M093 | P2 | Core | Database performance | Load-test bounded discovery, realtime, chat history and financial queries at launch/next-stage volume | Not started |  | DBA + performance + backend | M | M056; M078; M084 | Representative cardinalities and concurrency with EXPLAIN/query statistics meet chosen latency budget; indexes/caps/pagination based on measured plans; retention does not break reconciliation or deletion. | Unbounded nearby limits and growing tables can affect latency, privacy and resource cost; no current production-scale query evidence was executed. | supabase/migrations/20260915003031_harden_driver_discovery_identity.sql; audit/backend_review.md B-07,B-T23; audit/flutter_review.md FL-12 Original source: https://drive.google.com/file/d/13WznvHZhWTofuAfvMnxlKTPdDtwfs6AX/view?usp=drivesdk
M094 | P2 | Core | Operating economics | Build an observed launch cost model and usage budget with explicit assumptions | Not started |  | Product + finance + SRE | M | M023; M041; M084; M091 | Current account tariffs and observed requests per successful journey drive low/base/peak forecast; budget alerts and owner-approved service caps tested; no invented Rwanda rate or fixed per-scan promise. | No measured unit economics were established across paid OTP, AI parsing, containers, vectors, database, storage and egress. | audit/operations_review.md OPS-05; audit/privacy_review.md section 4; https://developers.cloudflare.com/containers/platform/pricing/; https://whatsappbusiness.com/products/platform-pricing/ Original source: https://drive.google.com/drive/folders/1IOYNDX1ALDVg9Mx6zXM1yZe8HP0xl7CG
M095 | P3 | Face | Measured optimization | Optimize inference pool/index checks only after accepted baseline capacity data | Not started |  | Performance + platform | M | M038; M041; M084; M094 | Measured bottleneck and benefit threshold documented; bounded pool or compatibility-cache change preserves model/consent correctness and cost cap; before/after load and failure results demonstrate improvement. | Single-instance serialized design is a controlled baseline; automatic scaling or broad rewrites are not justified without demand evidence. | cloudflare/face-service/src/handler.ts:90-165; services/face-inference/inference.py; audit/operations_review.md OPS-05; https://developers.cloudflare.com/containers/configuration/scaling-and-routing/ Original source: https://drive.google.com/file/d/1ZMe2Z6-28lqVhf4GD24uS02hOaPsgsYZ/view?usp=drivesdk https://drive.google.com/file/d/140d2FVWo8zH96uUG9K55Svsd5twTSLzR/view?usp=drivesdk